## Reloc
Data Before
[6 empty] | RF 1 |  | RF 2 |  | RF 3 |  | RF 4 |  | AAU 1 |  | AAU 2 |  | AAU 3 |  | MW 1 |  |  | MW 2 |  |  | MW 3 |  |  | MW 4
NO | Site ID Old | Site Name Old | Tenant | Site ID Tenant | Site Name Tenant | Height | Azimuth | Height2 | Azimuth3 | Height4 | Azimuth5 | Height6 | Azimuth7 | Height8 | Azimuth9 | Height10 | Azimuth11 | Height12 | Azimuth13 | Link | Height14 | Azimuth15 | Link16 | Height17 | Azimuth18 | Link19 | Height20 | Azimuth21 | Link22 | Height23 | Azimuth24 | Site ID New | Site Name New | LATITUDE | LONGITUDE | CR // CRQ // XLWO | Start Dismantle | Start Reinstall | OA | Data After
1 | R1200302 | BANGUN PURBA | XLS | SUM-SU-LBP-0405 | BANGUN PURBA Relocation | 69 | 0 | 69 | 180 | 69 | 280 | [8 empty] | to SUM-SU-LBP-0023 | 54 | 130 | to SUM-SU-SRH-1245 | 52 | 190 | to SUM-SU-LBP-0022 | 52 | 120 | to SUM-SU-SRH-8224 | 53 | 240 | ID-SU-03892 | BANGUN PURBA | 3.37141 | 98.8149 | XLWO-20260522-00000051 | 2026-05-26 | 2026-05-27 | 2026-05-29 | RF 1 |  | RF 2 |  | RF 3 |  | RF 4 |  | AAU 1 |  | AAU 2 |  | AAU 3 |  | MW 1 |  |  | MW 2 |  |  | MW 3 |  |  | MW 4
2 | R3350421 | KARANGJUNTI | IOH | 14BRS0006 | KARANGJUNTI_CM | 53 | 120 | 53 | 215 | 53 | 340 | [20 empty] | ID-JT-17956 | LOSARI KARANGJUNTI | -6.91628 | 108.7941 | CR-20260529-00000297 | 2026-06-03 | 2026-06-06 | 2026-06-08 | Height | Azimuth | Height | Azimuth | Height | Azimuth | Height | Azimuth | Height | Azimuth | Height | Azimuth | Height | Azimuth | Link | Height | Azimuth | Link | Height | Azimuth | Link | Height | Azimuth | Link | Height | Azimuth
3 | R3350421 | KARANGJUNTI | XLS | JAW-JT-BBS-0007 | KARANGJUNTI Relocation | 68 | 0 | 68 | 160 | 68 | 310 | [20 empty] | ID-JT-17956 | LOSARI KARANGJUNTI | -6.91429 | 108.7941 | XLWO-20260619-00006228 | 2026-06-22 | 2026-06-23 | 2026-06-27 | 68 | 0 | 68 | 180 | 68 | 280 | [8 empty] | to SUM-SU-LBP-0023 | 54 | 130 | SUM-SU-SRH-1245 | 51 | 190 | to SUM-SU-LBP-0022 | 60 | 120 | to SUM-SU-SRH-8224 | 53 | 240
4 | E3200525 | GEDUNG_LIPPO | IOH | 13BDG0292 | IMGEDUNG_LIPPO_EP | 3 | 30 | [24 empty] | ID-JB-03467 | PAKUHAJI WETAN NGAMPRAH | -6.82802 | 10754079 |  | 2025-09-11 |  |  | 53 | 30 | 53 | 120 | 53 | 240 | [8 empty] | to 14BRS0013 | 51 | 40
5 | E8200008 | JAILOLO | IOH | 32HBR0001 | JAILOLO_EP | 58 | 10 | 58 | 180 | 58 | 235 | [8 empty] | to 32HBR0002 | 54 | 35 | to 32HBR0011 | 33 | 75 | to 32TER0004 main | 44 | 200 | to 32TER0004 standby | 29 | 200 | ID-MU-14641 | GUAEMAADU JAILOLO | 1.0616 | 127.4636 | CR-20251215-00000284 | 2025-12-16 | 2025-12-21 | 2026-01-01
6 | R3270681 | JAPARA KUNINGAN | XLS | JAW-JB-KNG-1359 | JAPARA KUNINGAN | [26 empty] | E3200649 | JAPARA | -6.89649 | 108.51681 |  |  |  |  | 47 | 20
7 | E3200182 | GEULIS_RESORT | XLS | JAW-JB-CBI-0515 | GEULIS RESORT BOGOR | 51 | 190 | 51 | 270 | 51 | 320 | [8 empty] | to JAW-JB-BGR-0421 | 49 | 280 | [9 empty] | ID-JB-14444 | GEULIS SUKARAJA | -6.6318 | 106.8663 | XLWO-20260804-00000177 | 2026-08-10 | 2026-08-11 |  | 60 | 45 | 60 | 190 | 60 | 240 | [8 empty] | to 32HBR0002 | 71 | 10 | to 32HBR0011 | 55 | 110 | to 32TER0004 main | 50 | 205 | to 32TER0004 standby | 80 | 205
8 | E3200182 | GEULIS_RESORT | IOH | 13CBN0771 | GEULIS_RESORT_EP | 67 | 20 | 67 | 210 | 67 | 320 | [20 empty] | ID-JB-14444 | GEULIS SUKARAJA | -6.6318 | 106.8663 | CR-20260804-00000400 CR-20260804-00000411
9 | R3270184 | SETRAINDAH BARAT | IOH | 13BDG0084 | SETRAINDAHBARAT_CM | 18 | 90 | 18 | 150 | 18 | 330 | [28 empty] | 70 |  | 70 |  | 70
10 | R3270184 | SETRAINDAH BARAT | XLS | JAW-JB-BDG-0045 | SETRA INDAH BARAT | 18 | 30 | 18 | 130 | 18 | 320 |  |  | 18 | 50 | 18 | 230 | 18 | 330 | [20 empty] | 70 |  | 70 |  | 70

## Account
No | Account Project | Vendor | Project | Coverage Area
1 | SGP-TI-Nasional | PT. Sempurna Global Pertama | Telkom Infra | Nasional
2 | SGI-ZTE_XLSmart-Nasional | PT. Star Global Indonesia | ZTE_XLSmart | Nasional
3 | CMI-RBLD-Nasional | PT. Centratama Menara Indonesi | Rebuild | Nasional
4 | CMI-TMAIN-Nasional | PT. Centratama Menara Indonesi | Tower Maintenance | Nasional
5 | CMI-COLO-Nasional | PT. Centratama Menara Indonesi | Colocation | Nasional
6 | CMI-MAC-Nasional | PT. Centratama Menara Indonesi | MAC | Nasional
7 | MSG-RTGS-Bengkulu | PT. Mitra Sistematika Global | Remote Terminal Ground Segment | Bengkulu
8 | DMT-All-Nasional | PT. Dayamitra Telekomunikasi | All | Nasional
9 | CCSI-XLS_PLN-EJ | PT. China Comservice Indonesia | XLSmart_PLN | East Java
10 | MSG-COLO_IOH-Nasional | PT. Mitra Sistematika Global | Colocation_IOH | Nasional
11 | MSG-STH-Kalimantan | PT. Mitra Sistematika Global | Strengthening | Kalimantan
12 | CMI-TIP-Nasional | PT. Centratama Menara Indonesia | Tower Inspection Preventive | Nasional
13 | CCSI-XLS_PLN-CJ | PT. China Comservice Indonesia | XLSmart_PLN | Central Java
14 | CCSI-XLS_PLN-Kalimantan | PT. China Comservice Indonesia | XLSmart_PLN | Kalimantan
15 | CCSI-IBC-Nasional | PT. China Comservice Indonesia | In-Building Coverage | Nasional
16 | CCSI-XLS_PLN-Sulawesi | PT. China Comservice Indonesia | XLSmart_PLN | Sulawesi
17 | CMI-RLC-Nasional | PT. Centratama Menara Indonesi | Relocation | Nasional
18 | CMI-SURGE-Nasional | PT. Centratama Menara Indonesi | SURGE | Nasional

## List Material Inbound
Site ID | Site Name | Tenant | Material | UoM | Qty | SN | Remark | Inbound
E3500375 | MERPATI | XLS | Rack Recty | unit | 1
E3500375 | MERPATI | XLS | Recty EATON | unit | 1
E3500375 | MERPATI | XLS | Module recty | pcs | 6
E3500375 | MERPATI | XLS | RTN Huawei 950 | unit | 1
E3500375 | MERPATI | XLS | CSHU + 1 SFP | unit | 1
E3500375 | MERPATI | XLS | Fan RTN 950 | unit | 1
E3500375 | MERPATI | XLS | ISU 2 | pcs | 1
E3500375 | MERPATI | XLS | DCPD | pcs | 2
E3500375 | MERPATI | XLS | Kabel DCPD biru | tarikan | 4
E3500375 | MERPATI | XLS | Kabel DCPD hitam | tarikan | 4
E3500375 | MERPATI | XLS | BBU V9200 | unit | 1 | 219634374099
E3500375 | MERPATI | XLS | VBPe2q | pcs | 1
E3500375 | MERPATI | XLS | VPDc1 | pcs | 1
E3500375 | MERPATI | XLS | VEMC4 | pcs | 1
E3500375 | MERPATI | XLS | VBPE3q | pcs | 1
E3500375 | MERPATI | XLS | VSWd1 | pcs | 1
E3500375 | MERPATI | XLS | SFP (VBPE2q) | pcs | 6
E3500375 | MERPATI | XLS | SFP (VBPE3q) | pcs | 5
E3500375 | MERPATI | XLS | SFP (VSWd1) | pcs | 2
E3500375 | MERPATI | XLS | Casing GPS | pcs | 1
E3500375 | MERPATI | XLS | LPU2 | pcs | 1 | 219639300831
E3500375 | MERPATI | XLS | BLP2 | pcs | 2 | 200145 200343
E3500375 | MERPATI | XLS | SCU | pcs | 1 | 21964195814
E3500375 | MERPATI | XLS | 2XCTN 6120H-SC | pcs | 1 | D80AE69CFF38
E3500375 | MERPATI | XLS | SFP (2XCTN) | pcs | 3
E3500375 | MERPATI | XLS | PW1DC (2XCTN) | pcs | 2
E3500375 | MERPATI | XLS | Battery ZTE ZXESM R311 | pcs | 3
E3500375 | MERPATI | XLS | Kabel power batt (biru) | tarikan | 3
E3500375 | MERPATI | XLS | Kabel power batt (hitam) | tarikan | 3
E3500375 | MERPATI | XLS | Kabel grounding batt | tarikan | 3
E3500375 | MERPATI | XLS | Kabel power BBU (biru-hitam) | tarikan | 1
E3500375 | MERPATI | XLS | Kabel power RTN 950 (biru-hitam) | tarikan | 1
E3500375 | MERPATI | XLS | Kabel power AAU | tarikan | 3
E3500375 | MERPATI | XLS | Kabel power RRU | tarikan | 5
E3500375 | MERPATI | XLS | Kabel optic AAU | tarikan | 3
E3500375 | MERPATI | XLS | Kabel optic RRU | tarikan | 8
E3500375 | MERPATI | XLS | Antenna AAU +SFP 2pcs | unit | 3
E3500375 | MERPATI | XLS | RRU + SFP 1pcs | unit | 5
E3500375 | MERPATI | XLS | Antanna RF | unit | 3
E3500375 | MERPATI | XLS | Jumper Antenna RF | pcs | 20
E3500375 | MERPATI | XLS | Kabel AISG | tarikan | 6
E3500375 | MERPATI | XLS | Kabel grounding AAU | tarikan | 3
E3500375 | MERPATI | XLS | Kabel grounding RRU | tarikan | 1
E3500375 | MERPATI | XLS | Belting kabinet | pcs | 1
R3580695 | 3G_KUPANG KRAJAN | XLS | Antenna sector | pcs | 3 | KCK031874630005B KCK031874630011W KCK03187463000WW
R3580695 | 3G_KUPANG KRAJAN | XLS | RRU 9264 | pcs | 5 | 219645649504 219644276184 219644276183 219645649564 219645642979
R3580695 | 3G_KUPANG KRAJAN | XLS | Antena AAU A9652D | pcs | 3 | 219657872911 219657872872 219657873107
R3580695 | 3G_KUPANG KRAJAN | XLS | Battery Lithium | pcs | 3 | UB2410015715 UB2410013042 219648643871
R3580695 | 3G_KUPANG KRAJAN | XLS | ZXEDMSCU601B | pcs | 1 | 219653617801
R3580695 | 3G_KUPANG KRAJAN | XLS | DCPD 10B | pcs | 2 | 265625312394 265625312349
R3580695 | 3G_KUPANG KRAJAN | XLS | RTN 950 | pcs | 1 | 21021131746TBB90304
R3580695 | 3G_KUPANG KRAJAN | XLS | CSHU | pcs | 1 | 021YTFCNG6008019
R3580695 | 3G_KUPANG KRAJAN | XLS | EMGTA | pcs | 1 | E0247FB3ASE0-E5
R3580695 | 3G_KUPANG KRAJAN | XLS | EG4 | pcs | 1 | 020MXKNJ8004447
R3580695 | 3G_KUPANG KRAJAN | XLS | SP3S | pcs | 1 | 020SYWYOF2001053
R3580695 | 3G_KUPANG KRAJAN | XLS | ZXCTN G120H-SC | pcs | 1 | 210133047678
R3580695 | 3G_KUPANG KRAJAN | XLS | SFP ZXCTN | pcs | 4
R3580695 | 3G_KUPANG KRAJAN | XLS | ZX RAN V9200 | pcs | 1 | 219648108504
R3580695 | 3G_KUPANG KRAJAN | XLS | SFP RAN V9200 | pcs | 12
R3580695 | 3G_KUPANG KRAJAN | XLS | VSWD1 | pcs | 1 | N/A
R3580695 | 3G_KUPANG KRAJAN | XLS | VBPE3P | pcs | 1 | N/A
R3580695 | 3G_KUPANG KRAJAN | XLS | VBPE2Q | pcs | 1 | N/A
R3580695 | 3G_KUPANG KRAJAN | XLS | VEMC4 | pcs | 1 | N/A
R3580695 | 3G_KUPANG KRAJAN | XLS | VPDC1 | pcs | 1 | N/A
R3580695 | 3G_KUPANG KRAJAN | XLS | FAN RECTY | pcs | 2 | 2102120734N0EC000648
R3580695 | 3G_KUPANG KRAJAN | XLS | MODULE RECTY | pcs | 4 | 245777891 246069500 245403719 245706645
R3580695 | 3G_KUPANG KRAJAN | XLS | DISPLAY RECTY | pcs | 1 | N/A
R3580695 | 3G_KUPANG KRAJAN | XLS | RECTIFIER | unit | 1 | APS63G-000713
R3580695 | 3G_KUPANG KRAJAN | XLS | RACK RECTY | unit | 1 | SN BROKEN
R3580695 | 3G_KUPANG KRAJAN | XLS | KABEL POWER RRU | tarikan | 8
R3580695 | 3G_KUPANG KRAJAN | XLS | JUMPER | pcs | 18
R3580695 | 3G_KUPANG KRAJAN | XLS | OPTIC | tarikan | 8
E3500307 | MOROKREMBANGAN | IOH | Antenna sector | pcs | 3 | 13CN101991425 13CN101992628 Blur |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | CPRI | tarikan | 10 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | PMS | pcs | 1 | 2101073846NON8000434 |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | Battery ZTE | pcs | 1 | 123014631011 |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | MW NEC 1.2 + ODU | set | 1 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | MW RTN 0.6 + ODU | set | 1 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | Coax RTN | tarikan | 2 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | Jumper Antenna RF | pcs | 18 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | AHECC | pcs | 3 | KG252518520 RW242300802 KG252911421 |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | FXDB | pcs | 2 | L6130818055 L6130914051 |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | Kabel power biru-hitam | tarikan | 3 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | kabel hybrid | tarikan | 1 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | Rack Recty | set | 1 |  | Westindo | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | Sub Rack | pcs | 1 |  | Eltek | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | Modul ACDC | pcs | 4 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | IDU RTN | pcs | 1 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | AMIA | pcs | 1 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | ABIA | pcs | 1 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | ABIO | pcs | 1 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | IOH | ASIB | pcs | 1 |  |  | 2026-06-23
E3500307 | MOROKREMBANGAN | XLS | Sub Rack | set | 1 |  | 26.06.26 Diambil MS XLS | 2026-06-26
E3500307 | MOROKREMBANGAN | XLS | Modul subrack | pcs | 4 |  | 26.06.26 Diambil MS XLS | 2026-06-26
E3500307 | MOROKREMBANGAN | XLS | Modul SMU | pcs | 1 |  | 26.06.26 Diambil MS XLS | 2026-06-26
E3500307 | MOROKREMBANGAN | XLS | Kabel power battery | tarikan | 2 |  | 26.06.26 Diambil MS XLS | 2026-06-26
E3500307 | MOROKREMBANGAN | XLS | Antenna sector | pcs | 3
E3500307 | MOROKREMBANGAN | XLS | Antenna AAU | pcs | 2
E3500307 | MOROKREMBANGAN | XLS | RRU | pcs | 5
E3500307 | MOROKREMBANGAN | XLS | Kabel power AAU | tarikan | 2
E3500307 | MOROKREMBANGAN | XLS | Kabel power RRU | tarikan | 5
E3500307 | MOROKREMBANGAN | XLS | Jumper | pcs | 18
E3500307 | MOROKREMBANGAN | XLS | DCPD 10B | pcs | 2
E3500307 | MOROKREMBANGAN | XLS | ZXRAN V9200 | pcs | 1 | 219642055147
E3500307 | MOROKREMBANGAN | XLS | VBPe2q | pcs | 1
E3500307 | MOROKREMBANGAN | XLS | VPDc1 | pcs | 1
E3500307 | MOROKREMBANGAN | XLS | VBPe3p | pcs | 1
E3500307 | MOROKREMBANGAN | XLS | VSWd1 | pcs | 1
E3500307 | MOROKREMBANGAN | XLS | EMUA | pcs | 1
E3500307 | MOROKREMBANGAN | XLS | RTN 950A | pcs | 1
E3500307 | MOROKREMBANGAN | XLS | Battery ZTE | pcs | 3 | 219634692539 219634984146 219634983498
E3500307 | MOROKREMBANGAN | XLS | Cabinet | pcs | 1
R3580411 | PEGANTENAN | SF | Antenna 4.3-10 Int RE | pcs | 3
R3580412 | PEGANTENAN | SF | AISG 8 pin to DB15 Cable 5 M | pcs | 2
R3580413 | PEGANTENAN | SF | Filter 4.3-10 | pcs | 3
R3580414 | PEGANTENAN | SF | ZXSDR R8998G TDD 2300-2400MHz | pcs | 3
R3580415 | PEGANTENAN | SF | ZXSDR R8862A S8500 | pcs | 3
R3580416 | PEGANTENAN | SF | Connector RRU_Dismantle | pcs | 6
R3580417 | PEGANTENAN | SF | Bracket RUU Ints Kit Dism | pcs | 6
R3580418 | PEGANTENAN | SF | Connector GPS (I) | pcs | 1
R3580419 | PEGANTENAN | SF | Connector GPS (L) | pcs | 1
R3580420 | PEGANTENAN | SF | GPS Feeder | pcs | 1
R3580421 | PEGANTENAN | SF | 1/4 outer cond coax dism | tarikan | 10
R3580422 | PEGANTENAN | SF | Inst Kit Set Opr rack | set | 1
R3580423 | PEGANTENAN | SF | Frame with Fan | pcs | 1
R3580424 | PEGANTENAN | SF | Power module 3 | pcs | 2
R3580425 | PEGANTENAN | SF | Site Alarm | pcs | 1
R3580426 | PEGANTENAN | SF | Processing Unit | pcs | 1
R3580427 | PEGANTENAN | SF | CCE1B | pcs | 1
R3580428 | PEGANTENAN | SF | SFP SM-10KM | pcs | 1
R3580429 | PEGANTENAN | SF | BPN 2 | pcs | 2
R3580430 | PEGANTENAN | SF | SA Cable | pcs | 1
R3580431 | PEGANTENAN | SF | SFG 10G | pcs | 12
R3580432 | PEGANTENAN | SF | WTC09 | pcs | 1
R3580433 | PEGANTENAN | SF | NR8961 | pcs | 1
R3580434 | PEGANTENAN | SF | Coupler Kit | pcs | 1
R3580435 | PEGANTENAN | SF | Power Plug | pcs | 1
R3580436 | PEGANTENAN | SF | Waterproof Module | pcs | 1
R3580437 | PEGANTENAN | SF | Outdoor CAT5e FTP | tarikan | 35
R3580438 | PEGANTENAN | SF | B;ack Screened Cable | tarikan | 35
R3580439 | PEGANTENAN | SF | Antena pole rack | pcs | 2
R3580440 | PEGANTENAN | SF | Antena pole | pcs | 1
R3580441 | PEGANTENAN | SF | RF cable | pcs | 2
R3580442 | PEGANTENAN | SF | 116-OA-TH-1145 | pcs | 1
R3580443 | PEGANTENAN | SF | 116-OB-TH-1145 | pcs | 1
R3580444 | PEGANTENAN | SF | F4S-HM | pcs | 27
R3580445 | PEGANTENAN | SF | LC08 | pcs | 12
R3580446 | PEGANTENAN | SF | PR-43Mb-1250-2000Mb | pcs | 6
R3580447 | PEGANTENAN | XL | Rack BTS XL | pcs | 1
R3580448 | PEGANTENAN | XL | Rack Batray | pcs | 1
R3580449 | PEGANTENAN | XL | RACK DDF | pcs | 2
R3580450 | PEGANTENAN | XL | RACK OPTIK | pcs | 1
R3580451 | PEGANTENAN | XL | SMU02C | pcs | 1
R3580452 | PEGANTENAN | XL | BATRAY(GFMF) | pcs | 8
R3580453 | PEGANTENAN | XL | BATRAY (12TD) | pcs | 8
R3580454 | PEGANTENAN | XL | JUMPER PLAT BATRAY | pcs | 12
R3580455 | PEGANTENAN | XL | RRU5866 | pcs | 1
R3580456 | PEGANTENAN | XL | RRU5502 | pcs | 4
R3580457 | PEGANTENAN | XL | SFP-10G | pcs | 10
R3580458 | PEGANTENAN | XL | BBU5900 | pcs | 1
R3580459 | PEGANTENAN | XL | UBBPg2 | pcs | 1
R3580460 | PEGANTENAN | XL | UBBPd3 | pcs | 1
R3580461 | PEGANTENAN | XL | UBBP | pcs | 1
R3580462 | PEGANTENAN | XL | RTN950A | pcs | 2
R3580463 | PEGANTENAN | XL | CSHO | pcs | 2
R3580464 | PEGANTENAN | XL | SFP-2-125G | pcs | 4
R3580465 | PEGANTENAN | XL | MRFU9008 | pcs | 6
R3580466 | PEGANTENAN | XL | GPS (SCC800-S1) | pcs | 1
R3580467 | PEGANTENAN | XL | DCDU16D-02 | pcs | 1
R3580468 | PEGANTENAN | XL | EPU02D | pcs | 1
R3580469 | PEGANTENAN | XL | EPU02B | pcs | 1
R3580470 | PEGANTENAN | XL | OPTIK KABEL | tarikan | 5
R3580471 | PEGANTENAN | XL | CONECTOR POWER RRU | pcs | 5
R3580472 | PEGANTENAN | XL | RF JUMPER | pcs | 20
R3580473 | PEGANTENAN | XL | ANTENA SECTOR | pcs | 5
R3580474 | PEGANTENAN | XL | KABEL RET | pcs | 3
R3580475 | PEGANTENAN | XL | KABEL POWER BATRAI M | pcs | 4
R3580476 | PEGANTENAN | XL | KABEL POWER BATRAI H | pcs | 4
R6300019 | JL. KELAPA BJM | XLS | DCPDB10B | pcs | 1 | ZQ5625380269)
R6300020 | JL. KELAPA BJM | XLS | DCPDB10B | pcs | 1 | ZQ5625380267
R6300021 | JL. KELAPA BJM | XLS | MODULE EATON APR 48ES | pcs | 6 | 245192645 246560529 246560484 245192659 246560541 244585224
R6300022 | JL. KELAPA BJM | XLS | BBU ZTE ZXRAN V9200 | pcs | 1 | 219658736623
R6300023 | JL. KELAPA BJM | XLS | OTB | pcs | 1
R6300024 | JL. KELAPA BJM | XLS | ZTE LPU | pcs | 1 | 219658974417
R6300025 | JL. KELAPA BJM | XLS | ZXEDM SCU601B | pcs | 1 | 210132413134
R6300026 | JL. KELAPA BJM | XLS | BATT ZTE R311 | pcs | 1 | 219643079439
R6300027 | JL. KELAPA BJM | XLS | BATT HW ESM-48100B1 | pcs | 1 | EX2450067001
R6300028 | JL. KELAPA BJM | XLS | ESM-48100B1 | pcs | 1 | X2450073493
R6300029 | JL. KELAPA BJM | XLS | SFP ZTE 10G | pcs | 11
R6300030 | JL. KELAPA BJM | XLS | SFP ZTE 25G | pcs | 14
R6300031 | JL. KELAPA BJM | XLS | ANTENA ZTE AAU SECTOR 1 | pcs | 1 | 219657872977
R6300032 | JL. KELAPA BJM | XLS | ANTENA ZTE SECTOR 2 | pcs | 1 | 219657434607
R6300033 | JL. KELAPA BJM | XLS | ANTENA ZTE AAU SECTOR 3 | pcs | 1
R6300034 | JL. KELAPA BJM | XLS | RRU ZTE R9264 N1821 | pcs | 5 | 219656203200 219660088120 219660088140
R6300035 | JL. KELAPA BJM | XLS | RRU ZTE R9264 M728 | pcs | 2 | 219652643086 219652643038
R6300036 | JL. KELAPA BJM | XLS | ANTENA PROOSE | pcs | 3 | KCK031874G370052 KCK031874G37006Y KCK031874G3700005M
R6300037 | JL. KELAPA BJM | XLS | RECTIFIER EATON | pcs | 1
R6300038 | JL. KELAPA BJM | XLS | CABINET RBS TMCH 11 | pcs | 1
R6300039 | JL. KELAPA BJM | XLS | KABEL OPTIK | pcs | 11
R6300040 | JL. KELAPA BJM | XLS | KABEL POWER DC/RRU | pcs | 8
R6300041 | JL. KELAPA BJM | XLS | KABEL POWER AC | pcs | 1
R6300042 | JL. KELAPA BJM | XLS | ANTENA GPS DAN KABEL COAX | pcs | 1
R6300043 | JL. KELAPA BJM | XLS | GPS DAN KABEL CROSS | pcs | 1
R6300044 | JL. KELAPA BJM | XLS | ANTENA SECTOR 1 | pcs | 3
R6300045 | JL. KELAPA BJM | XLS | RRU ZTE SECTOR | pcs | 3 | 219267805084 219267805131 219267428494
R6300046 | JL. KELAPA BJM | XLS | RECTIFIER EATON | pcs | 1
R6300047 | JL. KELAPA BJM | XLS | CABINET ZTE | pcs | 1
R6300048 | JL. KELAPA BJM | XLS | KABEL POWER AC | tarikan | 5
R6300049 | JL. KELAPA BJM | XLS | KABEL POWER DC/RRU | tarikan | 60
R6300050 | JL. KELAPA BJM | XLS | KABEL OPTIK | tarikan | 150
R6300051 | JL. KELAPA BJM | XLS | BATT DRYCELL TYPE MAXLIFE FGB12-100 | pcs | 12 | CME002196791 CME002196791 CME002196798 CME002196797 CME002196792 CME002196799 CME002196800 CME002196794 CME002196796 CME002196803
R6300052 | JL. KELAPA BJM | XLS | CME002196803 | pcs | 3 | CME002196752 CME002196752 CME002197613
R6300053 | JL. KELAPA BJM | XLS | BBU ZTE ZXRAN V9200 | pcs | 1 | 219264286380
R6300054 | JL. KELAPA BJM | XLS | METRO-E ZTE ZXA10 | pcs | 1 | 219267639565
R6300055 | JL. KELAPA BJM | XLS | LPU2 | pcs | 1
R6300056 | JL. KELAPA BJM | XLS | DCPDB | pcs | 1 | LA0637206041
R6300057 | JL. KELAPA BJM | XLS | JUMPER | pcs | 12
R6300058 | JL. KELAPA BJM | XLS | SFP | pcs | 7
E3200269 | CILEUNGSIKIDUL | XL | RECIFIER OUTDOOR | pcs | 1
E3200270 | CILEUNGSIKIDUL | XL | ANTENNA MW 0.5 | pcs | 1 | 21524311113RH5000035
E3200271 | CILEUNGSIKIDUL | XL | ODU HUAWEI XMC | pcs | 1
E3200272 | CILEUNGSIKIDUL | XL | RTN COUPLER | pcs | 1
R5100062 | SMPK_THOMAS_AQUINO | XL | RECIFIER OUTDOOR | unit | 1
R5100063 | SMPK_THOMAS_AQUINO | XL | Rack BTS | unit | 1
R5100064 | SMPK_THOMAS_AQUINO | XL | RRU | pcs | 6
R5100065 | SMPK_THOMAS_AQUINO | XL | CPRI | pcs | 6
R5100066 | SMPK_THOMAS_AQUINO | XL | POWER RRU | pcs | 6
R5100067 | SMPK_THOMAS_AQUINO | XL | CPRI TRANSPOT | pcs | 1
R5100068 | SMPK_THOMAS_AQUINO | XL | SFP RRU | pcs | 12
R5100069 | SMPK_THOMAS_AQUINO | XL | POWER DCDU | pcs | 1
R5100070 | SMPK_THOMAS_AQUINO | XL | BATRAI LITHIUM | pcs | 1
R5100071 | SMPK_THOMAS_AQUINO | XL | ABBP D3 | pcs | 2
R5100072 | SMPK_THOMAS_AQUINO | XL | ABRIB | pcs | 1
R5100073 | SMPK_THOMAS_AQUINO | XL | UMPT B1 | pcs | 1
R5100074 | SMPK_THOMAS_AQUINO | XL | DCDU | pcs | 3
R5100075 | SMPK_THOMAS_AQUINO | XL | BBU 3900 | pcs | 1
R5100076 | SMPK_THOMAS_AQUINO | XL | EMU | pcs | 1
R5100077 | SMPK_THOMAS_AQUINO | XL | SLPU | pcs | 1
R5100078 | SMPK_THOMAS_AQUINO | XL | FAN 0.2 A | pcs | 1
R5100079 | SMPK_THOMAS_AQUINO | XL | FAN 0.1 A | pcs | 1
R5100080 | SMPK_THOMAS_AQUINO | XL | SFP TRANSPOT | pcs | 1
R5100081 | SMPK_THOMAS_AQUINO | XL | MODULE APR 48 | pcs | 4
R5100082 | SMPK_THOMAS_AQUINO | XL | DISPLAY APR ES | pcs | 1
R5100083 | SMPK_THOMAS_AQUINO | XL | OTB | pcs | 1
R5100084 | SMPK_THOMAS_AQUINO | XL | CSR | pcs | 1
R5100085 | SMPK_THOMAS_AQUINO | XL | OPTIK RTN | pcs | 1
R7300461 | Nuri Rajawali | XL | RRU | pcs | 5
R7300462 | Nuri Rajawali | XL | KABEL OPTIK | tarikan | 5
R7300463 | Nuri Rajawali | XL | KABEL POWER RRU | tarikan | 5
R7300464 | Nuri Rajawali | XL | BATERAI LITHIUM | pcs | 2
R7300465 | Nuri Rajawali | XL | RACK RECKTIFIER | pcs | 1
R7300466 | Nuri Rajawali | XL | RACK BTS KABINET | pcs | 1
R7300467 | Nuri Rajawali | XL | ANTENA RF | pcs | 3
R7300468 | Nuri Rajawali | XL | SUBRACK RECK | pcs | 1
R7300469 | Nuri Rajawali | XL | DCDU 12B | pcs | 2
R7300470 | Nuri Rajawali | XL | DCDU 12C | pcs | 1
R7300471 | Nuri Rajawali | XL | ALARM EMUA | pcs | 1
R7300472 | Nuri Rajawali | XL | BBU 5900 | pcs | 1
R7300473 | Nuri Rajawali | XL | FAN 10C | pcs | 1
R7300474 | Nuri Rajawali | XL | DCDU 12A | pcs | 1
R7300475 | Nuri Rajawali | XL | SLPU | pcs | 1
R7300476 | Nuri Rajawali | XL | FAN 2 D | pcs | 1
R7300477 | Nuri Rajawali | XL | MODUL REKCT | pcs | 4
R7300478 | Nuri Rajawali | XL | PASO LINK | pcs | 1
R7300479 | Nuri Rajawali | XL | OTB | pcs | 1
R7300480 | Nuri Rajawali | XL | IDU | pcs | 1
R3100496 | KELAPA DUA WETAN | XLS | ANTENA SECTOR | pcs | 3
R3100497 | KELAPA DUA WETAN | XLS | CABINET MTS9300A | pcs | 1 | ES24300011
R3100498 | KELAPA DUA WETAN | XLS | ATN9lOC | pcs | 1 | 1024188540sS'
R3100499 | KELAPA DUA WETAN | XLS | Radio 4499 | pcs | 3 | E55B355398 E558355396 E558355318
R3100500 | KELAPA DUA WETAN | XLS | Radio 2219 | pcs | 3 | E551139463 E550360896 E550360842
R3100501 | KELAPA DUA WETAN | XLS | Cabinet MTS9300A | pcs |  | E52370031508
R3100502 | KELAPA DUA WETAN | XLS | Modul Recty APR4850g | pcs | 3 | BTQ1011679 BTQ10 12246 BTQ1011737
R3100503 | KELAPA DUA WETAN | XLS | SMU02C | pcs | 1 | HV2360302464
R3100504 | KELAPA DUA WETAN | XLS | Batteraititium | pcs | 1 | ESM-4810002
R3100505 | KELAPA DUA WETAN | XLS | IDU Ipasotink MDP | pcs | 2 | 1320 35582
R3100506 | KELAPA DUA WETAN | XLS | BASEBAND 6630 | pcs | 1 | TD3858686120190108
R3100507 | KELAPA DUA WETAN | XLS | IDU IPASOLINK | pcs | 1 | 6568
R3100508 | KELAPA DUA WETAN | XLS | GENSET DENYO25 | pcs | 1
R3100533 | PELEPAH INDAH |  | ANTENA MW 0,3 | pcs | 1
R3100534 | PELEPAH INDAH |  | RADIO PASOLINK | pcs | 1
R3100535 | PELEPAH INDAH |  | Antenna Sektor 1 | pcs | 1 | KA669125A1828718
R3100536 | PELEPAH INDAH |  | Antenna Sektor 2 | pcs | 1 | RAPAC03184700132
R3100537 | PELEPAH INDAH |  | Antenna Sektor 3 | pcs | 1
R3100538 | PELEPAH INDAH |  | Antenna Sektor 4 | pcs | 1 | KA669125A1828730
R3100539 | PELEPAH INDAH |  | RRU 4443 B1 B3 | pcs | 1 | E23A822736
R3100540 | PELEPAH INDAH |  | RRU 4443 B1 B3 | pcs | 1 | E23A856711
R3100541 | PELEPAH INDAH |  | RRU 2219 BOA | pcs | 1 | CD3Y978419
R3100542 | PELEPAH INDAH |  | RRU 2219BOA | pcs | 1 | CD3Y978400
R3100543 | PELEPAH INDAH |  | RUS 01 B1 | pcs | 1 | SCB4N058020
R3100544 | PELEPAH INDAH |  | RRU 2219 BOA | pcs | 1 | CD3Y978393
R3100545 | PELEPAH INDAH |  | RRU 4443 B1 B3 | pcs | 1 | E23A808842
R3100546 | PELEPAH INDAH |  | ANTENNA MW Alita NEC 0,3 M | pcs | 1 | 2303601.1
R3100547 | PELEPAH INDAH |  | Antena MW 0,6 ELPO | pcs | 1
R3100548 | PELEPAH INDAH |  | Antena MW 0,3 NEC | pcs | 1 | 18R3C3A22F
R3100549 | PELEPAH INDAH |  | Antena MW 0,6 seragon | pcs | 1 | 17002040033
R3100550 | PELEPAH INDAH |  | Antena MW 0,3 NEC | pcs | 1
R3100551 | PELEPAH INDAH |  | Antena MW 0,3 NEC 1+ 1 | pcs | 1
R3100552 | PELEPAH INDAH |  | Antena MW ipasolink 0,3 | pcs | 1
R3100553 | PELEPAH INDAH |  | Radio NEC PASOLINK | pcs | 1 | 1152
R3100554 | PELEPAH INDAH |  | Radio NEC PASOLINK TRP-23G-1E | pcs | 1 | 18745
R3100555 | PELEPAH INDAH |  | Radio Elpo | pcs | 1
R3100556 | PELEPAH INDAH |  | Radio NEC PASOLINK TRP-23G-1E | pcs | 1 | 18628
R3100557 | PELEPAH INDAH |  | Radio NEC pasolink | pcs | 1
R3100558 | PELEPAH INDAH |  | Radio Ceragon | pcs | 1
R3100559 | PELEPAH INDAH |  | Radio NEC PASOLINK | pcs | 1 | 97546
R3100560 | PELEPAH INDAH |  | Radio nec ipasolink | pcs | 1
R3100561 | PELEPAH INDAH |  | Radio nec ipasolink | pcs | 1
R3100562 | PELEPAH INDAH |  | Baseband 6630 | pcs | 1 | TD38827457
R3100563 | PELEPAH INDAH |  | Basband 5216 | pcs | 1 | TD38884604
R3100564 | PELEPAH INDAH |  | IDU IPASOLINK 400 | pcs | 1
R3100565 | PELEPAH INDAH |  | IDU IPASOLANG 400 | pcs | 1
R3100566 | PELEPAH INDAH |  | MODUL REQTY 4 PCS | pcs | 1
R3100567 | PELEPAH INDAH |  | R .4850G | pcs | 4
R3100568 | PELEPAH INDAH |  | Batre Huawei Lithium | pcs | 1
R3100569 | PELEPAH INDAH |  | RACK CABINET | pcs | 1
E1600040 | MUARA_BELITI | IOH | BATTERY LITHIUM | pcs | 3
E1600041 | MUARA_BELITI | IOH | ANTENA SECTOR | pcs | 3
E1600042 | MUARA_BELITI | IOH | AHEGC | pcs | 3
E1600043 | MUARA_BELITI | IOH | FXDB | pcs | 2
E1600044 | MUARA_BELITI | IOH | BTS | pcs | 1
E1600045 | MUARA_BELITI | IOH | IDU NEC 2 | pcs | 2
E1600046 | MUARA_BELITI | IOH | METRO E | pcs | 1
E1600047 | MUARA_BELITI | IOH | SUBRACK ELTEK-1 MODULE | pcs | 3
E1600048 | MUARA_BELITI | IOH | BMS 6 EBERGY | pcs | 1
E1600049 | MUARA_BELITI | IOH | ANTENA MW 1.8 | pcs | 1
E1600050 | MUARA_BELITI | IOH | ANTENA MW 1.2 | pcs | 1
E1600051 | MUARA_BELITI | IOH | ODU HUAWEI XMC | pcs | 6
E1600052 | MUARA_BELITI | IOH | CABEL OPTIK | pcs | 8
E1600053 | MUARA_BELITI | IOH | CABEL COAX | pcs | 5
E1600054 | MUARA_BELITI | IOH | KABEL POWER RRU | pcs | 4
E1600055 | MUARA_BELITI | IOH | SAPRAK FXDB | pcs | 1
E1600056 | MUARA_BELITI | IOH | BRACKET AHEGC | pcs | 3
E1600057 | MUARA_BELITI | TSEL | CABEL OPTIK | pcs | 6
E1600058 | MUARA_BELITI | TSEL | CABEL POWER RRU | pcs | 6
E1600059 | MUARA_BELITI | TSEL | ANTENA SECTOR | pcs | 3
E1600060 | MUARA_BELITI | TSEL | BATTERY LITHIUM | pcs | 2
E1600061 | MUARA_BELITI | TSEL | RACK REKCTY | pcs | 2
E1600062 | MUARA_BELITI | TSEL | MODULE RECKTY | pcs | 2
E1600063 | MUARA_BELITI | TSEL | SAPRACK RECKTY | pcs | 1
E1600064 | MUARA_BELITI | TSEL | BTS | pcs | 1
E1600065 | MUARA_BELITI | TSEL | DCDU | pcs | 1
E1600066 | MUARA_BELITI | TSEL | METRO E | pcs | 1
E1600067 | MUARA_BELITI | TSEL | EUMB | pcs | 1
E1600068 | MUARA_BELITI | TSEL | RECTING RACK RECKTY | pcs | 1
E1600069 | MUARA_BELITI | TSEL | ANTENA KABEL GPS | pcs | 1
E1600070 | MUARA_BELITI | TSEL | BRACKET POLE ANTENA SECTOR | pcs | 3
R1200054 | PUSAT PASAR | XLS | ANTENA SECTOR | pcs | 3
R1200055 | PUSAT PASAR | XLS | RRU | pcs | 6
R1200056 | PUSAT PASAR | XLS | COMBAINER | pcs | 3
R1200057 | PUSAT PASAR | XLS | KABEL POWER | pcs | 8
R1200058 | PUSAT PASAR | XLS | KABEL OPTIK | pcs | 8
R1200059 | PUSAT PASAR | XLS | ANTENA MW 0.3 | pcs | 1
R1200060 | PUSAT PASAR | XLS | KABEL COAX | pcs | 1
R1200061 | PUSAT PASAR | XLS | ODU | pcs | 1
R1200062 | PUSAT PASAR | XLS | IDU | pcs | 1
R1200063 | PUSAT PASAR | XLS | BATERAIC | pcs | 2
R1200064 | PUSAT PASAR | XLS | SFP | pcs | 6
R1200065 | PUSAT PASAR | XLS | JUMPER ANTENA | pcs | 33
R1200066 | PUSAT PASAR | XLS | JUMPER COMBAINER | pcs | 12
R1200067 | PUSAT PASAR | XLS | BBU | pcs | 1
R1200068 | PUSAT PASAR | XLS | LUB | pcs | 1
R1200069 | PUSAT PASAR | XLS | SPF | pcs | 6
R1200070 | PUSAT PASAR | XLS | BPQ | pcs | 1
R1200071 | PUSAT PASAR | XLS | ACPDB | pcs | 1
R1200072 | PUSAT PASAR | XLS | KABEL ACPDB | pcs | 1
R3270659 | PERUMNAS CIJERAH | XLS | ANTENA SECTORAL | pcs | 4 | 212701316sN063001287 21270144s03ees100555 2127013165N013001274 2127013165N0L3001227
R3270660 | PERUMNAS CIJERAH | XLS | AAU | pcs | 1 | AAU5726E2102313XPH10Q5100379
R3270661 | PERUMNAS CIJERAH | XLS | RRU 5502 | pcs | 4 | 21023128SJ10JA000856 21023128SJ10JA14D000848 210231285BSIDUL5101382
R3270662 | PERUMNAS CIJERAH | XLS | RRU3938 | pcs | 2 | 212314GJA10R110222
R3270663 | PERUMNAS CIJERAH | XLS | RRU 5866 | pcs | 1 | 2102314GJM10R7700222
R3270664 | PERUMNAS CIJERAH | XLS | ANTENA MW 0.6 | pcs | 1 | 21524311-00 AEBU00739
R3270665 | PERUMNAS CIJERAH | XLS | ODU RTN | pcs | 2 | 215241403210K2000030 215241403410K5000117
R3270666 | PERUMNAS CIJERAH | XLS | RECKTIFIER | pcs |  | ES2110043711
R3270667 | PERUMNAS CIJERAH | XLS | MODULE RECTY | pcs | 3 | 006758 046724 009108
R3270668 | PERUMNAS CIJERAH | XLS | BATTERY LITHIUM | pcs | 2 | Huawei ESM-48100B1 Huawei ESM-481C00U5
R3270669 | PERUMNAS CIJERAH | XLS | DCDU 12B | pcs | 2 | 2102120751PQ1002842 210212073116TF1901874
R3270670 | PERUMNAS CIJERAH | XLS | DCDU 16D | pcs | 1 | 21021227206TQB913494
R3270671 | PERUMNAS CIJERAH | XLS | SLPU | pcs | 1 | 2121030116DAEC001639
R3270672 | PERUMNAS CIJERAH | XLS | UELP | pcs | 1 | 020FED4MGCO12034
R3270673 | PERUMNAS CIJERAH | XLS | UELP-C | pcs | 1 | 022KNY10F1004272
R3270674 | PERUMNAS CIJERAH | XLS | COUPLER | pcs | 1
R3270675 | PERUMNAS CIJERAH | XLS | SP35 | pcs | 1
R3270676 | PERUMNAS CIJERAH | XLS | GPS | pcs | 1
R3270677 | PERUMNAS CIJERAH | XLS | CSHU | pcs | 1 | O21YTFCNFBOO344O
R3270678 | PERUMNAS CIJERAH | XLS | ISM6 | pcs | 1 | 022VHK10K200443
R3270679 | PERUMNAS CIJERAH | XLS | E64 | pcs | 1 | 021MXJCNFB001555
R3270680 | PERUMNAS CIJERAH | XLS | SMU02C | pcs | 1
R3270681 | PERUMNAS CIJERAH | XLS | Rtn 950 | pcs | 1
E3500389 | BURNEH | IOH | KABEL POWER RRU | pcs | 6 | N3188038233
E3500390 | BURNEH | IOH | SCC800-B1 | pcs | 1
E3500391 | BURNEH | IOH | KABEL POWER DCDU | pcs | 1
E3500392 | BURNEH | IOH | KABEL BATTERY | pcs | 2
E3500393 | BURNEH | IOH | RAK RECKTY | pcs | 1
E3500394 | BURNEH | IOH | SMU RECKTY | pcs | 1
E3500395 | BURNEH | IOH | JUMPER | pcs | 30
E3500396 | BURNEH | IOH | PANEL BOX OUTDOOR | pcs | 1
E3500397 | BURNEH | IOH | MCMS03-B | pcs | 1
E3500398 | BURNEH | IOH | PANEL ATS | pcs | 1
E3500399 | BURNEH | IOH | ACPDB GENSET | pcs | 1
E3500400 | BURNEH | IOH | DC POWER BLUE | pcs | 1
E3500401 | BURNEH | IOH | DC POWER HITAM | pcs | 1
E3500402 | BURNEH | IOH | COAT | pcs | 8
E3500403 | BURNEH | IOH | SFP RRU | pcs | 9
E3500404 | BURNEH | IOH | SFP BBU | pcs | 9
E3500405 | BURNEH | IOH | GIM 01C | pcs | 1
E3500406 | BURNEH | IOH | NIM 01C3 | pcs | 1
E3500407 | BURNEH | IOH | UIM 02D | pcs | 1
E3500408 | BURNEH | IOH | UIM 03D | pcs | 1
E3500409 | BURNEH | IOH | FMLIA | pcs | 1
E3500410 | BURNEH | IOH | HYBRID KABEL | pcs | 3
E3500411 | BURNEH | IOH | SMK02C | pcs | 1
E3500412 | BURNEH | IOH | STICK ROAD MW | pcs | 2
E3500413 | BURNEH | IOH | ANTENA SECTOR | pcs | 3 | 21270112534XL300182 21270112534XL4001340 21270112534XL3000085
E3500414 | BURNEH | IOH | MW 0,6 | pcs | 2
E3500415 | BURNEH | IOH | MW 1,2 | pcs | 2
E3500416 | BURNEH | IOH | RRU 5502 | pcs | 3 | 2102312BSJ9WL3000761 2102312BSJ9WL3000595 2102312BSJ9WL200365
E3500417 | BURNEH | IOH | RRU 5901 | pcs | 3 | 2102311QMD108100307 2102311QMD10N710263 2102311QMD6TK9200550
E3500418 | BURNEH | IOH | RRU | pcs | 3
E3500419 | BURNEH | IOH | DPSIID | pcs | 1 | 2101073946POJFIOI3504
E3500420 | BURNEH | IOH | BBU | pcs | 1
E3500421 | BURNEH | IOH | UBBP | pcs | 3
E3500422 | BURNEH | IOH | UMPT | pcs | 1
E3500423 | BURNEH | IOH | UPEU | pcs | 1
E3500424 | BURNEH | IOH | RECKTY | pcs | 1
E3500425 | BURNEH | IOH | MODULE RECKTY | pcs | 1
E3500426 | BURNEH | IOH | BATTERY | pcs | 4
E3500427 | BURNEH | IOH | RACK-19 | pcs | 1
E3500428 | BURNEH | IOH | IDU | pcs | 2
E3500429 | BURNEH | IOH | DCDU | pcs | 1
E3500430 | BURNEH | IOH | OPTIK | pcs | 6
E3500431 | BURNEH | TSEL | FAN | pcs | 1 | 210212223
E3500432 | BURNEH | TSEL | DCDU | pcs
E3500433 | BURNEH | TSEL | DCDU 16D | pcs | 1
E3500434 | BURNEH | TSEL | DCDU 15D | pcs | 1
E3500435 | BURNEH | TSEL | BATTERY LITHIUM | pcs | 2
E3500436 | BURNEH | TSEL | BBU 5900 | pcs | 1
E3500437 | BURNEH | TSEL | ANTENA SECTOR A12 | pcs | 1
E3500438 | BURNEH | TSEL | ANTENA SECTOR AQU4 | pcs | 1
E3500439 | BURNEH | TSEL | ANTENA SECTOR AW45 | pcs | 1
E3500440 | BURNEH | TSEL | ANTENA SECTOR | pcs | 2
E3500441 | BURNEH | TSEL | RRU 5905 | pcs | 3 | 2102312BCY10L1005871 2102312BCY10L100159
E3500442 | BURNEH | TSEL | RRU 2300 | pcs | 2 | 2102311HYY10J7001937 2102311HYY10J7001712
E3500443 | BURNEH | TSEL | RRU 5502 | pcs | 2 | 2102312B5J9WM2000799 2102312B5J9WM20001022
E3500444 | BURNEH | TSEL | RRU 5865 | pcs | 1
E3500445 | BURNEH | TSEL | OPTIK | pcs | 9
E3500446 | BURNEH | TSEL | KABEL POWER RRU | pcs | 9
E3500447 | BURNEH | TSEL | RAK APM 5930 | pcs | 1
E3500448 | BURNEH | TSEL | RAK TMC 11H | pcs | 1
E3500449 | BURNEH | TSEL | RAK RECTI | pcs | 1
E3500450 | BURNEH | TSEL | ESFP TRANSMISI | pcs | 1
E3500451 | BURNEH | TSEL | ESFP RRU | pcs | 9
E3500452 | BURNEH | TSEL | ESFPBBU TO RRU | pcs | 9
E3500453 | BURNEH | TSEL | JUMPER 27 | pcs | 27
E3500454 | BURNEH | TSEL | KABEL BATTERY MERAH | pcs | 2
E3500455 | BURNEH | TSEL | KABEL BATTERY HITAM | pcs | 2
E3500456 | BURNEH | TSEL | KABEL POWERBANK BLUEBLACK | pcs | 2
E3500457 | BURNEH | TSEL | ANTENA GPS + ARESTER | pcs | 1
E3500458 | BURNEH | TSEL | POWER ACPDB | pcs | 1
E3500459 | BURNEH | TSEL | RECTI | pcs | 1
E3500460 | BURNEH | TSEL | MODULE RECTI | pcs | 5
E3500461 | BURNEH | TSEL | FAN 02 | pcs | 1
E3500462 | BURNEH | TSEL | UBBPE4 | pcs | 1
E3500463 | BURNEH | TSEL | UBBPD6 | pcs | 1
E3500464 | BURNEH | TSEL | UMPT | pcs | 1
E3500465 | BURNEH | TSEL | UPEU | pcs | 1
E3500466 | BURNEH | TSEL | BESI C KANAL BTS | pcs | 4
E3500467 | BURNEH | TSEL | OTB | pcs | 1
E3500468 | BURNEH | TSEL | UBBP62 | pcs | 1 | 21030586261002100000
E3500469 | BURNEH | TSEL | EMU A | pcs | 1
E3500470 | BURNEH | TSEL | FAN F | pcs | 1
E3500471 | BURNEH | TSEL | RRU 3276 | pcs | 1 | 2102312HY10J900 709
E1200424 | DAPUR_DUA_BELAS / DAPUR 12 | IOH | KABEL POWER BATTERY | pcs | 4
E1200425 | DAPUR_DUA_BELAS / DAPUR 13 | IOH | KABEL POWER ACPDB | pcs | 1
E1200426 | DAPUR_DUA_BELAS / DAPUR 14 | IOH | KABEL POWER GROUND | pcs | 1
E1200427 | DAPUR_DUA_BELAS / DAPUR 15 | IOH | KABEL POWER FSMF | tarikan | 2
E1200428 | DAPUR_DUA_BELAS / DAPUR 16 | IOH | KABEL POWER RTN | tarikan | 3
E1200429 | DAPUR_DUA_BELAS / DAPUR 17 | IOH | RTN 910 A | pcs | 1
E1200430 | DAPUR_DUA_BELAS / DAPUR 18 | IOH | RTN 905 | pcs | 1
E1200431 | DAPUR_DUA_BELAS / DAPUR 19 | IOH | RACK GPS | pcs | 1
E1200432 | DAPUR_DUA_BELAS / DAPUR 20 | IOH | RACK KABINET | pcs | 1
E1200433 | DAPUR_DUA_BELAS / DAPUR 21 | IOH | ACPDB | pcs | 1
E1200434 | DAPUR_DUA_BELAS / DAPUR 22 | IOH | COVER MODULE RP | pcs | 4
E1200435 | DAPUR_DUA_BELAS / DAPUR 23 | IOH | ODU | pcs | 2
E1200436 | DAPUR_DUA_BELAS / DAPUR 24 | IOH | MW 1.2 | pcs | 1
E1200437 | DAPUR_DUA_BELAS / DAPUR 25 | IOH | JUNCTION BOX | pcs | 1
E1200438 | DAPUR_DUA_BELAS / DAPUR 26 | IOH | CONECTOR COAX | pcs | 2
E1200439 | DAPUR_DUA_BELAS / DAPUR 27 | IOH | KABEL POWER TWIS | pcs | 4
E1200440 | DAPUR_DUA_BELAS / DAPUR 28 | IOH | KABEL COAX | pcs | 2
E1200441 | DAPUR_DUA_BELAS / DAPUR 29 | IOH | KABEL OPTIK | pcs | 13
E1200442 | DAPUR_DUA_BELAS / DAPUR 30 | IOH | FSMF | pcs | 2
E1200443 | DAPUR_DUA_BELAS / DAPUR 31 | IOH | FTIF | pcs | 1
E1200444 | DAPUR_DUA_BELAS / DAPUR 32 | IOH | SFP | pcs | 15
E1200445 | DAPUR_DUA_BELAS / DAPUR 33 | IOH | BATTERY LITHIUM | pcs | 2
E1200446 | DAPUR_DUA_BELAS / DAPUR 34 | IOH | MODULE RECTI | pcs | 4
E1200447 | DAPUR_DUA_BELAS / DAPUR 35 | IOH | SUBRACK RECTI | pcs | 1
E1200448 | DAPUR_DUA_BELAS / DAPUR 36 | IOH | FROU | pcs | 1
E1200449 | DAPUR_DUA_BELAS / DAPUR 37 | IOH | FXDB | pcs | 2
E1200450 | DAPUR_DUA_BELAS / DAPUR 38 | IOH | FXED | pcs | 1
E1200451 | DAPUR_DUA_BELAS / DAPUR 39 | IOH | RF JUMPER | pcs | 18
E1200452 | DAPUR_DUA_BELAS / DAPUR 40 | IOH | ANTENA SECTOR | pcs | 3

## LOS Survey
LINK INFORMATION
[17 empty] | 14BRS0006 KARANGJUNTI_CM | 14BRS0011 RUNGKANG_TB
|  | Near End | [5 empty] | Far End | [5 empty] | Result | Remark | Latitude | 6°54'51.5"S | 6°54'58.1"S
Site ID | Site Name | Site ID & Site Name (A) | Longitude (e) | Latitude (s) | Antenna Height (m) | Azimuth (º) | Distance (Km) | Candidate | Site ID & Site Name (B) | Longitude (e) | Latitude (s) | Antenna Height (m) | Azimuth (º) |  |  | Longitude | 108°47'39.1"E | 108°48'32.4"E
R1200302 | BANGUN PURBA | SUM-SU-LBP-0054 BANGUN PURBA Relocation |  |  | proposed at height 60 | 185 | 8.1 |  | SUM-SU-SRH-1245 Sei Buaya | 98.8075625 | 3.2984375 | proposed at height 50 | 6 | LOS | Need actual survey | True azimuth (°) | 90 | 15
R1200302 | BANGUN PURBA | SUM-SU-LBP-0054 BANGUN PURBA Relocation |  |  | proposed at height 52 | 10.5 | 6.6 |  | SUM-SU-LBP-0412 Batu Lokong | 98.8301875 | 3.4295625 | proposed at height 55 | 195 | LOS | Need actual survey | Elevation (m) | 12 | 18
R1200302 | BANGUN PURBA | SUM-SU-LBP-0054 BANGUN PURBA Relocation |  |  | proposed at height 53 | 10 | 12.9 |  | SUM-SU-SRH-8224 SF_Pematang Raya 2_COLLECTOR | 98.79774944 | 3.255764722 | proposed at height 55 | 190 | LOS | Need actual survey
E3500158 | PLANDI | 16JMB0118 SUMBER_MULYO_MT | 112.26398 | -7.56379 | proposed at height 43 | 220 | 1.1 | 1 | 16JMB0108 PLANDI_JMB1_EP | 112.257794 | -7.57167 | proposed at height 32 | 40 | LOS
R3350421 | KARANGJUNTI | 14BRS0006 KARANGJUNTI_CM | 108.7942 | -6.9143 | proposed at height 40 | 190 | 1.57 | 1 | 14BRS0004 KUBANGDJERO_TB | 108.79078 | -6.92804 | proposed at height 38 | 20 | LOS
R3350421 | KARANGJUNTI | 14BRS0006 KARANGJUNTI_CM | 108.7942 | -6.9143 | proposed at height 40 | 90 | 1.64 | 2 | 14BRS0011 RUNGKANG_TB | 108.809 | -6.91615 | proposed at height 40 | 280 | LOS
R3350421 | KARANGJUNTI | 14BRS0006 KARANGJUNTI_CM | 108.7942 | -6.9143 | proposed at height 40 | 50 | 2.37 | 3 | 14BRS0013 PEJAGAN3RUNGKANG_AG | 108.81081 | -6.90065 | proposed at height 50 | 230 | LOS
E3200182 | GEULIS_RESORT | E3200182 GEULIS_RESORT | 106.866094 | -6.631617 | Proposed at height 49 | 290 | 3.51 |  | JAW-JB-BGR-0421 GERBANG CIAWI | 106.835292 | -6.623942 | Existing

## List team
No | Nama | ID KTP | Tanggal Lahir | Task | Province | Jenis Sertif | No Sertif | Contact
1 | Utut Wahyu Eka | 3175101512870006 | 1987-12-15 | Engineer | BALI
2 | Hoirul Anam | 3509131008950005 | 1995-08-10 | Team Leader | BALI | TKPK1 | 12625/TKPK-TK1/XII/2021
3 | Muhammad Bahtiar | 3501120202880002 | 1988-02-02 | Installer | BALI | TKPK1 | 1221181022/N-TKPK1/31/X/2022
4 | Martono | 3511700407860004 | 1986-07-04 | Installer | BALI
5 | Ardiyanto Lase | 2171121512900000 | 15/12/1990 | Installer | BALI | FA | 00716/020/DSB/P3K/SEPTEMBER/22
6 | M. Andrian Armeidiana | 3522060205930005 | 1993-02-05 | Team Leader | JAKARTA | FA | 00844/024/DSB/P3K/OCTOBER/22
7 | Bagus Tri Wardani | 3517071608910002 | 16/8/1991 | Installer | JAKARTA | TKPK1 | 0184021122/N-TKPK1/32/XI/2022
8 | Akhmad Soleh | 3371010708840001 | 7/8/1984 | Installer | JAKARTA
9 | Akub | 3604161201900001 | 20/1/1990 | Installer | JAKARTA
10 | Joko Dedoyo Kecil Liyanto | 3315121502970005 | 1997-02-15 | Engineer | JAWA TENGAH
11 | Muhamad Ali Nur S | 3315122911940002 | 1994-11-29 | Team Leader | JAWA TENGAH | TKPK1 | 0843281022/N-TKPK1/33/X/2022
12 | Jimmi Perdana Putra | 3315120408010003 | 2000-01-08 | Member | JAWA TENGAH | TKPK1 | 0414200922/N-TKPK1/31/IX/2022
13 | Hengki Irawan | 3315120107010009 | 2000-01-07 | Member | JAWA TENGAH
14 | Rano Aprilian Werdhana | 3578040604880002 | 1988-04-06 | Team Leader | JAWATIMUR | TKPK1 | 0218190522/N-TKPK1/31/V/2022
15 | Adi Putra | 3516070402920001 | 1992-02-04 | Installer | JAWA TIMUR | TKPK1 | 5268/TKPKT-T1-TELKO/X/2021
16 | Riza Brama Putra | 3578041202860001 | 1986-02-12 | Installer | JAWA TIMUR
17 | Dicky Dermawan | 3578042504020001 | 2002-04-25 | Installer | JAWA TIMUR | TKPK1 | 3378/TKPK-TK1-TELKO/X/2020-BT
18 | Widodo | 3578091606740001 | 16/06/1974 | Installer | JAWA TIMUR | FA | 01129/042/DSB/P3K/DECEMBER/22
19 | Mohamad Hendra | 5308181905860000 | 19/05/1986 | Team Leader | KALIMANTAN TIMUR
20 | Brayen Varmandhella | 3506131805990001 | 18/05/1999 | Installer | KALIMANTAN TIMUR | TKPK1 | 0548220722/N-TKPK1/51/VII/2022
21 | Tri Nurdiansyah | 3216071611950006 | 16/11/1995 | Installer | KALIMANTAN TIMUR | TKPK1 | 22674/TKBT-TK2/X/2020-BT
22 | Samsudin Bin Arbaa | 5308181007910001 | 1991-10-07 | Installer | KALIMANTAN TIMUR
25 | Sunarji | 3524161003880001 | 1986-03-10 | Installer | LAMPUNG | FA | 01128/042/DSB/P3K/DECEMBER/22
27 | ahmad | 7371091507860007 | 1986-07-15 | Team Leader | MALUKU UTARA
28 | Putut Rahadi | 3578140909680000 | 1976-07-17 | Installer | MALUKU UTARA | TKPK1 | 4957/TKPK-TK1-TELKO/X/2021
29 | Andi Kurniawan | 3328181808890006 | 1989-08-18 | Installer | MALUKU UTARA
30 | Achmad Taufan Ardhitya Nugraha | 3578082603000001 | 2000-03-25 | Installer | MALUKU UTARA | TKPK1 | 0559220722/N-TKPK1/35/VII/2022
31 | Obet Benmetan | 5302072405020001 | 2002-05-24 | Engineer | NTT
32 | Tarman | 3514011709780001 | 1978-09-17 | Team Leader | NTT | TKPK1 | 0058011022/N-TKPK1/32/X/2022
33 | Fredi Septi Arianto | 3517132409880002 | 1988-09-24 | Member | NTT | TKPK1 | 4350/TKPK-TK1-TELKO/IV/2021
34 | Sunardi | 3574030410840005 | 1984-10-04 | Member
35 | ABD. KARIM JOKO WIBOWO | 7306132109790002 | 1972-09-21 | Team Leader | PAPUA TENGAH
36 | MUH. SAMSUNAR S | 7371120702030007 | 2000-03-02 | Member | PAPUA TENGAH
37 | SAPARUDDIN | 7305011002850001 | 1985-02-10 | Member | PAPUA TENGAH
38 | Moch. Ridwan | 3578141006820003 | 1982-06-10 | Member | PAPUA TENGAH | TKPK1 | 4960/TKPK-TK1-TELKO/X/2021
39 | Saddam Husein | 3578071905920001 | 1992-05-19 | Member | PAPUA TENGAH | TKPK1 | 4959/TKPK-TK1-TELKO/X/2021
40 | Moch Haris Islami | 3578060812840002 | 1984-12-08 | Team Leader | RIAU | TKPK1 | 5/0783240622/AS.01.04/VI/2022
41 | Rafsyanjani Akbar | 3215051102870003 | 1987-02-11 | Member | RIAU | TKPK1 | 4958/TKPK-TK1-TELKO/X/2021
42 | Rekli Mustofa | 3374131209790006 | 1979-09-12 | Member | RIAU
43 | Hari Jumardi | 1302122903850001 | 1985-03-29 | Member | RIAU
44 | Defta Maulana | 1408033011900001 | 30/11/1990 | Team Leader | RIAU
45 | Edi Suwanto | 1471071007750042 | 1975-10-07 | Installer | RIAU
46 | Beri Ahmad | 1403091612885463 | 16/12/1988 | Installer | RIAU
47 | Mawardi | 1106023004860003 | 1986-04-30 | Installer | RIAU | TKPK1 | 2855040624/N-TKPK1/14/VI/2024
48 | Muh. Nur Rizky | 7371091804010001 | 2000-01-04 | Engineer | SULAWESI SELATAN
49 | Imam Taupik | 3523051007900001 | 1990-07-10 | Team Leader | SULAWESI SELATAN | TKPK1 | 0563220722/N-TKPK1/35/VII/2022
50 | Faisol Amir | 3524050603850004 | 1985-03-06 | Member | SULAWESI SELATAN | TKPK1 | P.17.1813/TKPK-TK1/XII/2021
51 | Sapri | 7306131810910001 | 1991-10-18 | Member | SULAWESI SELATAN
52 | Rahman | 7306081708870020 | 1987-08-17 | Member | SULAWESI SELATAN
58 | Saiful S | 7371121808790000 | 18/08/1979 | Team Leader | SULAWESI TENGGARA
59 | Muh.Amin | 7305011504910000 | 15/01/1991 | Installer | SULAWESI TENGGARA
62 | MUH. AMIN | 7305011504910001 | 1991-04-15 | Team Leader | SULAWESI TENGGARA
63 | SUARJO | 7315043112950113 | 1995-12-31 | Member | SULAWESI TENGGARA
64 | SAMIR | 7371091211810008 | 1981-11-12 | Member | SULAWESI TENGGARA
65 | Samson Hidayat | 3524160202870004 | 1987-02-02 | Member | SULAWESI TENGGARA | TKPK1 | 0561220722/722/N-TKPK1/35/VII/2022
67 | Rizky Fernanda Nur LBS | 1205143007020007 | 2002-07-30 | Engineer | SUMATERA BARAT | TKPK1 | 2848040624/N-TKPK1/14/VI/2024
68 | Alam Syah Ginta | 1219011912800001 | 1980-12-19 | Team Leader | SUMATERA BARAT | TKPK1 | 4336040624/N-TKPK1/14/VI/2024
69 | Sediaman | 1271211211780001 |  | Member | SUMATERA BARAT
70 | Pardin Daulay | 1203070609811001 |  | Member | SUMATERA BARAT
71 | Tryas Catur Ananda | 3522082005900000 |  | Member | SUMATERA BARAT | FA | 273/PJK3-MEJ-P3K-DTK/BDT-T/DSB/20/06/2022
72 | Ismail | 1271211204800003 | 1980-04-12 | Team Leader | SUMATERA BARAT
74 | Darwin | 1271212912740003 | 1974-12-29 | Member | SUMATERA BARAT | TKPK1 | 2849040624/N-TKPK1/14/VI/2024
75 | Pirmansyah | 1205130109980002 | 1998-09-01 | Member | SUMATERA BARAT
72 | Aldira Hidayat | 1207211704020000 | 2002-04-17 | Member | SUMATERA BARAT
74 | Maolana Abdi | 5271012108940004 | 1993-04-07 | Installer | SUMATERA UTARA | TKPK1 | 0145071022/N-TKPK1/32/X/2022
75 | Jumadi Tampubolon | 5207062105870002 | 1987-05-21 | Installer | SUMATERA UTARA
72 | Endy | 1207260704930008 | 1993-04-07 | Installer | SUMATERA UTARA
| Amri Ricardo Sinaga | 1208162305930002 | 1993-05-23 |  | SUMATERA UTARA |  |  | +62 888-0774-1023
| Bento Sory Pinagar Silalahi | 1208060911940002 | 1994-11-09 |  | SUMATERA UTARA
| Joy Denharris Manurung | 1208160509970002 | 1998-09-05 |  | SUMATERA UTARA |  | 2065090523/TKBT2/13/V/2023
| Juhendi Markus Sinaga | 1208160405850001 | 1995-01-04 |  | SUMATERA UTARA |  | 0547150526/N-TKPK1/30/V/2026

## Email Permit
No | Name | PIC Site | ID KTP | Contact Number | Email Company | Password | Start Account | Expired Account | Validity Account
1 | Muhamad Darmanto |  | 3309142707940006 | 087865247367 | darmanto@tunggalsahabat.co.id |  | 2026-04-07 | 2026-06-06 | -60
2 | Muchamad Faiz Fahmi |  | 3325080505030004 | 085643166021 | faizfahmi@tunggalsahabat.co.id |  | 2026-04-07 | 2026-06-06 | -60
3 | Arrys Yasir Zulkarnain |  | 3515111205800002 | 089612377850 | yasir@tunggalsahabat.co.id |  | 2026-04-07 | 2026-06-06 | -60
4 | FARIZ MEYER |  | 3203112212830003 | 08814372949 | fariz@tunggalsahabat.co.id |  | 2026-04-07 | 2026-06-06 | -60
5 | TAUFIK HIDAYAT |  | 3275081809800033 | 081213207645 | taufik@tunggalsahabat.co.id |  | 2026-04-07 | 2026-06-06 | -60
6 | Abe Taskura Rizal |  | 3578020206890006 | 082141021724 | abe.taskurarizal@tunggalsahabat.co.id |  | 2026-04-07 | 2026-06-06 | -60
7 | JOKO NURSIO |  | 3578182109800001 | 087777788432 | joko.nursio@tunggalsahabat.co.id
8 | Suliswanto |  | 3316071612950001 | 089670307305 | suliswanto@tunggalsahabat.co.id | &,=U^$rM*k^H
8 | Ilham Tirta Kawah |  | 3578052606930002 | 085933744676 | Ilham.tirta@tunggalsahabat.co.id |  | 2026-04-07 | 2026-06-06 | -60
9 | Munasirin | Centra Java | 3324012212860001 | +62 812-5666-0163 | munasirin.ext_cj@tunggalsahabat.co.id | w[CatTrQLY7G
10 | Rano Aprilian Werdhana | East Java | 3578040604880002 | +62 896-7799-6532 | rano.ext_jav@tunggalsahabat.co.id | Pdyp4Pm,$!@X
11 | Herawan Bin Nasir | Kep. Riau |  | +62 859-3834-20733 | herawan.ext_sum@tunggalsahabat.co.id | b,kTkZ&n4Db2
12 | Sunandar Sandya Ramdhan | Central Kalimantan | 7304032512990002 | +62 823-5732-2405 | sandya.ext_kal@tunggalsahabat.co.id | OrDJNCv?J3oH
13 | Adi Nugroho |  |  | +62 812-3567-0006 | adinugroho.ext@tunggalsahabat.co.id | ~K,yBNDoX&@y
14 | Andi Wawan | West Java | 3275010107750260 | +62 819-9910-1650 | andiwawan.ext_wj@tunggalsahabat.co.id | wgwYgLGQbl$6
15 | Dedi Djunaidi | Sulawesi | 7171032606700001 | +62 81-1412-1707 | djunaidi.ext_sul@tunggalsahabat.co.id | VPZ^J}VD8mWF
16 | Safar | Sulawesi Tenggara | 7402020511850003 | +62 852-4162-2480 | safar.ext_ken@tunggalsahabat.co.id | &eg?Q5Y2V~ff
17 | Dwi Raharjo | Jabo | 3304121003890006 | +62 838-4577-1263 | raharjo.ext_jabo@tunggalsahabat.co.id | *5tuQ@s?yw2#
18 | Rangga Kenanga | Jabo | 3201201409810001 | +62 895-1706-7001 | rangga.kenanga@tunggalsahabat.co.id | 6q5e*8)0UU9z
19 | Dicky Dermawan | East Java | 3578042504020001 | +62 819-590-886 | dicky.dermawan_ext@tunghalsahabat.co.id | 9@6Y549;*Y26
20 | Haslan | Sulawesi Selatan | 7372041010840003 |  | haslan_ext@tunggalsahabat.co.id | bv#(RWlm~VR=
21 | Agus Sudarwanto | East Java | 3524131805850002 |  | agus.sudarwanto_ext@tunggalsahabat.co.id | +}aYEo)0ssT0%
22 | Muchammad Adhim | East Java | 3515130404860005 |  | muchammad.adhim_ext@tunggalsahabat.co.id | pTo_[-2v7,{q
23 | Hoirul Anam | East Java | 3524131805850002 |  | hoirulanam.ext_ej@tunggalsahabat.co.id | Td7Tj=mN$~t^
24 | Bayu Martin Iksanudin | West Java | 3315121209950002 |  | bayu.martin_ext@tunggalsahabat.co.id | zY$C^lcK47]l
25 | Arif Moh Riyadi | Central Java | 3315121006860001 |  | arif.mohriyadi_ext@tunggalsahabat.co.id | Doiw4{hY}veM
26 | Mubarok | East Java | 3578161408870011 |  | mubarok_ext@tunggalsahabat.co.id | 2#.ZVXUo;akB
27 | Yuda | West Java | 3216220112820005 |  | yuda.ext@tunggalsahabat.co.id | wo&cF!d@olge
28 | Haris Affandie | Kalimantan | 6471052008800013 | 081258518280 | haris.affandie_ext@tunggalsahabat.co.id | -A_n-a5o#2Ha
29 | Bambang Sumartono | Central Java | 3374091003740004 | 085742288777 | bambang_ext.cj@tunggalsahabat.co.id | #1F;)ybihtst
30 | Tri Margiyanto | JAYENGAN | 3311012907830000 | 085332424444 | tri.margiyanto_ext@tunggalsahabat.co.id | QK4rwj]SJ2YF
31 | Yoricho Bashkara | PEMENANG BARAT | 3275091304950022 | 087845606243 | yoricho.bashkara@tunggal.sahabat.co.id | QJ0mrq3Vy,IN
32 | Yayat | Kayoon | 3211180401790001 | 083148960851 | yayat_ext@tunggalsahabat.co.id | En4W{a.vOGbc
33 | Ajang Suprianto |  |  | 08813913468 | ajang.suprianto_ext@tunggalsahabat.co.id | }2bt8Cs*O=-p
34 | Dede Darno |  |  | 083112166206 | dede.darno_ext@tunggalsahabat.co.id | r5%AXQTo$&ec
35 | Edih |  |  | 085600237809 | edih_ext@tunggalsahabat.co.id | j%V+3]?sfF.]
36 | Priatna | Kayoon | 3211130901890002 | 088295614399 | priatna_ext@tunggalsahabat.co.id | f?~.;{n36q#u
37 | Supriatna | Kayoon | 3211112311740009 | 082286731149 | supriatna_ext@tunggalsahabat.co.id | ,@,WRs)QS(NV
38 | Wino | Kayoon | 3304141604820004 | 085291104789 | wino_ext@tunggalsahabat.co.id | !?G~9r5=uyaj
39 | Bibit Purwanto | Kayoon | 3373010201840002 | +62 822-3408-7449 | bibit.purwanto_ext@tunggalsahabat.co.id | O.V}mG@4m-4}
40 | Tri Heru Saputro | Kayoon | 3374131107810002 | +62 856-4341-6014 | tri.herusaputro_ext@tunggalsahabat.co.id | 8n0X3d5_25N5
41 | Slamet Riyadi | Kayoon | 3306060307830004 | +62 831-3121-2477 | slamet.riyadi_ext@tunggalsahabat.co.id | k*Q(qI+i(S$_
42 | Beni Prasetyo | Kayoon | 3373011001800006 | +62 831-9397-3243 | beni.prasetyo_ext@tunggalsahabat.co.id | K#&&R-~IIfn*
43 | Sodikin | Kayoon | 3322060912820001 | +62 851-8935-4982 | sodikin_ext@tunggalsahabat.co.id | Tt]ee(aWmO#o
44 | Eko Hariyanto | Kayoon | 3373012007830003 | +62 857-0466-5890 | eko.hariyanto_ext@tunggalsahabat.co.id | 2]#aCG?p$K$h
45 | Dafit Suhirwanto | Kayoon | 3322062408850001 | +62 819-3668-3830 | dafit.suhirwanto_ext@tunggalsahabat.co.id | 8X6xX7df3ohm
46 | Prolis Heru Murdiyanto | Kayoon | 3578060812800003 | +62 822-2881-9193 | prolisheru@tunggalsahabat.co.id
47 | Kusmana Ardiansyah |  |  |  | kusmana.ardiansyah_ext@tunggalsahabat.co.id | v6bzIUL3?-[V
48 | Al Kasan Sahbrawi |  |  |  | alkasan.sahbrawi_ext@tunggalsahabat.co.id | OCiAox(@n=a8
49 | H Ajo Eko |  |  |  | h.ajoeko_ext@tunggalsahabat.co.id | jXl$;%Xg9ph9
50 | Repah Eka Wigelar |  |  |  | repah.eka_ext@tunggalsahabat.co.id | noPXzC-TA!g&
51 | Endi Suhendi |  |  |  | endi.suhendi_ext@tunggalsahabat.co.id | sUO$ZVnsgI%[
52 | Dedi |  |  |  | dedi_ext@tunggalsahabat.co.id | VOt,q%0kld_w
53 | Mastam |  |  |  | mastam_ext@tunggalsahabat.co.id | Ab!CR8obxp=r
54 | Nur Arifin |  |  |  | nur.arifin_ext@tunggalsahabat.co.id | ?42[Ggyk+XQz
55 | Rifaldi |  |  |  | rifaldi_ext@tunggalsahabat.co.id | uq(T.y?km5qn
56 | Taufan Agya Wiguna |  |  |  | taufan.agya_ext@tunggalsahabat.co.id | myJeqR}2e9-C
57 | Demak Hutahean | Sumatera Utara | 1211012412890002
58 | Sumarlin Kaban | Sumatera Utara | 1211060207940001
59 | Jumadi Tampubolon | Sumatera Utara | 1207062105870002
60 | Arnold Zeneger Sigalingging | Sumatera Utara | 1211012911940002
61 | Miskam | Sumatera Utara | 3207361807810001
62 | Giyanto | Jabo | 3674040107780002 | +62 812-9264-9788 | giyanto.wj_ext@tunggalsahabat.co.id | M#U.(Ni#fSt}
63 | Stefanus Jatmiko |  |  |  | stefanus.jatmiko_ext@tunggalsahabat.co.id | DX_!HoF*>ZL
64 | Yadi Hermansyah |  |  |  | yadi.hermansyah_ext@tunggalsahabat.co.id | XxkCR2#Up!.,
65 | Apudin Maulana |  |  |  | apudin.maulana_ext@tunggalsahabat.co.id | oVfC,o*Y2JB~
66 | Fauzi Arief |  |  |  | fauzi.arief_ext@tunggalsahabat.co.id | d}AItFWa-XG!
67 | Ari Suryanto |  |  |  | ari.suryanto_ext@tunggalsahabat.co.id | s~lFTI1pvQ)I
68 | Afryla Akbar |  |  |  | afryla.akbar_ext@tunggalsahabat.co.id | 8~Q{H?vaEhg3
69 | Husen Wahyudi |  |  |  | husen.wahyudi_ext@tunggalsahabat.co.id | ixB#YM-kiyWt
70 | Onie Albert Manopo |  |  |  | onie.albert_ext@tunggalsahabat.co.id | tS&XSM.j]aR@
71 | Jefri Mokotika |  |  |  | jefri.mokotika_ext@tunggalsahabat.co.id | NmmPLD4Vk,xn
72 | Ongky Kevin Tandaju |  |  |  | ongky.kevin_ext@tunggalsahabat.co.id | Y&?OB,04Rm32
73 | Yosua Ronaldo Andu |  |  |  | yosua.ronaldo_ext@tunggalsahabat.co.id | 3B~FW4d*+=2y
74 | Saharuddin |  |  |  | saharuddin_ext@tunggalsahabat.co.id | 5^+30,Pj=07M
75 | Topan Effendy |  |  |  | topan.effendy_ext@tunggalsahabat.co.id | Nq%gj$WjV2vo
76 | Yoan Rivandi |  |  |  | yoan.rivandi_ext@tunggalsahabat.co.id | y+!~4SMQhLrQ
Formulas:
Validity Account = IF([Expired Account]="","",[Expired Account]-TODAY())
Expired Account = +[Start Account]+60

## SPH
6826391.4
| 1 | 1 | 1 | [7 empty] | 667947513.6
No | Account Project | Site ID | Site Name | Create Date | SPH Number | Scope | Description | Qty | UoM | Price | Total | DRM | BAN App | BAN Number | Remark
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Dismantle Tower | Biaya buat Pagar site keliling 48 m² | 1 | All In | 75000000 | 75000000 |  | 2025-10-30
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Dismantle Tower | Management fee pembuatan Pagar | 0.1 | All In | 75000000 | 7500000 |  | 2025-10-30
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Dismantle Tower | sewa genset 5 kva | 2 | day | 1200000 | 2400000 |  | 2025-10-30
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Dismantle Tower | BBM Genset | 2 | day | 150000 | 300000 |  | 2025-10-30
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Dismantle Tower | Operator Genset | 2 | day | 150000 | 300000 |  | 2025-10-30
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Relocation Equipment | Kabel AWG 10 XL | 100 | meter | 35000 | 3500000 |  | 2025-10-30
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Relocation Equipment | Kabel AWG 6 IOH | 200 | meter | 55000 | 11000000 |  | 2025-10-30
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Relocation Equipment | Kabel Feeder 7/8 | 500 | meter | 50000 | 25000000 |  | 2025-10-30
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Relocation Equipment | Jumper Feeder | 10 | pcs | 450000 | 4500000 |  | 2025-10-30
| CMI-RLC-Nasional | E3500300 | DUKUH_KUPANG | 2025-08-22 | 006/TSA-SPH-CMI/VIII/2025 | Relocation Equipment | Connector Feeder | 20 | pcs | 75000 | 1500000 |  | 2025-10-30
| CMI-RLC-Nasional | E3300285 | JAYENGAN | 2025-10-31 | 014/TSA-SPH-CMI/X/2025 | Dismantle Tower | Pembongkaran pondasi ex tower dan bts serta perapian renovasi gedung oleh pihak pemilik lahan | 1 | Ls | 4650000 | 4650000 |  | 2026-01-06
| CMI-RLC-Nasional | E3300285 | JAYENGAN | 2025-10-31 | 014/TSA-SPH-CMI/X/2025 | Dismantle Tower | Management Fee | 1 | Ls | 2700000 | 2700000 |  | 2026-01-06
| CMI-RLC-Nasional | E1200372 | NONGSA_RESORT_1 | 2025-10-13 | 007/TSA-SPH-CMI/X/2025 | Dismantle Tower | Scrap Lokal onsite | 13067.71 | Kg | -1500 | -19601565 |  | 2025-12-09
| CMI-RLC-Nasional | E1200372 | NONGSA_RESORT_1 | 2025-10-13 | 007/TSA-SPH-CMI/X/2025 | Dismantle Tower | Management Fee | 1 | Ls | 2700000 | 2700000 |  | 2025-12-09
| CMI-RLC-Nasional | E1200372 | NONGSA_RESORT_1 | 2025-10-13 | 007/TSA-SPH-CMI/X/2025 | Dismantle Tower | Material + Jasa pembuatan rumah genset | 1 | Ls | 4000000 | 4000000 |  | 2025-12-09
| CMI-RLC-Nasional | E1200372 | NONGSA_RESORT_1 | 2025-10-13 | 007/TSA-SPH-CMI/X/2025 | Dismantle Tower | Reinstall Genset | 1 | Ls | 6000000 | 6000000 |  | 2025-12-09
| CMI-RLC-Nasional | E1200372 | NONGSA_RESORT_1 | 2025-10-13 | 007/TSA-SPH-CMI/X/2025 | Relocation Equipment | Pembelian rack outdoor | 2 | Unit | 6000000 | 12000000 |  | 2025-12-09
| CMI-RLC-Nasional | E1200372 | NONGSA_RESORT_1 | 2025-10-13 | 007/TSA-SPH-CMI/X/2025 | Relocation Equipment | Pembelian kabel power NYFGBY 4 x 16 | 12 | Meter | 165000 | 1980000 |  | 2025-12-09
| CMI-RLC-Nasional | E1200372 | NONGSA_RESORT_1 | 2025-10-13 | 007/TSA-SPH-CMI/X/2025 | Relocation Equipment | Optic 100 meter | 8 | Pcs | 400000 | 3200000 |  | 2025-12-09
| CMI-RLC-Nasional | E1200372 | NONGSA_RESORT_1 | 2025-10-13 | 007/TSA-SPH-CMI/X/2025 | Relocation Equipment | Tiket Pesawat Jakarta - Batam | 4 | Person | 1000000 | 4000000 |  | 2025-12-09
| CMI-RLC-Nasional | E1200372 | NONGSA_RESORT_1 | 2025-10-13 | 007/TSA-SPH-CMI/X/2025 | Relocation Equipment | Tiket Pesawat Batam - Jakarta | 4 | Person | 1000000 | 4000000 |  | 2025-12-09
| CMI-RLC-Nasional | E3600214 | SUPERMAL | 2025-10-29 | 013/TSA-SPH-CMI/X/2025 | Dismantle Tower | Management Fee | 1 | Ls | 2700000 | 2700000
| CMI-RLC-Nasional | E3600214 | SUPERMAL | 2025-10-29 | 013/TSA-SPH-CMI/X/2025 | Relocation Equipment | Pembelian Rack Outdoor include delivery | 2 | unit | 7000000 | 14000000
| CMI-RLC-Nasional | E3600214 | SUPERMAL | 2025-10-29 | 013/TSA-SPH-CMI/X/2025 | Relocation Equipment | Pembelian Kabel AWG 10 | 175 | meter | 35000 | 6125000
| CMI-RLC-Nasional | E3600214 | SUPERMAL | 2025-10-29 | 013/TSA-SPH-CMI/X/2025 | Relocation Equipment | Pembelian opctic CPRI 70 meter | 7 | pcs | 250000 | 1750000
| CMI-RLC-Nasional | E3600214 | SUPERMAL | 2025-10-29 | 013/TSA-SPH-CMI/X/2025 | Relocation Equipment | Pembelian Kabel coax RG8 | 100 | meter | 15000 | 1500000
| CMI-RLC-Nasional | E1200351 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2025-11-04 | 001/TSA-SPH-CMI/XI/2025 | Dismantle Tower | Scrap Lokal onsite | 1488.6 | Kg | -1500 | -2232900 |  | 2026-12-09
| CMI-RLC-Nasional | E1200351 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2025-11-04 | 001/TSA-SPH-CMI/XI/2025 | Dismantle Tower | Management Fee | 1 | Ls | 2700000 | 2700000 |  | 2026-12-09
| CMI-RLC-Nasional | E1200351 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2025-11-04 | 001/TSA-SPH-CMI/XI/2025 | Dismantle Tower | Membrane bakar merk fosroc 14 meter (2 rol x 10 m) | 2 | roll | 1700000 | 3400000 |  | 2026-12-09
| CMI-RLC-Nasional | E1200351 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2025-11-04 | 001/TSA-SPH-CMI/XI/2025 | Dismantle Tower | Tukang pasang membrane bakar | 14 | meter | 80000 | 1120000 |  | 2026-12-09
| CMI-RLC-Nasional | E1200351 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2025-11-04 | 001/TSA-SPH-CMI/XI/2025 | Dismantle Tower | Ongkos unloading material ke lt 6 | 1 | Ls | 300000 | 300000 |  | 2026-12-09
| CMI-RLC-Nasional | E1200351 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2025-11-04 | 001/TSA-SPH-CMI/XI/2025 | Dismantle Tower | PB-CME-266 Plester Aci | 22 | M² | 56000 | 1232000 |  | 2026-12-09
| CMI-RLC-Nasional | E1200351 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2025-11-04 | 001/TSA-SPH-CMI/XI/2025 | Dismantle Tower | PB-CME-266 Waterproofing (SikaTop 107 Seal) | 22 | M² | 44000 | 968000 |  | 2026-12-09
| CMI-RLC-Nasional | E1200351 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2025-11-04 | 001/TSA-SPH-CMI/XI/2025 | Dismantle Tower | PB-CME-271 Pengecatan | 29 | M² | 64000 | 1856000 |  | 2026-12-09
| CMI-RLC-Nasional | R5100062 | SMPK_THOMAS_AQUINO | 2025-10-09 | 006/TSA-SPH-CMI/X/2025 | Dismantle Tower | Project Management fee | 1 | Ls | 2700000 | 2700000 |  | 2025-12-08
| CMI-RLC-Nasional | R5100062 | SMPK_THOMAS_AQUINO | 2025-10-09 | 006/TSA-SPH-CMI/X/2025 | Dismantle Tower | Delivery material scrap | 1193.68 | Kg | 1800 | 2148624 |  | 2025-12-08
| CMI-RLC-Nasional | R5100062 | SMPK_THOMAS_AQUINO | 2025-10-09 | 006/TSA-SPH-CMI/X/2025 | Dismantle Tower | Biaya Langsir roaster dari site ke WH TSA Surabaya | 1 | Ls | 6000000 | 6000000 |  | 2025-12-08
| CMI-RLC-Nasional | E6400049 | WADUK MANGGAR | 2025-12-11 | 001/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Ticket Pesawat Semarang to Balikpapan | 5 | orang | 1800000 | 9000000 |  | 2026-01-06
| CMI-RLC-Nasional | E6400049 | WADUK MANGGAR | 2025-12-11 | 001/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Ticket Kapal Laut Balikpapan to Semarang | 5 | orang | 935000 | 4675000 |  | 2026-01-06
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-09-15 | 006/TSA-SPH-CMI/IX/2025 | Relocation Equipment | Pembelian Rak Outdoor + Delivery | 1 | Set | 3000000 | 3000000 |  | 2025-12-08
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-09-15 | 006/TSA-SPH-CMI/IX/2025 | Relocation Equipment | Ticket Pesawat Makassar - Ternate | 8 | orang | 1455400 | 11643200 |  | 2025-12-08
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-09-15 | 006/TSA-SPH-CMI/IX/2025 | Relocation Equipment | Ticket Pesawat Ternate - Makassar | 8 | orang | 1455400 | 11643200 |  | 2025-12-08
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-09-15 | 006/TSA-SPH-CMI/IX/2025 | Relocation Equipment | Jasa Pengambilan Rack + Delivery Makassar ke site | 1 | Ls | 2550000 | 2550000 |  | 2025-12-08
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-09-15 | 006/TSA-SPH-CMI/IX/2025 | Relocation Equipment | Pengiriman MW dari Makassar ke site | 1 | Ls | 4500000 | 4500000 |  | 2025-12-08
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-12-30 | 004/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Ticket Pesawat team dismantle tower Surabaya - Ternate | 5 | orang | 2244900 | 11224500 |  | 2026-01-27
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-12-30 | 004/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Ticket Pesawat team dismantle tower Ternate - Surabaya | 5 | orang | 1998200 | 9991000 |  | 2026-01-27
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-12-30 | 004/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Ticket Speedboat Ternate - Jailolo PP | 5 | orang | 220000 | 1100000 |  | 2026-01-27
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-12-30 | 004/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Ticket Bus Semarang - Surabaya PP | 5 | orang | 200000 | 1000000 |  | 2026-01-27
| CMI-RLC-Nasional | E8200008 | JAILOLO | 2025-12-30 | 004/TSA-SPH-CMI/XII/2025 | Relocation Equipment | Reloc Genset | 1 | Ls | 4000000 | 4000000 |  | 2026-01-27
| CMI-RLC-Nasional | R6300038 | TRANS KALIMANTAN | 2026-02-06 | 002/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable Power RRU Awg 2x10 IOH | 50 | meter | 35000 | 1750000 |  | 2026-04-23
| CMI-RLC-Nasional | R6300038 | TRANS KALIMANTAN | 2026-02-06 | 002/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable Power RRU Awg 2x10 XLS | 30 | meter | 35000 | 1050000 |  | 2026-04-23
| CMI-RLC-Nasional | E1200343 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | 2025-12-29 | 009/TSA-SPH-CMI/XI/2025 | Dismantle Tower |  | 8236.656 | Kg | -1500 | -12354984 |  | 2026-01-27
| CMI-RLC-Nasional | E1200343 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | 2025-12-29 | 009/TSA-SPH-CMI/XI/2025 | Dismantle Tower | Project Management fee | 1 | Ls | 2700000 | 2700000 |  | 2026-01-27
| CMI-RLC-Nasional | E1200343 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | 2025-12-29 | 009/TSA-SPH-CMI/XI/2025 | Relocation Equipment | Pembelian kabel twisted 2 x 16 (70m x 3tarikan) | 210 | M | 45000 | 9450000 |  | 2026-01-27
| CMI-RLC-Nasional | E1200343 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | 2025-12-29 | 009/TSA-SPH-CMI/XI/2025 | Relocation Equipment | Pembelian optic 100m x 3tarikan | 300 | M | 10000 | 3000000 |  | 2026-01-27
| CMI-RLC-Nasional | R3100450 | KEBON SIRIH | 2025-12-23 | 004/TSA-SPH-CMI/XII/2025 | Relocation Equipment | Management Fee | 1 | Ls | 2700000 | 2700000 |  | 2026-01-28
| CMI-RLC-Nasional | R3100450 | KEBON SIRIH | 2025-12-23 | 004/TSA-SPH-CMI/XII/2025 | Relocation Equipment | Jasa Kontraktor / AKLI | 1 | Ls | 3300000 | 3300000 |  | 2026-01-28
| CMI-RLC-Nasional | R3100450 | KEBON SIRIH | 2025-12-23 | 004/TSA-SPH-CMI/XII/2025 | Relocation Equipment | Multiguna PLN 24-12-25 sd 20-01-26 | 1 | Ls | 14947622 | 14947622 |  | 2026-01-28
| CMI-RLC-Nasional | R3580411 | PEGANTENAN | 2025-12-29 | 002/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Sewa Alat Berat | 7 | hari | 4600000 | 32200000 |  | 2026-04-06
| CMI-RLC-Nasional | R3580411 | PEGANTENAN | 2025-12-29 | 002/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Buang puing pondasi | 29 | rit | 250000 | 7250000 |  | 2026-04-06
| CMI-RLC-Nasional | R3580411 | PEGANTENAN | 2025-12-29 | 002/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Import Soil | 70.4 | m3 | 125000 | 8800000 |  | 2026-04-06
| CMI-RLC-Nasional | R3580411 | PEGANTENAN | 2025-12-29 | 002/TSA-SPH-CMI/XII/2025 | Dismantle Tower | Management Fee sewa alat berat & buang pondasi | 1 | Ls | 3945000 | 3945000 |  | 2026-04-06
| CMI-RLC-Nasional | E3600061 | PARUNGSARI | 2026-03-16 | 007/TSA-SPH-CMI/I/2026 | Relocation Equipment | Kabel power twist 4x16mm | 100 | meter | 22500 | 2250000 |  | 2026-04-06
| CMI-RLC-Nasional | E3600061 | PARUNGSARI | 2026-03-16 | 007/TSA-SPH-CMI/I/2026 | Relocation Equipment | Tiang FO 7m IOH | 1 | pcs | 1500000 | 1500000 |  | 2026-04-06
| CMI-RLC-Nasional | E3600061 | PARUNGSARI | 2026-03-16 | 007/TSA-SPH-CMI/I/2026 | Relocation Equipment | Jasa Pasang tiang FO | 1 | Ls | 500000 | 500000 |  | 2026-04-06
| CMI-RLC-Nasional | E3600061 | PARUNGSARI | 2026-03-16 | 007/TSA-SPH-CMI/I/2026 | Relocation Equipment | Jasa Pemindahan + Splicing 24 Core FO TSEL | 1 | Ls | 1000000 | 1000000 |  | 2026-04-06
| CMI-RLC-Nasional | E3600061 | PARUNGSARI | 2026-03-16 | 007/TSA-SPH-CMI/I/2026 | Relocation Equipment | Jasa Pemindahan + Splicing 12 Core+Cable 100m FO Mandau (IOH) | 1 | Ls | 950000 | 950000 |  | 2026-04-06
| CMI-RLC-Nasional | E3600061 | PARUNGSARI | 2026-03-16 | 007/TSA-SPH-CMI/I/2026 | Relocation Equipment | PB-PWR-18 Reinstall Genset, Fuel Tank, ATS (Inc. Wiring, Commisioning and Fungtional Test) | 1 | set | 4000000 | 4000000 |  | 2026-04-06
| CMI-RLC-Nasional | E6400129 | SUSUK | 2026-01-12 | 005/TSA-SPH-CMI/I/2026 | Dismantle Tower | Bus Semarang to Surabaya PP | 5 | orang | 600000 | 3000000 |  | 2026-01-29
| CMI-RLC-Nasional | E6400129 | SUSUK | 2026-01-12 | 005/TSA-SPH-CMI/I/2026 | Dismantle Tower | Tiket Pesawat Surabaya to Samarinda | 5 | orang | 2800000 | 14000000 |  | 2026-01-29
| CMI-RLC-Nasional | E6400129 | SUSUK | 2026-01-12 | 005/TSA-SPH-CMI/I/2026 | Dismantle Tower | Travel Samarinda to Site PP | 5 | orang | 600000 | 3000000 |  | 2026-01-29
| CMI-RLC-Nasional | E6400129 | SUSUK | 2026-01-12 | 005/TSA-SPH-CMI/I/2026 | Relocation Equipment | Tiket Pesawat Jakarta to Samarinda | 5 | orang | 3900000 | 19500000 |  | 2026-01-29
| CMI-RLC-Nasional | E6400129 | SUSUK | 2026-01-12 | 005/TSA-SPH-CMI/I/2026 | Relocation Equipment | Travel Samarinda to Site PP | 5 | orang | 600000 | 3000000 |  | 2026-01-29
| CMI-RLC-Nasional | R6400134 | BATUAH KM.45 | 2026-01-14 | 006/TSA-SPH-CMI/I/2026 | Relocation Equipment | PB-PWR-18 Re instal Genset,Fuel tank,ATS (Inc wiring,Commisioning and Fungtional Test) | 1 | Ls | 4000000 | 4000000
| CMI-RLC-Nasional | E3200525 | GEDUNG_LIPPO | 2026-02-05 | 001/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable Optik CPRI SM 70m | 1 | tarikan | 250000 | 250000 |  | 2026-04-06 |  | Cancel
| CMI-RLC-Nasional | E3200525 | GEDUNG_LIPPO | 2026-02-05 | 001/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable Jumper DM-N4310 3m | 2 | pcs | 350000 | 700000 |  | 2026-04-06 |  | Cancel
| CMI-RLC-Nasional | E3200525 | GEDUNG_LIPPO | 2026-02-05 | 001/TSA-SPH-CMI/II/2026 | Relocation Equipment | P02-003-017 Supply and Install NYFGBY 4x16 mm2 include Accessories | 7 | meter | 165000 | 1155000 |  | 2026-04-06 |  | Cancel
| CMI-RLC-Nasional | E3200525 | GEDUNG_LIPPO | 2026-02-05 | 001/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable Power RRU Awg 2x10 | 60 | meter | 35000 | 2100000 |  | 2026-04-06 |  | Cancel
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-02-09 | 003/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable coax MW IOH | 40 | meter | 20000 | 800000 |  | 2026-04-06 | 011-DR-BAN/0426
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-02-09 | 003/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable Power RRU IOH 15 meter x 6 tarikan | 90 | meter | 35000 | 3150000 |  | 2026-04-06 | 011-DR-BAN/0426
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-02-09 | 003/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable Power RRU XL 20 meter x 6 tarikan | 120 | meter | 35000 | 4200000 |  | 2026-04-06 | 011-DR-BAN/0426
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-02-09 | 003/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable Power RRU Tsel 10 meter x 7 tarikan | 70 | meter | 35000 | 2450000 |  | 2026-04-06 | 011-DR-BAN/0426
| CMI-RLC-Nasional | R7300203 | KIMA 2 | 2026-02-12 | 004/TSA-SPH-CMI/II/2026 | Relocation Equipment | Cable Power RRU IOH 4 Meter x 4 Tarikan | 16 | meter | 35000 | 560000 |  | 2026-04-23
| CMI-RLC-Nasional | R1200302 | BANGUN PURBA | 2026-02-27 | 005/TSA-SPH-CMI/II/2026 | Relocation Equipment | PB-PWR-18 Reinstall Genset, Fuel Tank, ATS (Inc. Wiring, Commisioning and Fungtional Test) | 1 | set | 4000000 | 4000000 |  | 2026-05-05
| CMI-RLC-Nasional | R1200302 | BANGUN PURBA | 2026-02-27 | 005/TSA-SPH-CMI/II/2026 | Relocation Equipment | Pembelian Rak Outdoor + Delivery | 1 | set | 7000000 | 7000000 |  | 2026-05-05
| CMI-RLC-Nasional | R35780005 | WONOKESUMO | 2026-03-12 | 001/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Pulling cable FO | 200 | meter | 5000 | 1000000 |  | 2026-04-23
| CMI-RLC-Nasional | R35780005 | WONOKESUMO | 2026-03-12 | 001/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Bongkar pasang OTB | 1 | pcs | 350000 | 350000 |  | 2026-04-23
| CMI-RLC-Nasional | R35780005 | WONOKESUMO | 2026-03-12 | 001/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Joint core | 144 | core | 40000 | 5760000 |  | 2026-04-23 | 017-DR-BAN 0426
| CMI-RLC-Nasional | E3100287 | KAMPUNG_SAWAH | 2026-04-07 | 002/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Kabel Power Twisted | 50 | meter | 14000 | 700000
| CMI-RLC-Nasional | E3100287 | KAMPUNG_SAWAH | 2026-04-07 | 002/TSA-SPH-CMI/IV/2026 | Relocation Equipment | PB-PWR-18 Reinstall Genset, Fuel Tank, ATS (Inc. Wiring, Commisioning and Fungtional Test) | 1 | set | 4000000 | 4000000
| CMI-RLC-Nasional | E3100287 | KAMPUNG_SAWAH | 2026-04-07 | 002/TSA-SPH-CMI/IV/2026 | Relocation Equipment | E02-005-002 Galian tanah pondasi | 1.56 | m3 | 43698 | 68168.88
| CMI-RLC-Nasional | E3100287 | KAMPUNG_SAWAH | 2026-04-07 | 002/TSA-SPH-CMI/IV/2026 | Relocation Equipment | E02-005-003 Urugan kembali tanah pondasi | 0.55 | m3 | 34656 | 19060.8
| CMI-RLC-Nasional | E3100287 | KAMPUNG_SAWAH | 2026-04-07 | 002/TSA-SPH-CMI/IV/2026 | Relocation Equipment | E02-005-007-1 Volume beton K-225 tanpa tulangan | 0.53 | m3 | 2084061 | 1104552.33
| CMI-RLC-Nasional | E3100287 | KAMPUNG_SAWAH | 2026-04-07 | 002/TSA-SPH-CMI/IV/2026 | Relocation Equipment | E02-005-008 Pondasi batu kali incl tangga | 3.27 | m3 | 483357 | 1580577.39
| CMI-RLC-Nasional | E3100287 | KAMPUNG_SAWAH | 2026-04-07 | 002/TSA-SPH-CMI/IV/2026 | Relocation Equipment | E02-005-012 Sand layer | 0.2 | m3 | 270160 | 54032
| CMI-RLC-Nasional | E3200269 | CILEUNGSIKIDUL | 2026-04-15 | 003/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Pulling cable FO IOH & SF | 90 | meter | 5000 | 450000 | 2026-04-30 | 2026-05-05 | 020-DR-BAN 0526
| CMI-RLC-Nasional | E3200269 | CILEUNGSIKIDUL | 2026-04-15 | 003/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Bongkar pasang OTB IOH & SF | 2 | pcs | 350000 | 700000 | 2026-04-30 | 2026-05-05 | 020-DR-BAN 0526
| CMI-RLC-Nasional | E3200269 | CILEUNGSIKIDUL | 2026-04-15 | 003/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Joint core IOH & SF | 120 | core | 40000 | 4800000 | 2026-04-30 | 2026-05-05 | 020-DR-BAN 0526
| CMI-RLC-Nasional | E6400127 | N_KALIORANG | 2026-04-09 | 005/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Delivery Cabinet from Balikpapan to site | 1 | Ls | 2000000 | 2000000 |  | 2026-05-05 | 022-DR-BAN 0526
| CMI-RLC-Nasional | E6400127 | N_KALIORANG | 2026-04-09 | 005/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Kabel NYY 4x16 ACPDB to Recty | 5 | meter | 130000 | 650000 |  | 2026-05-05 | 022-DR-BAN 0526
| CMI-RLC-Nasional | E6400127 | N_KALIORANG | 2026-04-09 | 005/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Pengadaan rack enclosure | 1 | pcs | 3000000 | 3000000 |  | 2026-05-05 | 022-DR-BAN 0526
| CMI-RLC-Nasional | E6400127 | N_KALIORANG | 2026-04-09 | 005/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Akomodasi Team 2 orang | 3 | hari | 400000 | 1200000 |  | 2026-05-05 | 022-DR-BAN 0526
| CMI-RLC-Nasional | R35780005 | WONOKESUMO | 2026-04-10 | 006/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Cable Power RRU Telkomsel Awg 2x10 (32m x 9tarikan) | 288 | meter | 35000 | 10080000 | 2026-06-03 | 2026-07-27 | 034-DR-BAN 0726
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-04-16 | 007/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Tagihan Listrik April 2026 | 1 | bulan | 1508284 | 1508284 |  | 2026-05-05 | 024/DR-BAN/0526
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-04-16 | 007/TSA-SPH-CMI/IV/2026 | Relocation Equipment | BPUJL | 1 | unit | 4542700 | 4542700 |  | 2026-05-05 | 024/DR-BAN/0526
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-04-16 | 007/TSA-SPH-CMI/IV/2026 | Relocation Equipment | NIDI + SLO | 1 | unit | 1500000 | 1500000 |  | 2026-05-05 | 024/DR-BAN/0526
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-04-16 | 007/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Jasa AKLI | 1 | unit | 3300000 | 3300000 |  | 2026-05-05 | 024/DR-BAN/0526
| CMI-RLC-Nasional | E5300006 | V_LEMBOR | 2026-04-16 | 008/TSA-SPH-CMI/IV/2026 | Dismantle Tower | Ticket Surabaya - Labuan Bajo | 5 | orang | 2240140 | 11200700 | 2026-04-30 | 2026-05-05 | 019/DR-BAN/0526
| CMI-RLC-Nasional | E5300006 | V_LEMBOR | 2026-04-16 | 008/TSA-SPH-CMI/IV/2026 | Dismantle Tower | Ticket Labuan Bajo - Surabaya | 5 | unit | 2150414 | 10752070 | 2026-04-30 | 2026-05-05 | 019/DR-BAN/0526
| CMI-RLC-Nasional | R7200006 | NALU | 2026-04-21 | 009/TSA-SPH-CMI/IV/2026 | Dismantle Tower | Ticket Pesawat Team Makassar - Palu | 6 | orang | 1590044 | 9540264 | 2026-06-03 |  |  | Pending
| CMI-RLC-Nasional | R7200006 | NALU | 2026-04-21 | 009/TSA-SPH-CMI/IV/2026 | Dismantle Tower | Ticket Pesawat Team Palu - Makassar | 6 | orang | 1383200 | 8299200 | 2026-06-03
| CMI-RLC-Nasional | E3100485 | PEDONGKELAN | 2026-04-28 | 010/TSA-SPH-CMI/IV/2026 | Relocation Equipment | Cable Power RRU Awg 2x10 untuk Telkomsel | 30 | meter | 35000 | 1050000 |  | 2026-05-05 | 023/DR-BAN/0526
| CMI-RLC-Nasional | E7100037 | ROAD TO TAMAKO | 2026-05-04 | 001/TSA-SPH-CMI/V/2026 | Dismantle Tower | Ticket Makassar - Manado | 6 | orang | 1667400 | 10004400 | 2026-06-03 |  |  | cancel karena team langsung ke V_Tahuna
| CMI-RLC-Nasional | E7100037 | ROAD TO TAMAKO | 2026-05-04 | 001/TSA-SPH-CMI/V/2026 | Dismantle Tower | Ticket Manado - Makassar | 6 | orang | 1667400 | 10004400 | 2026-06-03 |  |  | cancel karena team langsung ke V_Tahuna
| CMI-RLC-Nasional | R1200302 | BANGUN PURBA | 2026-05-21 | 002/TSA-SPH-CMI/V/2026 | Relocation Equipment | Delivery Cabinet recty | 1 | set | 9500000 | 9500000 | 2026-06-03
| CMI-RLC-Nasional | R1200302 | BANGUN PURBA | 2026-05-21 | 002/TSA-SPH-CMI/V/2026 | Relocation Equipment | Additional Team Reloc untuk 3 hari | 4 | orang | 1000000 | 4000000 | 2026-06-03
| CMI-RLC-Nasional | E9400005 | TVRI BIAK | 2026-05-08 | 003/TSA-SPH-CMI/V/2026 | Dismantle Tower | Scrap Material onsite | 22270.78 | kg | -1500 | -33406170 | 2026-05-15 | 2026-06-10 | 028/DR-BAN/0626
| CMI-RLC-Nasional | E7400036 | V_WANCI | 2026-05-12 | 004/TSA-SPH-CMI/V/2026 | Dismantle Tower | Scrap Material onsite | 18868.812 | kg | -1500 | -28303218 | 2026-05-15 | 2026-06-10 | 027/DR-BAN/0626
| CMI-RLC-Nasional | E7100037 | ROAD TO TAMAKO | 2026-05-12 | 005/TSA-SPH-CMI/V/2026 | Dismantle Tower | Scrap Material onsite | 57349.8 | kg | -1200 | -68819760 | 2026-05-15 | 2026-06-10 | 026/DR-BAN/0626
| CMI-RLC-Nasional | E1200119 | TELADAN | 2026-05-13 | 006/TSA-SPH-CMI/V/2026 | Dismantle Tower | Sewa Crane | 1 | hari | 5000000 | 5000000 | 2026-06-03
| CMI-RLC-Nasional | E7100038 | V_TAHUNA | 2026-05-12 | 007/TSA-SPH-CMI/V/2026 | Dismantle Tower | Scrap Material onsite | 18868.812 | kg | 1200 | 22642574.4
| CMI-RLC-Nasional | E1200337 | BUKIT_BALADA | 2026-05-21 | 008/TSA-SPH-CMI/V/2026 | Dismantle Tower | Scrap Material onsite | 16910.318 | kg | 1500 | 25365477
| CMI-RLC-Nasional | E1200424 | DAPUR_DUA_BELAS / DAPUR 12 | 2026-05-28 | 009/TSA-SPH-CMI/V/2026 | Dismantle Tower | Scrap Material onsite (Tower + Mounting RF & MW) | 13517.71 | kg | 1500 | 20276565
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-06-20 |  | Relocation Equipment | Tagihan Listrik Juni 2026 551400883538 | 1 | bulan | 1660915 | 1660915 |  |  |  | akan dimasukkan ke site lain
| CMI-RLC-Nasional | R5100055 | T_COW TEUKU UMAR | 2026-06-23 | 002/TSA-SPH-CMI/VI/2026 | Dismantle Tower | Sewa Crane + Mobilisasi | 1 | Ls | 7000000 | 7000000
1 | CMI-RLC-Nasional | E3200525 | GEDUNG_LIPPO | 2026-06-30 | 003/TSA-SPH-CMI/VI/2026 | Relocation Equipment | Cable Optik CPRI SM 70m | 9 | tarikan | 250000 | 2250000
2 | CMI-RLC-Nasional | E3200525 | GEDUNG_LIPPO | 2026-06-30 | 003/TSA-SPH-CMI/VI/2026 | Relocation Equipment | Cable Jumper DM-N4310 3m | 18 | pcs | 350000 | 6300000
3 | CMI-RLC-Nasional | E3200525 | GEDUNG_LIPPO | 2026-06-30 | 003/TSA-SPH-CMI/VI/2026 | Relocation Equipment | P02-003-017 Supply and Install NYFGBY 4x16 mm2 include Accessories | 7 | meter | 165000 | 1155000
4 | CMI-RLC-Nasional | E3200525 | GEDUNG_LIPPO | 2026-06-30 | 003/TSA-SPH-CMI/VI/2026 | Relocation Equipment | Cable Power RRU Awg 2x10 @60m x 9 tarikan | 540 | meter | 35000 | 18900000
5 | CMI-RLC-Nasional | E3200525 | GEDUNG_LIPPO | 2026-06-30 | 003/TSA-SPH-CMI/VI/2026 | Relocation Equipment | Patch Cord LC to LC 15m | 4 | pcs | 250000 | 1000000
1 | CMI-RLC-Nasional | E1200363 | PINTU 4 MUKA KUNING | 2026-07-02 | 001/TSA-SPH-CMI/VI/2026 | Dismantle Tower | Tiket Pesawat Semarang - Batam | 5 | orang | 2116300 | 10581500
2 | CMI-RLC-Nasional | E1200363 | PINTU 4 MUKA KUNING | 2026-07-02 | 001/TSA-SPH-CMI/VI/2026 | Dismantle Tower | Tiket Pesawat Batam - Semarang | 5 | orang | 2116300 | 10581500
1 | CMI-RLC-Nasional | E1200363 | PINTU 4 MUKA KUNING | 2026-05-21 | 001/TSA-SPH-CMI/VI/2026 | Dismantle Tower | Scrap Material onsite | 8762.04 | Kg | 1500 | 13143060
1 | CMI-RLC-Nasional | E3200384 | KARABA INDAH | 2026-07-15 | 004/TSA-SPH-CMI/VII/2026 | Relocation Equipment | PB-PWR-18 Reinstall Genset, Fuel Tank, ATS (Inc. Wiring, Commisioning and Fungtional Test) | 1 | set | 4000000 | 4000000
1 | CMI-RLC-Nasional | R3350408 | TINGKIR SALATIGA | 2026-07-15 | 005/TSA-SPH-CMI/VII/2026 | Relocation Equipment | PB-PWR-18 Reinstall Genset, Fuel Tank, ATS (Inc. Wiring, Commisioning and Fungtional Test) | 1 | set | 4000000 | 4000000
1 | CMI-RLC-Nasional | E1200036 | BANDARA BINAKA | 2026-07-18 | 006/TSA-SPH-CMI/VII/2026 | Dismantle Equipment | Penyeberangan Sibolga ke G. Sitoli | 1 | Ls | 1662500 | 1662500
2 | CMI-RLC-Nasional | E1200036 | BANDARA BINAKA | 2026-07-18 | 006/TSA-SPH-CMI/VII/2026 | Dismantle Equipment | Penyeberangan G. Sitoli ke Sibolga | 1 | Ls | 1662500 | 1662500
3 | CMI-RLC-Nasional | E1200036 | BANDARA BINAKA | 2026-07-18 | 006/TSA-SPH-CMI/VII/2026 | Dismantle Equipment | Rental Mobil | 7 | hari | 500000 | 3500000
4 | CMI-RLC-Nasional | E1200036 | BANDARA BINAKA | 2026-07-18 | 006/TSA-SPH-CMI/VII/2026 | Dismantle Equipment | Penginapan | 5 | hari | 500000 | 2500000
1 | CMI-RLC-Nasional | E1200036 | BANDARA BINAKA | 2026-07-18 | 006/TSA-SPH-CMI/VII/2026 | Dismantle Tower | Scrap Onsite | 22120.78 | Kg | 1500 | 33181170
1 | CMI-RLC-Nasional | R3350202 | RAYA TAHUNAN KALIPANG | 2026-07-18 | 007/TSA-SPH-CMI/VII/2026 | Dismantle Tower | Jasa dismantle kamuflase 30m x 5m = 150m² x 4 sisi = 600m² | 600 | m² | 15000 | 9000000
2 | CMI-RLC-Nasional | R3350202 | RAYA TAHUNAN KALIPANG | 2026-07-18 | 007/TSA-SPH-CMI/VII/2026 | Dismantle Tower | Buang puing fiber kamuflase | 1 | Ls | 1500000 | 1500000
1 | CMI-RLC-Nasional | E3500373 | HOTEL CORE SBY | 2026-07-20 | 008/TSA-SPH-CMI/VII/2026 | Dismantle Tower | Sewa Alat Berat | 1 | Ls | 5000000 | 5000000
| CMI-RLC-Nasional | R5100118 | PENYARINGAN RELOC | 2026-06-20 |  | Relocation Equipment | Tagihan Listrik Juli 2026 551400883538 | 1 | bulan | 1893011 | 1893011 |  |  |  | akan dimasukkan ke site lain
1 | CMI-RLC-Nasional | E3300214 | SALATIGA_SLT | 2026-07-24 | 010/TSA-SPH-CMI/VII/2026 | Relocation Equipment | PB-PWR-18 Reinstall Genset, Fuel Tank, ATS (Inc. Wiring, Commisioning and Fungtional Test) | 1 | set | 4000000 | 4000000
2 | CMI-RLC-Nasional | E3300214 | SALATIGA_SLT | 2026-07-24 | 010/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-002 Galian tanah pondasi | 1.56 | m3 | 43698 | 68168.88
3 | CMI-RLC-Nasional | E3300214 | SALATIGA_SLT | 2026-07-24 | 010/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-003 Urugan kembali tanah pondasi | 0.55 | m3 | 34656 | 19060.8
4 | CMI-RLC-Nasional | E3300214 | SALATIGA_SLT | 2026-07-24 | 010/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-007-1 Volume beton K-225 tanpa tulangan | 0.53 | m3 | 2084061 | 1104552.33
5 | CMI-RLC-Nasional | E3300214 | SALATIGA_SLT | 2026-07-24 | 010/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-008 Pondasi batu kali incl tangga | 3.27 | m3 | 483357 | 1580577.39
6 | CMI-RLC-Nasional | E3300214 | SALATIGA_SLT | 2026-07-24 | 010/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-012 Sand layer | 0.2 | m3 | 270160 | 54032
1 | CMI-RLC-Nasional | E1200036 | BANDARA BINAKA | 2026-07-28 | 011/TSA-SPH-CMI/VII/2026 | Reinstall | Penyeberangan Sibolga ke G. Sitoli | 1 | Ls | 1662500 | 1662500
2 | CMI-RLC-Nasional | E1200036 | BANDARA BINAKA | 2026-07-28 | 011/TSA-SPH-CMI/VII/2026 | Reinstall | Penyeberangan G. Sitoli ke Sibolga | 1 | Ls | 1662500 | 1662500
3 | CMI-RLC-Nasional | E1200036 | BANDARA BINAKA | 2026-07-28 | 011/TSA-SPH-CMI/VII/2026 | Reinstall | Rental Mobil | 7 | hari | 500000 | 3500000
4 | CMI-RLC-Nasional | E1200036 | BANDARA BINAKA | 2026-07-28 | 011/TSA-SPH-CMI/VII/2026 | Reinstall | Penginapan | 5 | hari | 500000 | 2500000
1 | CMI-RLC-Nasional | R6200094 | JUWATA PERMAI | 2026-07-29 | 012/TSA-SPH-CMI/VII/2026 | Relocation Equipment | PB-PWR-18 Reinstall Genset, Fuel Tank, ATS (Inc. Wiring, Commisioning and Fungtional Test) | 1 | set | 4000000 | 4000000
2 | CMI-RLC-Nasional | R6200094 | JUWATA PERMAI | 2026-07-29 | 012/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-002 Galian tanah pondasi | 1.56 | m3 | 43698 | 68168.88
3 | CMI-RLC-Nasional | R6200094 | JUWATA PERMAI | 2026-07-29 | 012/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-003 Urugan kembali tanah pondasi | 0.55 | m3 | 34656 | 19060.8
4 | CMI-RLC-Nasional | R6200094 | JUWATA PERMAI | 2026-07-29 | 012/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-007-1 Volume beton K-225 tanpa tulangan | 0.53 | m3 | 2084061 | 1104552.33
5 | CMI-RLC-Nasional | R6200094 | JUWATA PERMAI | 2026-07-29 | 012/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-008 Pondasi batu kali incl tangga | 3.27 | m3 | 483357 | 1580577.39
6 | CMI-RLC-Nasional | R6200094 | JUWATA PERMAI | 2026-07-29 | 012/TSA-SPH-CMI/VII/2026 | Relocation Equipment | E02-005-012 Sand layer | 0.2 | m3 | 270160 | 54032

## oret2
| Site ID | Site Name | Tower Provider | LATITUDE | LONGITUDE | Height proposed | Azimuth
Near End (Site Acceptor) | JAW-JB-KNG-1359 | JAPARA KUNINGAN | EMA | -6.89649 | 108.51681 | 44
Far End | JAW-JB-KNG-1353 | KUNINGAN BANGUN | DMT | -6.88686 | 108.502806 | existing
| E3200649 | JAPARA

## Update Boram
Update BORAM
[15 empty] | ID Pelanggan PLN | Nama Pelanggan PLN | Nama Site | Alamat | Keterangan
No | Site ID CMI | Site Name CMI | Tenant | Site ID Tenant | Site Name Tenant | ID Pel | Daya (VA) | SPBR Submit CMI | SPBR Release | SPBR Submit PLN | BA Boram | Progress | Remark | BOT PLN | 152001107489 | PT. INDOSAT | PINTU4_MUKA_KUNING_EP | JL. TANJUNG RAYA , MUKA KUNING
1 | R35780005 | WONOKESUMO | IOH | 16SBY0363 | WONOSARILOR_CM | 511040607208 | 10600 | 2026-04-13 |  |  | 2024-10-31 | Done Boram | IOH tidak mengeluarkan SPBR karena id pel tersebut sudah boram
2 | R35780005 | WONOKESUMO | TSEL | SBY098 | PEGIRIANCMI | 511040502273 | 10600 |  |  | 2026-04-13 | 2026-04-24 | Done Boram | SPBR edit sendiri
3 | E3300061 | RSMARGONO | IOH | 14PWT0167 | RSMARGONO_EP | 522011266252 |  | 2025-03-05 | 2025-05-27 | 2025-05-28 | 2025-10-27 | Done Boram
4 | E6400044 | MARKONI | IOH | 22BPP0085 | MARKONI_EP | 232000283760 |  | 2025-08-19 | 2025-08-25 | 2025-08-26 | 2025-09-22 | Done Boram
5 | R3350400 | SUMBER LAWANG | XLS | JAW-JT-SGN-1855 | SUMBER LAWANG | 520591331135 |  | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-20 | Done Boram
6 | E8200008 | JAILOLO | IOH | 32HBR0001 | JAILOLO_EP | 412500929541 |  | 2025-12-23 | 2026-01-07 | 2026-01-07 | 2026-02-19 | Done Boram
7 | R5100120 | PANTAI PANDAWA | IOH | 17DPR0188 | PANTAIPANDAWA_CM | 551201457578 |  | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-06-18 | Done Boram
8 | R3580411 | PEGANTENAN | XLS | JAW-JI-PMK-2000 | PEGANTENAN PAMEKASAN | 517800793803 |  | 2025-12-11 | 2025-12-17 | 2025-12-17 | 2025-12-22 | Done Boram
9 | E3500148 | KEDUNGPRING | IOH | 16LMG0033 | KEDUNGPRING_EP | 518041036694 |  | 2025-09-22 | 2025-09-22 | 2025-09-23 | 2025-10-18 | Done Boram
10 | E3500148 | KEDUNGPRING | XLS | JAW-JI-LMG-4290 | KEDUNGPRING TLANAK | 518041755248 |  | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-10-10 | Done Boram
11 | R6300019 | JL. KELAPA BJM | XLS | KAL-KS-BJM-0197 | JL. KELAPA BJM | 221103103075 |  | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-22 | Done Boram | 19.05.26 Boram done
12 | R6300019 | JL. KELAPA BJM | TSEL | BJM179 | JL. KELAPA BJM | 221103114978 | 10600 | 2026-05-11 | 2026-06-02 | 2026-06-02 | 2026-07-03 | Done Boram
13 | E5100119 | NUSALEMBONGAN | IOH | 17SPR0033 | NUSALEMBONGAN_EP | 551320015922 |  | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-10 | Done Boram
14 | R3350113 | PLIKEN | IOH | 14PWT0194 | PLIKEN_CM | 522020867980
15 | R3350113 | PLIKEN | TSEL |  |  | 522020914363 | 7700
16 | E1200347 | JODOH | IOH | 05BTM0110 | JODOH_EP | 151001044556 |  | 2025-10-06 | 2025-09-30 | 2025-10-01 | 2025-10-27 | Done Boram
17 | R6300038 | TRANS KALIMANTAN | IOH | 23MRB0023 | TRANSKALIMANTAN_CM | 221500493526 | 5500 | 2026-01-08 | 2026-01-08 | 2026-01-19 | 2026-01-20 | Done Boram
18 | R6300038 | TRANS KALIMANTAN | XLS | KAL-KS-MRH-0386 | TRANS KALIMANTAN | 221500137257 | 13200 | 2026-01-08 | 2026-01-08 | 2026-01-19 | 2026-01-20 | Done Boram
19 | E1200343 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | IOH | 05BTM0074 | TEMIANG_BATAM_EP | 152001110528 | 13200 | 2025-12-05 | 2025-12-10 | 2025-12-10 | 2025-12-19 | Done Boram
20 | E1200343 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | XLS | SUM-KR-BTM-0604 | BULIANG | 152002075724 | 6600 | 2025-12-05 | 2025-12-10 | 2025-12-10 | 2025-12-19 | Done Boram
21 | E1200343 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | TSEL | BTM147 | TEMIANG_BATAM BUKIT MATA KUCING 2 | 152001757921 | 10600 | 2025-12-05 | 2025-12-15 | 2025-12-15 | 2025-12-19 | Done Boram
22 | E3600061 | PARUNGSARI | IOH | 11RKB0143 | PARUNGSARI_RKB1_EP | 539211120671 |  | 2025-08-02 | 2025-08-08 | 2025-08-09 | 2025-09-26 | Done Boram
23 | E3600061 | PARUNGSARI | XLS | NJKT_1717 | PARUNGSARI | 562100172529 |  | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-11 | Done Boram
24 | E3600061 | PARUNGSARI | TSEL |  |  | 562101444860 |  | 2025-09-04 | 2025-11-13 | 2025-11-13 | 2025-11-21 | Done Boram
25 | E3200644 | JALAKSANA | IOH | 13KNG0046 | JALAKSANA_EP | 533710563089 |  | 2025-11-14 | 2025-11-28 | 2025-11-28 | No Boram | Done Boram
26 | E3200269 | CILEUNGSIKIDUL | IOH | 13CBN1024 | CIELUNGSIKIDUL_EP | 538654954208 | 23000 | 2026-04-08 | 2026-04-16 | 2026-04-17 | 2026-04-21 | Done Boram
27 | E3200644 | JALAKSANA | XLS | ZCRB_4188 | JALAKSANA | 533711051862 |  | 2025-11-14 | 2025-11-27 | 2025-11-27 | 2025-12-09 | Done Boram
28 | E3200269 | CILEUNGSIKIDUL | XLS | NBGR_0125 | CILEUNGSIKIDUL | 538655662867 | 10600 | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-21 | Done Boram
29 | E3500300 | DUKUH_KUPANG | IOH | 16SBY0152 | DUKUH_KUPANG_EP | 511413067240 |  | 2025-07-31 | 2025-07-31 | 2025-08-01 | 2025-08-14 | Done Boram
30 | E3500300 | DUKUH_KUPANG | XLS | JAW-JI-SBY-2359 | PUTAT GEDE | 511413182597 |  | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-09 | Done Boram
31 | E3300323 | WIROSARI | IOH | 14GRO0118 | WIROSARI_EP | 523073092633 |  | 2025-08-12 |  |  |  | Submit App SPBR
32 | E3200297 | CILOTO | IOH | 13CJR0017 | CILOTO_EP | 536712081435
33 | E3600042 | TOL_CILEGON_SERANG | IOH | 11CLG0103 | TOL_CLGN_SRANG_EP | 539411151940 |  | 2025-09-15 | 2025-09-15 | 2025-10-17 | 2025-10-27 | Done Boram
34 | E3600042 | TOL_CILEGON_SERANG | XLS | JAW-BT-SRG-1198 | BOJONEGARA_SERDANG | 561200596663 |  | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-27 | Done Boram
35 | E3600042 | TOL_CILEGON_SERANG | TSEL |  |  | 539411611457 |  | 2025-09-08 | 2025-11-13 | 2025-11-13 | 2025-11-24 | Done Boram
36 | E3100485 | PEDONGKELAN | IOH | 12JKU0476 | PEDONGKELAN_EP | 545200594263 |  | 2026-04-20 | 2026-05-04 |  |  | SPBR Release | waiting penyambungan inbuilding di new site
37 | E3100485 | PEDONGKELAN | TSEL | JUX617 | MEDAN MARUNDA | 545303131129 |  | 2026-04-20 | 2026-05-04 |  |  | SPBR Release | waiting penyambungan inbuilding di new site
38 | R5100062 | SMPK_THOMAS_AQUINO | XLS | BAL-BA-MGW-0604 | SMPK THOMAS AQUINO | 551103534720 |  | 2025-10-28 | 2025-11-03 | 2025-11-04 | 2025-11-26 | Done Boram
39 | E3300214 | SALATIGA_SLT | IOH | 14STG0029 | SALATIGA_SLT_EP | 523511005416 | 23000
40 | E3300214 | SALATIGA_SLT | XLS | JAW-JT-SLT-2167 | SALATIGA SELATAN | 523511496062 | 17600
41 | E3300288 | PR KUDUS | IOH | 14KDS0024 | PRKUDUS_EP | 520013759025 |  | 2025-09-24 | 2025-09-24 | 2025-09-25 | 2025-09-30 | Done Boram
42 | E1200351 | DANAGRAHA_BUILDING1 / DANA GRAHA | IOH | 05BTM0128 | DANAGRAHA_BUILDING_EP | 151001829409 |  | 2025-10-31 | 2025-10-31 | 2025-11-06 | 2025-12-02 | Done Boram
43 | E1200372 | NONGSA_RESORT_1 | IOH | 05BTM0283 | NONGSA_RESORT_EP | 151000866377 | 13200 | 2025-10-21 | 2025-11-27 | 2025-11-27 | 2025-12-18 | Done Boram
44 | E1200372 | NONGSA_RESORT_1 | XLS | SUM-KR-BTM-0492 | NONGSA_RESORT_1 | 154000398840 | 6600 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-12-09 | Done Boram
45 | E1200372 | NONGSA_RESORT_1 | TSEL | BTM429 | NONGSA_RESORT | 154000200962 | 7700 | 2025-10-27 | 2025-11-07 | 2025-11-12 | 2025-12-09 | Done Boram
46 | R5100118 | PENYARINGAN RELOC | IOH | 17DPS0255 | PENYARINGAN_CM | 551004242550 | 6600 | 2026-01-08 | 2026-01-09 | 2026-02-12 | 2026-02-27 | Done Boram
47 | R5100118 | PENYARINGAN RELOC | XLS | BAL-BA-DPR-0349 | PENYARINGAN BALI Relocation | 551004153092 | 16500 | 2026-01-08 | 2026-01-08 | 2026-02-12 | 2026-02-27 | Done Boram
48 | R5100118 | PENYARINGAN RELOC | TSEL | DPR134 | PENYARINGAN RELOC | 551004164236 | 10600 | 2026-01-08 | 2026-01-23 | 2026-02-12 | 2026-02-27 | Done Boram
49 | R6400134 | BATUAH KM.45 | XLS | KAL-KI-TRG-0464 | BATUAH KM.45 | 231047000599 | 6600 | 2026-01-08 | 2026-01-08 | 2026-01-14 | 2026-02-20 | Done Boram
50 | E3500389 | BURNEH | IOH | 16BKN0064 | BURNEH_EP | 517300513859 | 16500 | 2026-02-09 | 2026-02-23 | 2026-02-23 | 2026-04-02 | Done Boram
51 | R7300461 | Nuri Rajawali | XLS | SUL-SN-MKS-0125 | RAJAWALI | 321401616005 |  | 2025-10-28 | 2025-11-03 | 2025-11-03 | 2025-11-20 | Done Boram
52 | E3500389 | BURNEH | TSEL | BKN109 | BURNEH | 517300843005 | 10600 | 2026-02-09 | 2026-03-03 | 2026-03-04 | 2026-04-02 | Done Boram
53 | R3100496 | KELAPA DUA WETAN | XLS | JAW-JK-CKG-0221 | KELAPA DUA WETAN | 547200633598 |  | 2025-11-13 | 2025-12-11 | 2025-12-11 | 2025-12-12 | Done Boram
54 | E1600040 | MUARA_BELITI | IOH | 07LLG0030 | MUARA_BELITI_EP | 147800047966 | 13200 | 2026-06-26 | 2026-07-02 | 2026-07-02 | 2026-07-13 | Done Boram | 07.07.26 done boram, waiting BA
55 | R3350446 | WURYANTORO | XLS | JAW-JT-WNG-2807 | WURYANTORO | 520601092420 | 13900 | 2025-11-13 | 2025-12-16 | 2025-12-16 | 2026-01-10 | Done Boram
56 | E1600040 | MUARA_BELITI | TSEL |  |  | 147800525248
57 | R3300369 | NUSUKAN I | IOH | 14SKA0067 | KAPTENPT_CM | 520521333891 | 11000
58 | R3300369 | NUSUKAN I | XLS | JAW-JT-SKT-2056 | NUSUKAN RELOCATION 2 | 520521374285 | 13900
59 | R7300203 | KIMA 2 | IOH | 29UPD0326 | IRSUTAMI_BIRA_CM | 321302090948 | 7700 | 2026-01-22 | 2026-02-25 | 2026-02-25 | 2026-03-06 | Done Boram
60 | R7200006 | NALU | IOH | 27TLI0023 | NALU | 315010498239 | 10600 | 2026-04-16 | 2026-04-20 | 2026-04-21 | 2026-04-29 | Done Boram
61 | R3270659 | PERUMNAS CIJERAH | XLS | JAW-JB-BDG-0733 | PERUMNAS CIJERAH | 535555667882 |  | 2025-11-13 | 2025-11-25 | 2025-11-25 | 2025-11-28 | Done Boram
62 | R7300203 | KIMA 2 | XLS | SUL-SN-MKS-0278 | KIMA DUA | 321300601220 | 23000 | 2026-01-22 | 2026-02-18 | 2026-02-18 | 2026-03-06 | Done Boram
63 | R7200006 | NALU | XLS | SUL-ST-TLI-0176 | NALU HANYALAH | 315010360795 | 6600 | 2026-04-16 | 2026-04-20 | 2026-04-21 | 2026-04-29 | Done Boram
64 | E3100424 | SUNTER_B | IOH | 12JKU0296 | SUNTER_JKU1_EP | 545103061273 |  | 2025-11-10 |  |  |  | Submit App SPBR
65 | R3100533 | PELEPAH INDAH | XLS | JAW-JK-TJP-2426 | PELEPAH INDAH | 545102776942 | 16500 | 2026-01-07 | 2026-01-08 | 2026-01-12 | 2026-01-15 | Done Boram
66 | E1200395 | KM 6 TG.PINANG / SUNGAI JANG SEAFOOD | IOH | 05TJG0026 | KM6PINANG_EP | 183090278172 |  | 2026-05-08 | 2026-05-11 | 2026-05-11 | 2026-06-11 | Done Boram | 15.05.26 Boram done (waiting BA Boram)
67 | R3580695 | 3G_Kupang Krajan Sawahan | XLS | JAW-JI-SBY-2377 | KUPANGKRAJAN SAWAHAN | 511063165327 | 13200 | 2026-03-02 | 2026-03-05 | 2026-03-05 | 2026-03-18 | Done Boram
68 | E3100287 | KAMPUNG_SAWAH | IOH | 12JKS0715 | KAMPUNG_SAWAH_EP | 547500442841 | 33000 | 2026-03-31 | 2026-04-07 | 2026-04-07 | 2026-04-15 | Done Boram
69 | E6400049 | WADUK MANGGAR | XLS | ZBLK_0069 | WADUK MANGGAR | 232011576146 |  | 2025-11-12 | 2025-12-16 | 2025-12-16 |  | SPBR submit to PLN | TSA tidak jadi boram, diminta KTP penanggung jawab dari XL sama PLN. XL tidak mau ngasih
70 | E3100287 | KAMPUNG_SAWAH | XLS | JAW-JK-KYB-0175 | RAYA LENTENG AGUNG RELOC | 547401310502 | 16500 | 2026-03-31 | 2026-04-02 | 2026-04-07 | 2026-04-15 | Done Boram
71 | E6400049 | WADUK MANGGAR | TSEL |  |  | 232011396690 |  | 2025-11-13 |  |  |  | Submit App SPBR | TSA tidak jadi boram, diminta KTP penanggung jawab dari telkomsel sama PLN. Tsel tidak mau ngasih
72 | R1200302 | BANGUN PURBA | XLS | SUM-SU-LBP-0405 | BANGUN PURBA | 126170452098 | 13200 | 2026-05-21 | 2026-05-26 | 2026-05-29 | 2026-06-17 | Done Boram
73 | E1200357 | BENGKONG_HARAPAN | IOH | 07BTM059 | BENGKONGHARAPAN_EP | 151000434988 | 10600 | 2026-03-04 | 2026-03-09 | 2026-03-09 | 2026-05-13 | Done Boram | KWH Stolen Done payment, waiting BA putus langganan
74 | R3350436 | CIMANGGU CILACAP | XLS | JAW-JT-CLP-0423 | CIMANGGU CILACAP | 525020470615
75 | R3350421 | KARANGJUNTI | IOH | 14BRS0006 | KARANGJUNTI_CM | 522550779277 | 7700 | 2026-05-12 | 2026-06-05 | 2026-06-08 | 2026-06-23 | Done Boram
76 | R3350421 | KARANGJUNTI | XLS | JAW-JT-BBS-0007 | KARANGJUNTI | 522550705294 | 16500 | 2026-05-12 | 2026-05-13 | 2026-06-22 | 2026-07-14 | Done Boram | 13.07.26 Plan boram by PLN
77 | E7300112 | BANTAENG | IOH | 29BTN0012 | BANTAENG_EP | 327400105660 | 16500
78 | R3270184 | SETRAINDAH BARAT | IOH | 13BDG0084 | SETRAINDAHBARAT_CM | 535596541629 | 13200 | 2026-07-30 |  |  |  | Submit App SPBR
79 | R3270184 | SETRAINDAH BARAT | XLS | JAW-JB-BDG-0045 | SETRA INDAH BARAT | 535596533200 | 13200 | 2026-07-30 | 2026-08-03 |  |  | SPBR Release
80 | E3500307 | MOROKREMBANGAN | IOH | 20SBY108 | MOROKREMBANGAN_EP | 511040478991 | 13200 | 2026-06-08 | 2026-06-15 | 2026-06-16 | 2016-07-17 | Done Boram
81 | E3500307 | MOROKREMBANGAN | XLS | BJM179 | PERAK BARAT KREMBANGAN BARU | 511040594261 | 23000 | 2026-06-08 | 2026-06-12 | 2026-06-16 | 2016-07-17 | Done Boram
82 | E3500307 | MOROKREMBANGAN | TSEL | SBY374 | MOROKREMBANGAN | 511040545712 | 10600 | 2026-06-08 | 2026-06-12 | 2026-06-16 | 2016-07-17 | Done Boram
83 | E1200337 | BUKIT_BALADA | IOH | 05BTM0018 | BUKIT_BALADA_EP | 152000372414 | 13200
84 | E1200337 | BUKIT_BALADA | TSEL | [9 empty] | need ID Pel PLN (No ID Pel di box KWH)
85 | E1200119 | TELADAN | IOH | 02MDN0444 | TELADAN_MDN_EP | 120030477253
86 | E1200424 | DAPUR_DUA_BELAS / DAPUR 12 | IOH | 05BTM0054 | DAPUR_DUA_BELAS_EP | 152001107489 | 13200 | 2026-06-25 |  |  |  | Submit App SPBR | SPBR NY release
87 | E1200424 | DAPUR_DUA_BELAS / DAPUR 12 | TSEL |  |  | 153000082661 | 10600 | [5 empty] | need confirmation ID Pel PLN
88 | E1200363 | PINTU 4 MUKA KUNING | IOH | 05BTM0207 | PINTU4_MUKA_KUNING_EP | 151000857894 | 16500 | 2026-06-08 |  |  |  | Submit App SPBR | SPBR NY release
89 | R7300149 | KDI AEROPPALA | TSEL | UPD832 |  | 321203251026 | 13200 | 2026-06-05 | 2026-06-05 | 2026-06-12 | 2026-07-31 | Done Boram
90 | E3200034 | CIPANGAUR | IOH | 13CBN0069 | CIPANGAUR_EP | 538530316568 | 16500
91 | E3200269 | CILEUNGSIKIDUL | XLS | NBGR_0125 | CILEUNGSIKIDUL | 538656796899 | 13200 | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-21 | Done Boram
92 | R3350451 | BANYUURIP | IOH | 14PWR0054 | BANYUURIP_CM | 521520857598 | 7700
93 | R3350451 | BANYUURIP | XLS | JAW-JT-PWR-1640 | BANYUURIP PURWOREJO | 521520810681 | 11000
94 | E9400005 | TVRI BIAK | IOH | 33BIA0006 |  | 422100182082 | 10600 | 2026-07-02 |  |  |  | Submit App SPBR | Waiting SPBR release
95 | E3600214 | SUPERMAL | IOH | 11TGN0458 | SUPERMAL_EP | In Building | - |  |  |  | 2026-03-17 | Done Boram | BA Switch Off
96 | E3500375 | MERPATI | All Tenant |  |  |  | 82500 |  |  |  | 2026-03-11 | Done Boram | BA Switch Off
97 | R3100450 | KEBON SIRIH | XLS | ZJKT_4697 | KEBON SIRIH | In Building |  |  |  |  | 2026-01-07 | Done Boram | BA Switch Off
98 | E3500158 | PLANDI | IOH | 16JMB0108 | PLANDI_JMB1_EP | 514530964071 | 16500
99 | E3500158 | PLANDI | TSEL | [9 empty] | need ID Pel PLN (Box KWH digembok)
100 | E3500158 | PLANDI | XLS | JAW-JI-JBG-0619 | NGUDIREJO JOMBANG | [7 empty] | need ID Pel PLN (Box KWH digembok)
101 | E3300153 | GISIKDRONO | IOH | 14SMG0091 | GISIKDRONO_EP | [7 empty] | Site drop need ID Pel PLN (No ID Pel di box KWH)
102 | E3300153 | GISIKDRONO | TSEL | [9 empty] | Site drop need ID Pel PLN (No ID Pel di box KWH)
103 | E3300200 | UNISULA | IOH | 14SMG0336 | UNISULA_EP | [7 empty] | need ID Pel PLN (Sticker PLN sobek)
104 | R3350408 | TINGKIR SALATIGA | XLS | JAW-JT-SLT-2171 | TINGKIR SALATIGA | 523511222790 | 23000
105 | E3500373 | HOTEL CORE SBY | IOH | 16SBY0489 | HOTEL_CORE_EP | 511423501201 | 10600 | 2026-07-17 |  |  |  | Submit App SPBR
106 | E3200384 | KARABA INDAH | SF |  |  | 534756881111 | 6600
107 | E3200384 | KARABA INDAH | XLS | JAW-JB-KWG-2515 | KARYA PUTRA KARAWANG | 534757438011 | 13200
108 | E3200384 | KARABA INDAH | IOH | 13KRW0084 | KARABAINDAH_EP | 534753543847 | 33000
109 | E1200036 | BANDARA BINAKA | IOH | 02GST0004 | VANDRIA_HILIWETO_CM | 127100529332 | 10600 | 2026-07-21 |  |  |  | Submit App SPBR
110 | E3500496 | LAMONGAN | IOH | 16LMG0158 | LAMONGAN_LMG_EP
111 | E3500496 | LAMONGAN | XLS | JAW-JI-LMG-1492 | JETIS LAMONGAN
112 | E3500496 | LAMONGAN | TSEL
113 | R3270681 | JAPARA KUNINGAN | XLS | JAW-JB-KNG-1359 | JAPARA KUNINGAN | 533710321490 | 16500
114 | R6200094 | JUWATA PERMAI | XLS | KAL-KU-TAR-0032 | JUWATA PERMAI | 251000332002 | 13200 | [6 empty] | Status: AKTIF IDPEL: 251000332002 Nama: PT. EXCELCOMINDO PRATAMA Tarif/Daya: B2/13200 Kogol: 0 Unit: ULP TARAKAN, UP3 KALIMANTAN UTARA, UIW KALIMANTAN TIMUR No.Meter: 311916003671 Merk/Type Meter: WASION/IMETER310 No.Gardu: 23520GD010000007553 Nama Gardu: GD HTP0007 No.Tiang: III6.B1 KDDK: FBAAAFF24000 Alamat: JLN. AKI PINGKA/JUATA PERMAI Koordinat: https://www.google.com/maps/search/?api=1&query=3.3645222222,117.5502222222
115
116
117
118
119
120
121
122
123

## CMI-RLC-Nasional
Plan
OG
Pending | [5 empty] | 1 |  | 356 | [24 empty] | 61 | [28 empty] | 152 |  |  |  |  | 291
Prayudi | [21 empty] | Aghnia | [6 empty] | Prayudi | [12 empty] | Prayudi | [14 empty] | Prabowo | [9 empty] | Prayudi | [13 empty] | New Site / FE MW
NO | Vendor Code | Project Code | Scope Of Area | Unique ID | Assignment | Site ID Old | Site ID New | Site Name | Zone | Entity | Provinsi | Kota/Kabupaten | Site Address | LATITUDE | LONGITUDE | Tower Weight - Original (kg) | Tower Height (Eng) (m) | Tenant | Site Type | Tower Type | SOW Detail | PIC | Kontak | SOW Permit | Start | Expired | Validitas Permit | Remark Permit | Survey | Survey Report Submit | End Lease / Drop | RFD Approved | Dismantle Perangkat | Dismantle CME | Inbound | Install | OA/RFS | ATP Approve MS | BAST | Update Progress | Remark Progress | 1st BOQ Submit | 1st BOQ Pass TI | Engineering Structural Manager App | SPH 1 / BAN 1 App | Upload 1st BOQ & BAN Isaac | App 1st BOQ & BAN Isaac | 1st BOQ | 2nd BOQ Submit | 2nd BOQ Pass TI | Engineering Structural Manager App | SPH 2 / BAN 2 App | Upload 2nd BOQ & BAN Isaac | App 2nd BOQ & BAN Isaac | 2nd BOQ | Remark BOQ | HSE Plan & JSA Submit | Isaac HSE Plan & JSA App | JSA Doc No. | SWP Submit | SWP App | SWP Doc No | HSE & JSA | SWP | BA Dism / BA OA / BAST Submit | BA Dism / BA OA / BAST App | SOW | PO Number | PO Release | Aging PO | PO Variation 1 | PO Variation 1 Release | Aging PO Variation 1 | PO Variation 2 | PO Variation 2 Release | Aging PO Variation 2 | Blocking Issue | PIC Responsible | Company | Target Submit Date | Site ID | Site Name | LATITUDE | LONGITUDE | CR IOH | XLWO | CRQ Tsel | Remark Reloc
1 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E3300061 | ID-JT-05773 | RSMARGONO | 11 | EMA | JAWA TENGAH | Kab. Banyumas | KOMPLEK RS. MARGONO JL. JEND. SUDIRMAN PURWOKERTO | -7.43475 | 109.2674 | 13067.712 | 55 | IOH (hwei) | Greenfield | SST 4 Legs | Dismantle Tower | Joko Dedoyo Kecil Liyanto | 87861095209 | Dismantle | 2025-02-25 | 2025-03-04 | Expired |  | 2025-01-24 | 2025-01-29 |  | 2025-02-28 |  | 2025-03-06 |  |  |  |  | 2025-03-11 | BAST |  | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-04-18 | 2025-03-19 | 2025-03-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-01 | 2025-02-07 | JSA No.02/TSA/HSE/02/2025 | 2025-02-01 | 2025-02-07 | SWP-HSE-09 | Approved | Approved | 2025-03-11 | 2025-03-11 | Dismantle Tower | EMAPO25-000807 | 2025-05-14 | 56 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JT-14614 | PAMIJEN SOKARAJA | -7.4353 | 109.2703 | CR-20250226-00000275
2 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E3300061 | ID-JT-05773 | RSMARGONO | 11 | EMA | JAWA TENGAH | Kab. Banyumas | KOMPLEK RS. MARGONO JL. JEND. SUDIRMAN PURWOKERTO | -7.43475 | 109.2674 | 13067.712 | 55 | IOH (hwei) | Greenfield | SST 4 Legs | Dismantle Equipment | Joko Dedoyo Kecil Liyanto | 87861095209 | Dismantle | 2025-02-25 | 2025-03-04 | Expired |  | 2025-01-24 | 2025-01-29 |  |  | 2025-03-01 |  |  |  |  | 2025-03-11 |  | ATP App MS |  | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-04-18 | 2025-03-19 | 2025-03-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-01 | 2025-02-07 | JSA No.02/TSA/HSE/02/2025 | 2025-02-01 | 2025-02-20 |  | Approved | Approved | 2025-03-11 | 2025-05-26 | Dismantle Equipment | EMAPO25-000808 | 2025-05-14 | 56 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JT-14614 | PAMIJEN SOKARAJA | -7.4353 | 109.2703 | CR-20250226-00000275
3 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E3300061 | ID-JT-05773 | RSMARGONO | 11 | EMA | JAWA TENGAH | Kab. Banyumas | KOMPLEK RS. MARGONO JL. JEND. SUDIRMAN PURWOKERTO | -7.43475 | 109.2674 | 13067.712 | 55 | IOH (hwei) | Greenfield | SST 4 Legs | Relocation Equipment | Joko Dedoyo Kecil Liyanto | 87861095209 | Dismantle | 2025-02-25 | 2025-03-04 | Expired |  | 2025-01-24 | 2025-01-29 | [5 empty] | 2025-03-03 | 2025-03-03 | 2025-03-11 |  | ATP App MS |  | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-04-18 | 2025-03-19 | 2025-03-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-01 | 2025-02-07 | JSA No.02/TSA/HSE/02/2025 | 2025-02-01 | 2025-02-20 |  | Approved | Approved | 2025-03-11 | 2025-05-26 | Relocation Equipment | EMAPO25-000809 | 2025-05-14 | 56 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JT-14614 | PAMIJEN SOKARAJA | -7.4353 | 109.2703 | CR-20250226-00000275
4 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E3300061 | ID-JT-05773 | RSMARGONO | 11 | EMA | JAWA TENGAH | Kab. Banyumas | KOMPLEK RS. MARGONO JL. JEND. SUDIRMAN PURWOKERTO | -7.43475 | 109.2674 | 13067.712 | 55 | IOH (hwei) | Greenfield | SST 4 Legs | Rebuild_LOS Survey 14PWT0167_RSMARGONO to 14PWT0200_Purwadadi MT | Joko Dedoyo Kecil Liyanto | 87861095209 | Dismantle | 2025-02-25 | 2025-03-04 | Expired |  | 2025-03-21 | 2025-03-21 | [7 empty] | 2025-03-21 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO25-000367 | 2025-03-10 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | 14PWT0200 | Purwadadi MT | -7.4353 | 109.2703
5 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E3300287 | ID-JT-05997 | SINGOSAREN_NEW | 11 | EMA | JAWA TENGAH | Kota Surakarta | Jl. Gatot Subroto No.27 - 28, Kemlayan, Kec. Serengan, Kota Surakarta | -7.57308 | 110.82058 | 2490.696 | 20 | IOH (hwei) | Rooftop | MT 4 Legs | Dismantle Tower |  |  | Survey | 2025-02-04 | 2025-02-12 | Expired |  | 2025-02-07 | 2025-02-10 |  | 2026-01-12 |  | 2026-02-05 |  |  |  |  | 2026-02-05 | BAST | 03.02.26 Start dismantle | 2025-12-08 | 2026-01-12 | 2025-12-15 |  | 2026-01-12 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-11 | 2025-02-17 | JSA No.10/TSA/HSE/02/2025 | 2025-02-11 | 2025-02-17 | SWP-HSE-16 | Approved | Approved | 2026-02-06 | 2026-02-06 | Dismantle Tower | EMAPO26-000073 | 2026-01-30 | 18 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JT-14679 | KEMLAYAN SURAKARTA | -7.5729 | 110.8208
6 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E3300287 | ID-JT-05997 | SINGOSAREN_NEW | 11 | EMA | JAWA TENGAH | Kota Surakarta | Jl. Gatot Subroto No.27 - 28, Kemlayan, Kec. Serengan, Kota Surakarta | -7.57308 | 110.82058 | 2490.696 | 20 | IOH (hwei) | Rooftop | MT 4 Legs | Dismantle Equipment |  |  | Survey | 2025-02-04 | 2025-02-12 | Expired |  | 2025-02-07 | 2025-02-10 | Drop | [8 empty] | Drop | Dismantle Equipment by MNO | 2025-12-08 | 2026-01-12 | 2025-12-15 |  | 2026-01-12 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-11 | 2025-02-17 | JSA No.10/TSA/HSE/02/2025 | 2025-02-11 | 2025-02-17 |  | Approved | Approved |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Dismantle Equipment by MNO |  |  |  | ID-JT-14679 | KEMLAYAN SURAKARTA | -7.5729 | 110.8208
7 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E3300287 | ID-JT-05997 | SINGOSAREN_NEW | 11 | EMA | JAWA TENGAH | Kota Surakarta |  | -7.57308 | 110.82058 | 2490.696 | 20 | IOH (hwei) | Rooftop | MT 4 Legs | Relocation Equipment |  |  | Survey | 2025-02-04 | 2025-02-12 | Expired |  | 2025-02-07 | 2025-02-10 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-02-11 | 2025-02-17 | JSA No.10/TSA/HSE/02/2025 | 2025-02-11 | 2025-02-17 |  | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Dismantle Equipment by MNO |  |  |  | ID-JT-14679 | KEMLAYAN SURAKARTA | -7.5729 | 110.8208
8 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | R3350400 | ID-JT-02664 | SUMBER LAWANG | 11 | CMI | JAWA TENGAH | Kab. Sragen |  | -7.32809 | 110.86232 | 13212.913 | 70 | XL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-02-04 | 2025-02-12 | Expired |  | 2025-02-07 | 2025-02-10 |  | 2025-05-07 |  | 2025-05-16 |  |  |  |  | 2025-05-16 | BAST |  | 2025-04-28 | 2025-05-19 | 2025-05-19 |  | 2025-05-23 | 2025-05-22 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-11 | 2025-02-13 | JSA No.09/TSA/HSE/02/2025 | 2025-02-11 | 2025-02-13 | SWP-HSE-17 | Approved | Approved | 2025-05-16 | 2025-05-22 | Dismantle Tower | CMIPO25-002455 | 2025-06-26 | 35 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JT-15609 | KEBAYAN SRAGEN | -7.3273 | 110.8625
9 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | R3350400 | ID-JT-02664 | SUMBER LAWANG | 11 | CMI | JAWA TENGAH | Kab. Sragen |  | -7.32809 | 110.86232 | 13212.913 | 70 | XL | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-02-04 | 2025-02-12 | Expired |  | 2025-02-07 | 2025-02-10 |  |  | 2025-05-10 |  |  |  |  | 2025-08-20 | 2025-08-20 | ATP App MS |  | 2025-04-28 | 2025-05-19 | 2025-05-19 |  | 2025-05-23 | 2025-05-22 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-11 | 2025-02-13 | JSA No.09/TSA/HSE/02/2025 | 2025-02-11 | 2025-05-02 |  | Approved | Approved |  |  | Dismantle Equipment | CMIPO25-002456 | 2025-06-26 | 35 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JT-15609 | KEBAYAN SRAGEN | -7.3273 | 110.8625
10 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | R3350400 | ID-JT-02664 | SUMBER LAWANG | 11 | CMI | JAWA TENGAH | Kab. Sragen |  | -7.32809 | 110.86232 | 13212.913 | 70 | XL | Greenfield | SST 4 Legs | Relocation Equipment |  |  | Survey | 2025-02-04 | 2025-02-12 | Expired |  | 2025-02-07 | 2025-02-10 | [5 empty] | 2025-05-15 | 2025-05-15 | 2025-08-20 | 2025-08-20 | ATP App MS |  | 2025-04-28 | 2025-05-19 | 2025-05-19 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-11 | 2025-02-13 | JSA No.09/TSA/HSE/02/2025 | 2025-02-11 | 2025-05-02 |  | Approved | Approved |  |  | Relocation Equipment | CMIPO25-002457 | 2025-06-26 | 35 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JT-15609 | KEBAYAN SRAGEN | -7.3273 | 110.8625
11 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | R3350400 | ID-JT-02664 | SUMBER LAWANG | 11 | CMI | JAWA TENGAH |  |  | -7.32809 | 110.86232 | 13212.913 | 70 | XL | Greenfield | SST 4 Legs | Rebuild_LOS Survey JAW-JT-SGN-1855_LTE_SUMBER_LAWANG to JAW-JT-PWD-1573_SOBO_GEYER |  |  | Survey | 2025-02-04 | 2025-02-12 | Expired |  | 2025-04-16 | 2025-05-08 | [7 empty] | 2025-05-27 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | CMIPO25-002162 | 2025-05-30 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | JAW-JT-PWD-1573 | SOBO_GEYER | -7.3273 | 110.8625
12 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E6400044 | ID-KI-07431 | MARKONI | 18 | EMA | KALIMANTAN TIMUR | Kota Balikpapan | Damai, Kota Balikpapan, Kalimantan Timur | -1.27367 | 116.85109 | 5076.24 | 25 | IOH (nokia) | Rooftop | MT 4 Legs | Dismantle Tower |  |  | Survey | 2025-01-29 | 2025-02-05 | Expired |  | 2025-02-10 | 2025-02-13 |  | 2025-08-08 |  | 2025-09-01 |  |  |  | 2025-09-25 | 2025-09-25 | BAST |  | 2025-09-09 | 2025-08-21 | 2025-08-21 | 2025-09-10 | 2025-09-22 | 2025-09-22 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-13 | 2025-02-17 | JSA No.13/TSA/HSE/02/2025 | 2025-02-13 | 2025-02-17 | SWP-HSE-18 | Approved | Approved | 2025-09-25 | 2025-09-29 | Dismantle Tower | EMAPO25-002009 | 2025-10-08 | 16 |  |  | 0 |  |  |  | Complete |  |  |  | ID-KI-15616 | DAMAI BALIKPAPAN | -1.2708 | 116.8515
13 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E6400044 | ID-KI-07431 | MARKONI | 18 | EMA | KALIMANTAN TIMUR | Kota Balikpapan | Damai, Kota Balikpapan, Kalimantan Timur | -1.27367 | 116.85109 | 5076.24 | 25 | IOH (nokia) | Rooftop | MT 4 Legs | Dismantle Equipment |  |  | Survey | 2025-01-29 | 2025-02-05 | Expired |  | 2025-02-10 | 2025-02-13 |  | 2025-08-08 | 2025-08-11 |  |  |  |  | 2026-02-25 | 2026-02-25 | ATP App MS |  | 2025-09-09 | 2025-08-21 | 2025-08-21 |  | 2025-09-22 | 2025-09-22 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-13 | 2025-02-17 | JSA No.13/TSA/HSE/02/2025 | 2025-02-13 | 2025-02-17 |  | Approved | Approved |  |  | Dismantle Equipment | EMAPO25-002010 | 2025-10-08 | 16 |  |  | 0 |  |  |  | Complete | CMI Project | CMI
14 | CMI | RLC | Nasional | #NAME? | 2025-01-13 | E6400044 | ID-KI-07431 | MARKONI | 18 | EMA | KALIMANTAN TIMUR | Kota Balikpapan | Damai, Kota Balikpapan, Kalimantan Timur | -1.27367 | 116.85109 | 5076.24 | 25 | IOH (nokia) | Rooftop | MT 4 Legs | Relocation Equipment | Abe Rizal |  | Survey | 2025-01-29 | 2025-02-05 | Expired |  | 2025-02-10 | 2025-02-13 |  | 2025-08-08 |  |  |  |  | 2025-11-04 | 2026-02-25 | 2026-02-25 | ATP App MS | 11.11.25 ATP MS done | 2025-09-09 | 2025-08-21 | 2025-08-21 | 2025-09-10 | 2025-09-22 | 2025-09-22 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-13 | 2025-02-17 | JSA No.13/TSA/HSE/02/2025 | 2025-02-13 | 2025-02-17 |  | Approved | Approved |  |  | Relocation Equipment | EMAPO25-002011 | 2025-10-08 | 16 |  |  | 0 |  |  |  | Complete | CMI Project | CMI |  | ID-KI-15616 | DAMAI BALIKPAPAN
15 | CMI | RLC | Nasional | #NAME? | 2025-01-09 | R5100123 | ID-BA-09703 | PALAPA BARAT | 16 | CMI | BALI | Kab. Badung |  | -8.6806 | 115.16718 |  | 12 | IOH | Rooftop | Pole | Dismantle Tower | Hoirul Anam | +62 813-3368-2903 | Urgent Site |  |  | NY Submit |  | 2024-12-29 | 2025-01-23 |  | 2025-01-16 |  | 2025-01-16 |  |  |  |  | 2025-01-17 | BAST |  | 2025-01-20 | 2025-01-20 |  |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit |  | 2025-01-20 | 2025-01-23 | JSA No.04/TSA/HSE/01/2025 | 2025-01-20 | 2025-01-23 | SWP-HSE-01 | Approved | Approved | 2025-01-20 | 2025-02-05 | Dismantle Tower | CMIPO25-000681 | 2025-02-11 | 0 |  |  | 0 |  |  |  | Complete | [8 empty] | XLWO-20250110-0000009
16 | CMI | RLC | Nasional | #NAME? | 2025-01-09 | R5100123 | ID-BA-09703 | PALAPA BARAT | 16 | CMI | BALI | Kab. Badung |  | -8.6806 | 115.16718 |  | 12 | IOH | Rooftop | Pole | Dismantle Equipment |  |  | Urgent Site |  |  | NY Submit |  | 2024-12-29 | 2025-01-23 |  |  | 2025-01-14 |  |  |  |  | 2025-01-17 |  | ATP App MS |  | 2025-01-20 | 2025-01-20 |  |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit |  | 2025-01-20 | 2025-01-23 | JSA No.04/TSA/HSE/01/2025 | 2025-01-20 | 2025-01-10 |  | Approved | Approved | 2025-01-20 | 2025-02-05 | Dismantle Equipment | CMIPO25-000682 | 2025-02-11 | 0 |  |  | 0 |  |  |  | Complete
17 | CMI | RLC | Nasional | #NAME? | 2025-01-09 | R5100123 | ID-BA-09703 | PALAPA BARAT | 16 | CMI | BALI | Kab. Badung |  | -8.6806 | 115.16718 |  | 12 | IOH | Rooftop | Pole | Relocation Equipment | Prayudi |  | Urgent Site |  |  | NY Submit |  | 2024-12-29 | 2025-01-23 | [5 empty] | 2025-01-15 | 2025-01-15 | 2025-01-17 |  | ATP App MS |  | 2025-01-20 | 2025-01-20 |  |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit |  | 2025-01-20 | 2025-01-23 | JSA No.04/TSA/HSE/01/2025 | 2025-01-20 | 2025-01-10 |  | Approved | Approved | 2025-01-20 | 2025-02-05 | Relocation Equipment | CMIPO25-000683 | 2025-02-11 | 0 |  |  | 0 |  |  |  | Complete
18 | CMI | RLC | Nasional | #NAME? | 2025-01-14 | E3300170 | ID-JT-05881 | WATUGONG | 11 | EMA | JAWA TENGAH | Kota Semarang | Banyumanik, Kec. Banyumanik, Kota Semarang, Jawa Tengah | -7.0804 | 110.412 | 1364.403 |  |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-02-13 | 2025-02-20 | Expired |  | 2025-01-15 | 2025-01-29 |  |  |  | 2026-05-15 |  |  |  | 2026-05-15 | 2026-05-15 | BAST | 14.05.26 Start dismantle | 2025-05-09 | 2025-05-19 | 2025-05-11 |  | 2025-11-06 | 2025-11-06 | 1st BOQ App on ISAAC | 2026-05-20 |  |  |  |  | 2026-05-26 | 2nd BOQ App on ISAAC | 06.11.25 BOQ survey app | 2025-02-18 | 2025-02-18 | JSA No.15/TSA/HSE/02/2025 | 2025-02-18 | 2025-02-18 | SWP-HSE-22 | Approved | Approved |  |  | Dismantle Tower | EMAPO25-002203 | 2025-11-13 | 7 | EMAPO26-000856 | 2026-07-03 | 38 |  |  |  | Complete | CMI Project
19 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | R5100015 | ID-BA-00032 | MERCURE KUTA | 16 | CMI | BALI | Kab. Badung | MERCURE HOTEL,JL. PANTAI KUTA BR. PANDA MAS.KUTA,BADUNG,BALI,80361 | -8.72108 | 115.1704 |  | 9 |  | Rooftop | Pole | Dismantle Tower |  |  | Dismantle | 2025-02-12 | 2025-02-19 | Expired |  | 2025-02-03 | 2025-02-19 |  | 2025-03-07 |  | 2025-03-08 |  |  |  |  | 2025-03-08 | BAST |  | 2025-02-03 | 2025-02-03 | 2025-02-03 |  | 2025-03-05 | 2025-03-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-03 | 2025-02-20 | JSA No.04/TSA/HSE/02/2025 | 2025-02-03 | 2025-02-20 | SWP-HSE-11 | Approved | Approved | 2025-03-08 | 2025-03-10 | Dismantle Tower | CMIPO25-001383 | 2025-03-21 | 15 |  |  | 0 |  |  |  | Complete
20 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | R5100017 | ID-BA-00042 | BELO-PETANG | 16 | CMI | BALI | Kab. Badung | HOUSE,JL. RAYA KINTAMANI PLAGA BR. BELO DESA BELO KEC. PETANG KAB. BADUNG.DESA BELO KEC. PETANG,BADUNG,BALI,80353 | -8.27693 | 115.23985 |  | 12 |  | Rooftop | Pole | Dismantle Tower |  |  | Dismantle | 2025-02-05 | 2025-02-12 | Expired |  | 2025-02-03 | 2025-02-19 |  | 2025-03-11 |  | 2025-03-13 |  |  |  |  | 2025-03-14 | BAST |  | 2025-02-03 | 2025-02-03 | 2025-02-03 |  | 2025-03-05 | 2025-03-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-03 | 2025-02-20 | JSA No.05/TSA/HSE/02/2025 | 2025-02-03 | 2025-02-20 | SWP-HSE-12 | Approved | Approved | 2025-03-14 | 2025-03-21 | Dismantle Tower | CMIPO25-001384 | 2025-03-21 | 15 |  |  | 0 |  |  |  | Complete
21 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | R5100005 | ID-BA-00178 | MENGWI / BUDUK | 16 | CMI | BALI | Kab. Badung | BANJAR TENGAH DESA BUDUK KEC. MENGUI BADUNG BALI | -8.606059 | 115.16469 |  | 6 |  | Rooftop | Pole | Dismantle Tower | Utut Wahyu Eka | 8112345378 | Dismantle | 2025-02-05 | 2025-02-12 | Expired |  | 2025-01-29 | 2025-02-01 |  | 2025-02-04 |  | 2025-02-10 |  |  |  |  | 2025-02-19 | BAST |  | 2025-02-03 | 2025-02-03 | 2025-02-03 |  | 2025-02-04 | 2025-02-13 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-01 | 2025-02-03 | JSA No.01/TSA/HSE/02/2025 | 2025-02-01 | 2025-02-03 | SWP-HSE-08 | Approved | Approved | 2025-02-17 | 2025-03-06 | Dismantle Tower | CMIPO25-001181 | 2025-03-14 | 29 |  |  | 0 |  |  |  | Complete
22 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | E1200243 | ID-SB-03997 | RD TO PAINAN/BUKIT LANGKISAU | 3 | EMA | SUMATERA BARAT | Kab. Pesisir Selatan | JL. RAYA PANTAI CAROCOK PAINAN KEC. 4 JURAI | -1.34411 | 100.57142 | 22120.78 | 55 |  | Greenfield | SST 4 Legs | Dismantle Tower | Ismail | 82168704736 | Dismantle | 2025-02-12 | 2025-02-19 | Expired |  | 2025-01-27 | 2025-01-30 |  | 2025-02-11 |  | 2025-02-17 |  |  |  |  | 2025-02-24 | BAST |  | 2025-02-01 | 2025-02-01 | 2025-02-26 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-01-29 | 2025-01-30 | JSA No.01/TSA/HSE/01/2025 | 2025-01-29 | 2025-01-30 | SWP-HSE-04 | Approved | Approved | 2025-02-22 | 2025-02-24 | Dismantle Tower | EMAPO25-000459 | 2025-03-20 | 15 |  |  | 0 |  |  |  | Complete
23 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | E1200260 | ID-SB-04014 | SURIAN | 3 | EMA | SUMATERA BARAT | Kab. Solok | JL. PASAR SURIAN, JORONG PASAR, KEC. PANTAI CERMIN, KAB. SOLOK | -1.25231 | 100.88605 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower | Ismail | 82168704736 | Dismantle | 2025-02-12 | 2025-02-19 | Expired |  | 2025-01-27 | 2025-01-30 |  | 2025-02-08 |  | 2025-02-24 |  |  |  |  | 2025-02-25 | BAST |  | 2025-02-01 | 2025-02-01 | 2025-02-26 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-01-28 | 2025-01-30 | JSA No.03/TSA/HSE/01/2025 | 2025-01-28 | 2025-01-30 | SWP-HSE-03 | Approved | Approved | 2025-02-25 | 2025-02-25 | Dismantle Tower | EMAPO25-000460 | 2025-03-20 | 15 |  |  | 0 |  |  |  | Complete
24 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | E7400037 | ID-SG-07845 | V_TOMIA | 19 | EMA | SULAWESI TENGGARA | Kab. Wakatobi | LINGKUNGAN UNTU KEL. WAHA KEC. TOMIA KABUPATEN WAKATOBI, SULAWESI TENGGARA | -5.7283 | 123.89737 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower | Saiful S | 82195397250 | Dismantle | 2025-02-12 | 2025-02-19 | Expired |  | 2025-01-30 | 2025-01-30 |  | 2025-02-11 |  | 2025-03-26 |  |  |  |  | 2025-03-26 | BAST |  | 2025-02-01 | 2025-02-01 | 2025-02-26 | 2025-02-26 | 2025-02-19 | 2025-02-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-01-30 | 2025-01-30 | JSA No.06/TSA/HSE/01/2025 | 2025-01-30 | 2025-01-30 | SWP-HSE-06 | Approved | Approved | 2025-04-14 | 2025-04-14 | Dismantle Tower | EMAPO25-000463 | 2025-03-20 | 29 |  |  | 0 |  |  |  | Complete
25 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | E7300173 | ID-SN-07804 | BIKERU | 19 | EMA | SULAWESI SELATAN | Kab. Sinjai | JL. PERSATUAN RAYA, KEL. SANGIASERI, KEC. SINJAI SELATAN | -5.2588 | 120.1596 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower | Saiful S | 82195397250 | Dismantle | 2025-02-12 | 2025-02-19 | Expired |  | 2025-01-26 | 2025-01-30 |  | 2025-02-11 |  | 2025-02-28 |  |  |  |  | 2025-03-11 | BAST |  | 2025-02-01 | 2025-02-01 | 2025-02-26 | 2025-02-26 | 2025-03-05 | 2025-03-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-01-29 | 2025-01-30 | JSA No.05/TSA/HSE/01/2025 | 2025-01-29 | 2025-01-30 | SWP-HSE-05 | Approved | Approved | 2025-03-11 | 2025-03-11 | Dismantle Tower | EMAPO25-000462 | 2025-03-20 | 15 |  |  | 0 |  |  |  | Complete
26 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | E7200035 | ID-ST-07619 | V_WAKAI | 19 | EMA | SULAWESI TENGAH | Kab. Tojo Una Una | DS. WAKAI KEC. UNA-UNA, KAB. TOJO UNA-UNA, SULAWESI TENGAH | -0.41265 | 121.859 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower | Saiful S | 82195397250 | Dismantle | 2025-02-12 | 2025-02-19 | Expired |  | 2025-01-30 | 2025-01-30 |  | 2025-02-11 |  | 2025-03-03 |  |  |  |  | 2025-03-03 | BAST |  | 2025-02-01 | 2025-02-01 | 2025-02-26 | 2025-02-26 | 2025-02-10 | 2025-02-10 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-01-30 | 2025-01-30 | JSA No.07/TSA/HSE/01/2025 | 2025-01-30 | 2025-01-30 | SWP-HSE-07 | Approved | Approved | 2025-03-03 | 2025-03-03 | Dismantle Tower | EMAPO25-000461 | 2025-03-20 | 38 |  |  | 0 |  |  |  | Complete
27 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | R5100027 | ID-BA-00065 | SULI | 16 | CMI | BALI | Kota Denpasar | JL. SULI NO.91 BANJAR KERTHA BHUWANA KAJA KEL. DANGRI KANGIN KEC. DENPASAR UTARA - BALI | -8.64226 | 115.22391 |  | 9 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-02-12 | 2025-02-19 | Expired |  | 2025-01-31 | 2025-02-03 |  | 2025-09-15 |  | 2025-09-22 |  |  |  | 2025-11-04 | 2025-11-04 | BAST |  | 2025-02-03 | 2025-02-03 | 2025-02-03 |  | 2025-02-04 | 2025-02-11 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-03 | 2025-02-03 | JSA No.03/TSA/HSE/02/2025 | 2025-02-03 | 2025-02-03 | SWP-HSE-10 | Approved | Approved | 2025-11-05 | 2025-11-05 | Dismantle Tower | CMIPO25-001182 | 2025-03-10 | 27 |  |  | 0 |  |  |  | Complete
28 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | E3500317 | ID-JI-06482 | MIC_BUNGURASIH | 15 | EMA | JAWA TIMUR | Kab. Sidoarjo | JL RAYA BUNGURASIH SIDOARJO, AT WALL OF RAMAYAN DEPT.STORE | -7.35169 | 112.72274 | 793 | 6 |  | Rooftop | Pole | Dismantle Tower |  |  | Dismantle | 2025-02-04 | 2025-02-12 | Expired |  | 2025-02-04 | 2025-02-05 |  | 2025-02-11 |  | 2025-02-21 |  |  |  |  | 2025-03-14 | BAST |  | 2025-02-05 | 2025-02-05 | 2025-02-20 |  | 2025-03-05 | 2025-03-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-05 | 2025-02-05 | JSA No.08/TSA/HSE/02/2025 | 2025-02-05 | 2025-02-05 | SWP-HSE-13 | Approved | Approved | 2025-02-24 | 2025-02-24 | Dismantle Tower | EMAPO25-000478 | 2025-03-24 | 18 |  |  | 0 |  |  |  | Complete
29 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | E3300111 | ID-JT-05823 | DCS_ONGKLOK | 11 | EMA | JAWA TENGAH | Kab. Wonosobo | JL. DIENG NO. 60, RT.04/RW.05, KEL. KALIANGET, KEC WONOSOBO KAB. WONOSOBO, JAWA TENGAH | -7.3472 | 109.907 | 1161 | 6 |  | Rooftop | Pole | Dismantle Tower |  |  | Dismantle | 2025-01-29 | 2025-02-05 | Expired |  | 2025-02-04 | 2025-02-05 |  | 2025-02-11 |  | 2025-02-17 |  |  |  |  | 2025-02-19 | BAST |  | 2025-02-24 | 2025-02-24 | 2025-02-24 |  | 2025-03-05 | 2025-03-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-05 | 2025-02-05 | JSA No.07/TSA/HSE/02/2025 | 2025-02-05 | 2025-02-05 | SWP-HSE-14 | Approved | Approved | 2025-02-19 | 2025-02-19 | Dismantle Tower | EMAPO25-000458 | 2025-03-20 | 14 |  |  | 0 |  |  |  | Complete
30 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | E3300302 | ID-JT-06012 | BHSPALUR | 11 | EMA | JAWA TENGAH | Kab. Karanganyar | DESA NGRINGO, KEC. JATEN, KAB. KARANGANYAR, JAWA TENGAH | -7.567 | 110.8678 | 3968.058 | 34.7 |  | Rooftop | MT 4 Legs | Dismantle Tower |  |  | Survey | 2025-02-25 | 2025-03-04 | Expired |  | 2025-02-11 | 2025-02-13 |  | 2025-04-15 |  | 2025-04-24 |  |  |  |  | 2025-04-25 | BAST |  | 2025-02-24 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 2025-03-20 | 2025-03-20 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-13 | 2025-02-17 | JSA No.12/TSA/HSE/02/2025 | 2025-02-13 | 2025-02-17 | SWP-HSE-20 | Approved | Approved | 2025-04-25 | 2025-04-25 | Dismantle Tower | EMAPO25-000669 | 2025-04-24 | 35 |  |  | 0 |  |  |  | Complete
31 | CMI | RLC | Nasional | #NAME? | 2025-01-24 | E7400027 | ID-SG-07835 | SWISSBELL_KENDARI | 19 | EMA | SULAWESI TENGGARA | Kota Kendari | JL__EDI_SABARA_NO_88_BYPASS_93122 | -3.968 | 122.5319 | 1861.482 | 5.5 |  | Rooftop | Pole & Guyed Mast | Dismantle Tower |  |  | Survey |  |  | NY Submit |  | 2025-02-04 | 2025-02-05 |  | 2025-06-21 |  | 2025-07-28 |  |  |  | 2025-07-29 | 2025-07-30 | BAST |  | 2025-02-24 | 2025-02-24 | 2025-03-04 | 2025-03-04 | 2025-02-05 | 2025-02-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-05 | 2025-02-05 | JSA No.06/TSA/HSE/02/2025 | 2025-02-05 | 2025-02-05 | SWP-HSE-15 | Approved | Approved | 2025-07-30 |  | Dismantle Tower | EMAPO25-000479 | 2025-03-24 | 47 |  |  | 0 |  |  |  | Complete
32 | CMI | RLC | Nasional | #NAME? | 2025-02-06 | E8200008 | ID-MU-07908 | JAILOLO | 20 | EMA | MALUKU UTARA | Kab. Halmahera Barat | DESA GUEAMADU, KEC. JAILOLO, KAB. HALMAHERA BARAT | 1.06113 | 127.46551 | 18868.812 | 72 | IOH (hwei) | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-02-06 | 2025-02-13 | Expired |  | 2025-02-07 | 2025-03-21 |  | 2025-08-08 |  | 2025-12-26 |  |  |  |  | 2025-12-30 | BAST |  | 2025-09-15 | 2025-12-09 | 2025-09-16 | 2025-12-09 | 2025-12-11 | 2025-12-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | TSA ada hutang 1 cabinet untuk digunakan di site lain | 2025-02-13 | 2025-04-07 | JSA No.11/TSA/HSE/02/2025 | 2025-02-13 | 2025-04-26 | SWP-HSE-19 | Approved | Approved | 2025-12-30 | 2025-12-31 | Dismantle Tower | EMAPO25-002375 | 2025-12-30 | 18 |  |  | 0 |  |  |  | Complete |  |  |  | ID-MU-14641 | GUAEMAADU JAILOLO | 1.0616 | 127.4636
33 | CMI | RLC | Nasional | #NAME? | 2025-02-06 | E8200008 | ID-MU-07908 | JAILOLO | 20 | EMA | MALUKU UTARA | Kab. Halmahera Barat | DESA GUEAMADU, KEC. JAILOLO, KAB. HALMAHERA BARAT | 1.06113 | 127.46551 | 18868.812 | 72 | IOH (hwei) | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-02-06 | 2025-02-13 | Expired |  | 2025-02-07 | 2025-03-21 |  |  | 2025-12-18 |  |  |  |  | 2026-01-13 |  | ATP App MS | 01.12.25 Start dism equipment | 2025-09-15 | 2025-12-09 |  | 2025-12-09 | 2025-12-11 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | TSA ada hutang 1 cabinet untuk digunakan di site lain | 2025-02-13 | 2025-04-07 | JSA No.11/TSA/HSE/02/2025 | 2025-02-13 | 2025-04-26 |  | Approved | Approved | 2026-02-26 | 2026-02-26 | Dismantle Equipment | Include Reloc | 2025-12-30 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | ID-MU-14641 | GUAEMAADU JAILOLO | 1.0616 | 127.4636
34 | CMI | RLC | Nasional | #NAME? | 2025-02-06 | E8200008 | ID-MU-07908 | JAILOLO | 20 | EMA | MALUKU UTARA | Kab. Halmahera Barat | DESA GUEAMADU, KEC. JAILOLO, KAB. HALMAHERA BARAT | 1.06113 | 127.46551 | 18868.812 | 72 | IOH (hwei) | Greenfield | SST 4 Legs | Relocation Equipment |  |  | Survey | 2025-02-06 | 2025-02-13 | Expired |  | 2025-02-07 | 2025-03-21 | [5 empty] | 2025-12-21 | 2026-01-13 | 2026-01-13 |  | ATP App MS | 21.12.25 partial OA | 2025-09-15 | 2025-12-09 |  | 2025-12-09 | 2025-12-11 |  | Upload 1st BOQ & BAN Isaac | 2025-12-30 |  |  | 2026-02-02 |  | 2026-02-02 | 2nd BOQ App on ISAAC |  | 2025-02-13 | 2025-04-07 | JSA No.11/TSA/HSE/02/2025 | 2025-02-13 | 2025-04-26 |  | Approved | Approved | 2026-02-26 | 2026-02-26 | Relocation Equipment | EMAPO25-002378 | 2026-02-10 | 0 | EMAPO26-000137 | 2026-02-10 | 8 |  |  |  | Complete |  |  |  | ID-MU-14641 | GUAEMAADU JAILOLO | 1.0616 | 127.4636
35 | CMI | RLC | Nasional | #NAME? | 2025-02-11 | R5300046 | ID-NT-08458 | N3T POMA | 16 | CMI | NUSA TENGGARA TIMUR | Kab. Sikka | RATEGILI, RT 001/ RW 007 DUSUN RATEGILI , DESA POMA KECAMATAN TANA WAWO KAB SIKKA | -8,663972222 | 121,99636 | 9023.12 | 52 | XL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Dismantle | 2025-02-12 | 2025-02-19 | Expired |  | 2025-02-14 | 2025-02-17 |  | 2025-03-11 |  | 2025-03-11 |  |  |  |  | 2025-04-24 | BAST |  | 2025-02-27 | 2025-04-24 | 2025-04-24 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-16 | 2025-02-17 | JSA No.14/TSA/HSE/02/2025 | 2025-02-16 | 2025-02-17 | SWP-HSE-21 | Approved | Approved | 2025-04-24 | 2025-05-06 | Dismantle Tower | CMIPO25-003409 | 2025-07-31 | 44 |  |  | 0 |  |  |  | Complete
36 | CMI | RLC | Nasional | #NAME? | 2025-02-11 | R5300046 | ID-NT-08458 | N3T POMA | 16 | CMI | NUSA TENGGARA TIMUR | Kab. Sikka | RATEGILI, RT 001/ RW 007 DUSUN RATEGILI , DESA POMA KECAMATAN TANA WAWO KAB SIKKA | -8,663972222 | 121,99636 | 9023.12 | 52 | XL | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Dismantle | 2025-02-12 | 2025-02-19 | Expired |  | 2025-02-14 | 2025-02-17 |  |  | 2025-02-23 |  |  |  |  | 2025-04-24 |  | ATP App MS |  | 2025-02-27 | 2025-04-24 | 2025-04-24 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-16 | 2025-02-17 | JSA No.14/TSA/HSE/02/2025 | 2025-02-16 | No Need (site down) |  | Approved | Approved |  |  | Dismantle Equipment | CMIPO25-003410 | 2025-07-31 | 44 |  |  | 0 |  |  |  | Complete
37 | CMI | RLC | Nasional | #NAME? | 2025-02-11 | R5300046 | ID-NT-08458 | N3T POMA | 16 | CMI | NUSA TENGGARA TIMUR | Kab. Sikka | RATEGILI, RT 001/ RW 007 DUSUN RATEGILI , DESA POMA KECAMATAN TANA WAWO KAB SIKKA | -8,663972222 | 121,99636 | 9023.12 | 52 | XL | Greenfield | SST 4 Legs | Relocation Equipment |  |  | Dismantle | 2025-02-12 | 2025-02-19 | Expired |  | 2025-02-14 | 2025-02-17 | [5 empty] | 2025-09-07 |  | 2025-04-24 |  | ATP App MS |  | 2025-02-27 | 2025-04-24 | 2025-04-24 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-16 | 2025-02-17 | JSA No.14/TSA/HSE/02/2025 | 2025-02-16 | No Need (site down) |  | Approved | Approved |  |  | Relocation Equipment | CMIPO25-003411 | 2025-07-31 | 44 |  |  | 0 |  |  |  | Complete
38 | CMI | RLC | Nasional | #NAME? | 2025-02-17 | E3500541 | ID-JI-06705 | GANDUSARI | 15 | EMA | JAWA TIMUR | Kab. Trenggalek | Jl. Gandusari - Kampak | -8.12748 | 111.71111 | 22120 | 70 | IOH | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey |  |  | NY Submit |  | 2025-02-19 | 2025-02-20 | Drop | [8 empty] | Drop | Survey Only | 2025-08-19 | 2025-10-30 |  |  |  | 2025-10-30 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-02-20 | 2025-02-24 | JSA No.16/TSA/HSE/02/2025 | 2025-02-20 | 2025-02-24 | SWP-HSE-23 | Approved | Approved |  |  | Dismantle Tower | EMAPO25-002238 | 2025-11-21 | Drop |  |  | Drop |  |  |  | Complete |  |  |  | ID-JI-16221 | DURENAN TRENGGALEK | -8.1119 | 111.8047
39 | CMI | RLC | Nasional | #NAME? | 2025-02-17 | E3500541 | ID-JI-06705 | GANDUSARI | 15 | EMA | JAWA TIMUR | Kab. Trenggalek | Jl. Gandusari - Kampak | -8.12748 | 111.71111 | 22120 | 70 | IOH | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey |  |  | NY Submit |  | 2025-02-19 | 2025-02-20 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-02-20 | 2025-02-24 | JSA No.16/TSA/HSE/02/2025 | 2025-02-20 | 2025-02-24 |  | Approved | Approved |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop | Drop | Drop |  | ID-JI-16221 | DURENAN TRENGGALEK | -8.1119 | 111.8047
40 | CMI | RLC | Nasional | #NAME? | 2025-02-17 | E3500541 | ID-JI-06705 | GANDUSARI | 15 | EMA | JAWA TIMUR | Kab. Trenggalek | Jl. Gandusari - Kampak | -8.12748 | 111.71111 | 22120 | 70 | IOH | Greenfield | SST 4 Legs | Relocation Equipment |  |  | Survey |  |  | NY Submit |  | 2025-02-19 | 2025-02-20 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-02-20 | 2025-02-24 | JSA No.16/TSA/HSE/02/2025 | 2025-02-20 | 2025-02-24 |  | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop | Drop | Drop |  | ID-JI-16221 | DURENAN TRENGGALEK | -8.1119 | 111.8047
41 | CMI | RLC | Nasional | #NAME? | 2025-02-25 | E1200267 | ID-RI-04021 | AMIK_DURI | 2 | EMA | RIAU | Kab. Bengkalis | JL. KAYANGAN RT 01 RW 07 KEL. BABUSSALAM MANDAU RIAU | 1.27403 | 101.17672 | 646.226 | 5 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-02-25 | 2025-03-04 | Expired |  | 2025-03-03 | 2025-02-04 |  | 2025-03-11 |  | 2025-03-22 |  |  |  |  | 2025-03-22 | BAST |  | 2025-03-19 | 2025-03-19 | 2025-03-19 |  | 2025-03-25 | 2025-03-25 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-03-04 | 2025-03-12 | JSA No.02/TSA/HSE/03/2025 | 2025-03-04 | 2025-02-12 | SWP-HSE-25 | Approved | Approved | 2025-03-25 | 2025-03-25 | Dismantle Tower | EMAPO25-000667 | 2025-04-24 | 30 |  |  | 0 |  |  |  | Complete
42 | CMI | RLC | Nasional | #NAME? | 2025-02-25 | E1200268 | ID-RI-04022 | SUDIRMAN_DURI / SUDIRMAN DURI-4 | 2 | EMA | RIAU | Kab. Bengkalis | JL. JEND. SUDIRMAN NO. 9 KEL. BABUSSALAM KEL. MANDAU KAB. BENGKALIS- RIAU | 1.280917 | 101.195194 | 4930.116 | 25 |  | Rooftop | MT 4 Legs | Dismantle Tower |  |  | Survey | 2025-02-25 | 2025-03-04 | Expired |  | 2025-03-01 | 2025-04-07 |  | 2025-04-22 |  | 2025-05-02 |  |  |  |  | 2025-05-20 | BAST |  | 2025-04-21 | 2025-05-16 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-16 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-11 | 2025-04-11 | JSA No.03/TSA/HSE/04/2025 | 2025-04-11 | 2025-04-16 | SWP-HSE-29 | Approved | Approved |  | 2025-05-20 | Dismantle Tower | EMAPO25-000993 | 2025-06-05 | 20 |  |  | 0 |  |  |  | Complete
43 | CMI | RLC | Nasional | #NAME? | 2025-02-25 | E1200270 | ID-RI-04023 | HOTEL_FAJAR | 2 | EMA | RIAU | Kab. Bengkalis | JALAN JEND. SUDIRMAN DESA GAJAH SAKTI KECAMATAN MANDAU KABUPATEN BENGKALIS PROVINSI RIAU | 1.27047 | 101.20196 | 1577.217 | 12 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-02-25 | 2025-03-04 | Expired |  | 2025-03-03 | 2025-02-04 |  | 2025-04-15 |  | 2025-04-24 |  |  |  |  | 2025-04-25 | BAST |  | 2025-03-19 | 2025-03-19 | 2025-03-19 |  | 2025-03-25 | 2025-03-25 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-03-06 | 2025-03-25 | JSA No.03/TSA/HSE/03/2025 | 2025-03-06 | 2025-03-20 | SWP-HSE-26 | Approved | Approved | 2025-04-25 | 2025-04-28 | Dismantle Tower | EMAPO25-000668 | 2025-04-24 | 30 |  |  | 0 |  |  |  | Complete
44 | CMI | RLC | Nasional | #NAME? | 2025-02-25 | E1200417 | ID-KR-04167 | V_SERASAN / SERASAN | 2 | EMA | KEPULAUAN RIAU | Natuna | JL.DATUK BONE KEC.SARASAN, KAB.NATUNA | 2.50902 | 109.02495 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-02-25 | 2025-03-04 | Expired |  | 2025-03-03 | 2025-03-03 |  | 2025-04-15 |  | 2025-04-28 |  |  |  |  | 2025-04-29 | BAST |  | 2025-04-10 | 2025-04-10 | 2025-04-18 | 2025-04-18 | 2025-04-22 | 2025-04-22 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-03-04 | 2025-03-04 | JSA No.01/TSA/HSE/03/2025 | 2025-03-04 | 2025-03-04 | SWP-HSE-24 | Approved | Approved | 2025-04-29 | 2025-04-29 | Dismantle Tower | EMAPO25-000796 | 2025-05-14 | 22 |  |  | 0 |  |  |  | Complete
45 | CMI | RLC | Nasional | #NAME? | 2025-02-28 | R5100120 | ID-BA-09700 | PANTAI PANDAWA | 16 | CMI | BALI | Kab. Badung | JL. KARANG PUTIH, BANJAR DESA KUTUH, KEC KUTA SELATAN, KAB BADUNG | -8.84399 | 115.18181 |  | 9 | IOH | Rooftop | Pole | Dismantle Tower |  |  | Survey |  |  | NY Submit |  | 2025-03-02 | 2025-01-20 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-03-06 | 2025-03-12 | JSA No.04/TSA/HSE/03/2025 | 2025-03-06 | 2025-03-12 | SWP-HSE-27 | Approved | Approved |  |  | Dismantle Tower | Drop |  | Drop |  |  | Drop |  |  |  | Drop | Drop | Drop | N/A | ID-BA-15316 | PANDAWA KUTA | -8.8448 | 115.1854
46 | CMI | RLC | Nasional | #NAME? | 2025-02-28 | R5100120 | ID-BA-09700 | PANTAI PANDAWA | 16 | CMI | BALI | Kab. Badung | JL. KARANG PUTIH, BANJAR DESA KUTUH, KEC KUTA SELATAN, KAB BADUNG | -8.84399 | 115.18181 |  | 9 | IOH | Rooftop | Pole | Dismantle Equipment |  |  | Survey | 2025-05-22 | 2025-08-20 | Expired |  | 2025-03-02 | 2025-01-20 |  |  | 2025-05-26 |  |  |  |  | 2025-05-26 |  | ATP App MS |  | 2025-03-06 | 2025-03-06 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-17 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-03-06 | 2025-03-12 | JSA No.04/TSA/HSE/03/2025 | 2025-04-30 | 2025-04-30 |  | Approved | Approved |  |  | Dismantle Equipment | CMIPO25-001886 | 2025-05-14 | 58 |  |  | 0 |  |  |  | Complete |  |  |  | ID-BA-15316 | PANDAWA KUTA | -8.8448 | 115.1854 | CR-20250521-00000262
47 | CMI | RLC | Nasional | #NAME? | 2025-02-28 | R5100120 | ID-BA-09700 | PANTAI PANDAWA | 16 | CMI | BALI | Kab. Badung | JL. KARANG PUTIH, BANJAR DESA KUTUH, KEC KUTA SELATAN, KAB BADUNG | -8.84399 | 115.18181 |  | 9 | IOH | Rooftop | Pole | Relocation Equipment | Prayudi |  | Survey | 2025-05-22 | 2025-08-20 | Expired |  | 2025-03-02 | 2025-01-20 | [5 empty] | 2025-05-26 | 2025-05-26 | 2025-05-26 |  | ATP App MS |  | 2025-03-06 | 2025-03-06 | 2025-03-12 | 2025-03-12 | 2025-03-17 | 2025-03-17 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-03-06 | 2025-03-12 | JSA No.04/TSA/HSE/03/2025 | 2025-04-30 | 2025-04-30 |  | Approved | Approved |  |  | Relocation Equipment | CMIPO25-001934 | 2025-05-26 | 70 |  |  | 0 |  |  |  | Complete |  |  |  | ID-BA-15316 | PANDAWA KUTA | -8.8448 | 115.1854 | CR-20250522-00000228
48 | CMI | RLC | Nasional | #NAME? | 2025-02-28 | R5100120 | ID-BA-09700 | PANTAI PANDAWA | 16 | CMI | BALI | Kab. Badung | JL. KARANG PUTIH, BANJAR DESA KUTUH, KEC KUTA SELATAN, KAB BADUNG | -8.84399 | 115.18181 |  | 9 | IOH | Rooftop | Pole | Rebuild_LOS Survey 17DPR0188_PANTAIPANDAWA_CM to 17DPR0395_MB_PANTAI_PANDAWA |  |  | Survey | 2025-05-22 | 2025-08-20 | Expired |  | 2025-03-26 | 2025-03-27 | [7 empty] | 2025-03-27 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | CMIPO25-001207 | 2025-03-17 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | 17DPR0395 | MB_PANTAI_PANDAWA
49 | CMI | RLC | Nasional | #NAME? | 2025-02-28 | R3580411 | ID-JI-02869 | PEGANTENAN | 13 | CMI | JAWA TIMUR | Kab. Pamekasan | DUSUN DAJAH DS PEGANTENAN , KB PAMEKASAN - JAWA TIMUR | -7.04081 | 113.4853 | 13143 |  |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-03-17 | 2025-03-24 | Expired |  | 2025-03-17 | 2025-03-21 |  | 2025-12-03 | [5 empty] | 2025-12-29 | 2025-12-29 | BAST | 04.12.25 Start dismantle tower | 2025-04-30 | 2025-05-21 | 2025-05-20 | 2026-04-06 | 2025-05-21 | 2025-05-21 | 1st BOQ App on ISAAC | 2026-04-01 |  |  | 2026-04-07 |  | 2026-04-29 | 2nd BOQ App on ISAAC |  | 2025-04-11 | 2025-04-12 | JSA No.01/TSA/HSE/04/2025 | 2025-04-11 | 2025-04-12 | SWP-HSE-30 | Approved | Approved | 2025-12-29 | 2025-12-29 | Dismantle Tower | CMIPO25-002379 | 2025-06-19 | 29 | CMIPO26-001700 | 2026-05-19 | 20 |  |  |  | Complete |  |  |  | E3500442 | PENGANTENAN | -7.0447 | 113.4842
50 | CMI | RLC | Nasional | #NAME? | 2025-02-28 | R3580411 | ID-JI-02869 | PEGANTENAN | 13 | CMI | JAWA TIMUR | Kab. Pamekasan | DUSUN DAJAH DS PEGANTENAN , KB PAMEKASAN - JAWA TIMUR | -7.04081 | 113.4853 | 13143 |  |  | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-03-17 | 2025-03-24 | Expired |  | 2025-03-17 | 2025-03-21 |  |  | 2025-12-02 |  | 2026-01-14 |  |  | 2025-05-12 |  | ATP App MS | 08.01.26 SF done inbound 14.01.26 XL done inbound | 2025-04-30 | 2025-05-21 | 2025-05-20 |  | 2025-05-21 | 2025-05-21 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-11 | 2025-04-12 | JSA No.01/TSA/HSE/04/2025 | 2025-04-11 | 2025-04-12 |  | Approved | Approved | 2026-02-25 | 2026-02-25 | Dismantle Equipment | CMIPO25-002380 | 2025-06-19 | 29 |  |  | 0 |  |  |  | Complete |  |  |  | E3500442 | PENGANTENAN | -7.0447 | 113.4842
51 | CMI | RLC | Nasional | #NAME? | 2025-02-28 | R3580411 | ID-JI-02869 | PEGANTENAN | 13 | CMI | JAWA TIMUR | Kab. Pamekasan | DUSUN DAJAH DS PEGANTENAN , KB PAMEKASAN - JAWA TIMUR | -7.04081 | 113.4853 | 13143 |  |  | Greenfield | SST 4 Legs | Relocation Equipment |  |  | Install/Dismantle | 2025-06-19 | 2025-06-25 | Expired |  | 2025-03-17 | 2025-03-21 | [5 empty] | 2025-04-18 | 2025-04-23 | 2025-05-12 |  | ATP App MS | XL done Install NY OA, SF done OA | 2025-04-30 | 2025-05-21 | 2025-05-20 | 2025-05-20 | 2025-05-21 | 2025-05-21 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-11 | 2025-04-12 | JSA No.01/TSA/HSE/04/2025 | 2025-04-11 | 2025-04-12 |  | Approved | Approved | 2026-02-25 | 2026-02-25 | Relocation Equipment | EMAPO25-001303 | 2025-06-25 | 35 | EMAPO25-001304 | 2025-06-25 | 0 |  |  |  | Complete |  |  |  | E3500442 | PENGANTENAN | -7.0447 | 113.4842
52 | CMI | RLC | Nasional | #NAME? | 2025-02-28 | R3580411 | ID-JI-02869 | PEGANTENAN | 13 | CMI | JAWA TIMUR | Kab. Pamekasan | DUSUN DAJAH DS PEGANTENAN , KB PAMEKASAN - JAWA TIMUR | -7.04081 | 113.4853 | 13143 |  |  | Greenfield | SST 4 Legs | Rebuild_LOS Survey ZSBY_2801_PEGANTENAN to ZSBY_2433_TEBUL TIMUR |  |  | Survey | 2025-03-17 | 2025-03-24 | Expired |  | 2025-03-17 | 2025-03-21 | [7 empty] | 2025-03-21 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO25-000962 | 2025-05-30 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | ZSBY_2433 | TEBUL TIMUR | -7.0447 | 113.4842
53 | CMI | RLC | Nasional | #NAME? | 2025-03-18 | E9400008 | ID-PA-07934 | PLB_TIMIKA | 20 | EMA | PAPUA TENGAH | Kab. Mimika | JL. POROS POMAKO DISTRIK MIMIKA TIMUR KAB. MIMIKA,PAPUA | -4.76712 | 136.77 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey |  |  | NY Submit |  | 2025-03-18 | 2025-03-21 |  | 2025-03-22 |  | 2025-04-19 |  |  |  |  | 2025-04-23 | BAST |  | 2025-03-19 | 2025-04-24 |  | 2025-04-24 | 2025-04-24 | 2025-04-24 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-03-20 | 2025-03-21 | JSA No.05/TSA/HSE/03/2025 | 2025-03-20 | 2025-03-21 | SWP-HSE-28 | Approved | Approved | 2025-04-22 | 2025-05-14 | Dismantle Tower | EMAPO25-000580 | 2025-04-24 | 0 |  |  | 0 |  |  |  | Complete
54 | CMI | RLC | Nasional | #NAME? | 2025-03-19 | E3500148 | ID-JI-06316 | KEDUNGPRING | 15 | EMA | JAWA TIMUR | Kab. Lamongan | DESA TELANAK, KEC. KEDUNGPRING, KAB. LAMONGAN | -7.17095 | 112.198 | 18868.81 | 70 | IOH, XL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-03-19 | 2025-03-26 | Expired |  | 2025-03-22 | 2025-04-16 |  | 2025-08-04 |  | 2025-09-29 |  |  |  |  | 2025-09-29 | BAST |  | 2025-09-22 | 2025-11-18 | 2025-09-27 | 2025-12-09 | 2025-12-09 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | 011/TSA-SPH-CMI/IX/2025 Done Reivisi 1 Desember 25 | 2025-04-22 | 2025-04-22 | JSA No.10/TSA/HSE/04/2025 | 2025-04-22 | 2025-04-22 | SWP-HSE-38 | Approved | Approved | 2025-09-29 | 2025-10-02 | Dismantle Tower | EMAPO25-002371 | 2025-12-30 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JI-15761 | TLANAK KEDUNGPRING | -7.172830 | 112.197350
55 | CMI | RLC | Nasional | #NAME? | 2025-03-19 | E3500148 | ID-JI-06316 | KEDUNGPRING | 15 | EMA | JAWA TIMUR | Kab. Lamongan | DESA TELANAK, KEC. KEDUNGPRING, KAB. LAMONGAN | -7.17095 | 112.198 | 18868.81 | 70 | IOH, XL | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-03-19 | 2025-03-26 | Expired |  | 2025-03-22 | 2025-04-16 |  |  | 2025-09-20 |  |  |  |  | 2025-10-13 |  | ATP App MS |  | 2025-09-22 | 2025-11-18 |  |  | 2025-12-09 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-04-22 | 2025-04-22 | JSA No.10/TSA/HSE/04/2025 | 2025-04-22 | 2025-04-22 |  | Approved | Approved | 2025-09-29 | 2025-10-02 | Dismantle Equipment | Include Reloc | 2025-12-30 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JI-15761 | TLANAK KEDUNGPRING | -7.172830 | 112.197350
56 | CMI | RLC | Nasional | #NAME? | 2025-03-19 | E3500148 | ID-JI-06316 | KEDUNGPRING | 15 | EMA | JAWA TIMUR | Kab. Lamongan | DESA TELANAK, KEC. KEDUNGPRING, KAB. LAMONGAN | -7.17095 | 112.198 | 18868.81 | 70 | IOH, XL | Greenfield | SST 4 Legs | Relocation Equipment | Abe Rizal |  | Survey | 2025-03-19 | 2025-03-26 | Expired |  | 2025-03-22 | 2025-04-16 | [5 empty] | 2025-09-22 | 2025-09-22 | 2025-10-13 |  | ATP App MS |  | 2025-09-22 | 2025-11-18 |  | 2025-12-09 | 2025-12-09 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | 011/TSA-SPH-CMI/IX/2025 Done Reivisi 1 Desember 25 | 2025-04-22 | 2025-04-22 | JSA No.10/TSA/HSE/04/2025 | 2025-04-22 | 2025-04-22 |  | Approved | Approved | 2025-10-13 | 2025-10-13 | Relocation Equipment | EMAPO25-002377 | 2025-12-30 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JI-15761 | TLANAK KEDUNGPRING | -7.172830 | 112.197350 | CR-20250917-00000204 | XLWO-20250915-00000024
57 | CMI | RLC | Nasional | #NAME? | 2025-03-25 | R3400078 | ID-YO-09674 | HOTEL HORISON ULTIMA YOGYAKARTA | 11 | CMI | DI YOGYAKARTA | Kota Yogyakarta | Jl. Gowongan Kidul No.33-49, Sosromenduran, Gedong Tengen, Kota Yogyakarta, Daerah Istimewa Yogyakarta 55271 | -7.78803 | 110.36449 | 654.45 |  | SF | Rooftop | Pole | Dismantle Tower | Rano Aprilian Werdhana | 89677996532 | Survey | 2025-04-08 | 2025-04-14 | Expired |  | 2025-04-09 | 2025-04-15 | Drop | [8 empty] | Drop | Survey Only | 2025-08-19 | [5 empty] | 1st BOQ Submit | [6 empty] | NY Submit |  | 2025-04-15 | 2025-04-15 | JSA No.02/TSA/HSE/04/2025 | 2025-04-15 | 2025-04-15 | SWP-HSE-31 | Approved | Approved |  |  | Dismantle Tower | Include R3400081 |  | Drop |  |  | Drop |  |  |  | PO Release only HORISON ULTIMA RISS HOTEL YOGYAKARTA | Drop | Drop
58 | CMI | RLC | Nasional | #NAME? | 2025-03-25 | R3400078 | ID-YO-09674 | HOTEL HORISON ULTIMA YOGYAKARTA | 11 | CMI | DI YOGYAKARTA | Kota Yogyakarta | Jl. Gowongan Kidul No.33-49, Sosromenduran, Gedong Tengen, Kota Yogyakarta, Daerah Istimewa Yogyakarta 55271 | -7.78803 | 110.36449 | 654.45 |  | SF | Rooftop | Pole | Dismantle Equipment | Rano Aprilian Werdhana | 89677996532 | Survey | 2025-04-08 | 2025-04-14 | Expired |  | 2025-04-09 | 2025-04-15 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-04-15 | 2025-04-15 | JSA No.02/TSA/HSE/04/2025 | 2025-04-15 | 2025-04-15 |  | Approved | Approved |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop | Drop | Drop
59 | CMI | RLC | Nasional | #NAME? | 2025-03-25 | R3400078 | ID-YO-09674 | HOTEL HORISON ULTIMA YOGYAKARTA | 11 | CMI | DI YOGYAKARTA | Kota Yogyakarta | Jl. Gowongan Kidul No.33-49, Sosromenduran, Gedong Tengen, Kota Yogyakarta, Daerah Istimewa Yogyakarta 55271 | -7.78803 | 110.36449 | 654.45 |  | SF | Rooftop | Pole | Relocation Equipment | Rano Aprilian Werdhana | 89677996532 | Survey | 2025-04-08 | 2025-04-14 | Expired |  | 2025-04-09 | 2025-04-15 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-04-15 | 2025-04-15 | JSA No.02/TSA/HSE/04/2025 | 2025-04-15 | 2025-04-15 |  | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop | Drop | Drop
60 | CMI | RLC | Nasional | #NAME? | 2025-03-25 | R3400081 | ID-YO-01773 | HORISON ULTIMA RISS HOTEL YOGYAKARTA | 11 | CMI | DI YOGYAKARTA | Kota Yogyakarta | Jl. Gowongan Kidul No.33-49, Sosromenduran, Gedong Tengen, Kota Yogyakarta, Daerah Istimewa Yogyakarta 55271 | -7.78806 | 110.36456 | 872.6 |  | IOH | Rooftop | Pole | Dismantle Tower | Rano Aprilian Werdhana | 89677996532 | Survey | 2025-04-08 | 2025-04-14 | Expired |  | 2025-04-09 | 2025-04-15 | Drop | [8 empty] | Drop | Survey Only | 2025-08-19 | 2025-10-30 |  |  | 2025-11-06 | 2025-11-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-15 | 2025-04-15 | JSA No.04/TSA/HSE/04/2025 | 2025-04-15 | 2025-04-15 | SWP-HSE-32 | Approved | Approved |  |  | Dismantle Tower | CMIPO25-004937 | 2025-11-13 | Drop |  |  | Drop |  |  |  | Complete
61 | CMI | RLC | Nasional | #NAME? | 2025-03-25 | R3400081 | ID-YO-01773 | HORISON ULTIMA RISS HOTEL YOGYAKARTA | 11 | CMI | DI YOGYAKARTA | Kota Yogyakarta | Jl. Gowongan Kidul No.33-49, Sosromenduran, Gedong Tengen, Kota Yogyakarta, Daerah Istimewa Yogyakarta 55271 | -7.78806 | 110.36456 | 872.6 |  | IOH | Rooftop | Pole | Dismantle Equipment | Rano Aprilian Werdhana | 89677996532 | Survey | 2025-04-08 | 2025-04-14 | Expired |  | 2025-04-09 | 2025-04-15 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-04-15 | 2025-04-15 | JSA No.04/TSA/HSE/04/2025 | 2025-04-15 | 2025-04-15 |  | Approved | Approved |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop | Drop | Drop
62 | CMI | RLC | Nasional | #NAME? | 2025-03-25 | R3400081 | ID-YO-01773 | HORISON ULTIMA RISS HOTEL YOGYAKARTA | 11 | CMI | DI YOGYAKARTA | Kota Yogyakarta | Jl. Gowongan Kidul No.33-49, Sosromenduran, Gedong Tengen, Kota Yogyakarta, Daerah Istimewa Yogyakarta 55271 | -7.78806 | 110.36456 | 872.6 |  | IOH | Rooftop | Pole | Relocation Equipment | Rano Aprilian Werdhana | 89677996532 | Survey | 2025-04-08 | 2025-04-14 | Expired |  | 2025-04-09 | 2025-04-15 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-04-15 | 2025-04-15 | JSA No.04/TSA/HSE/04/2025 | 2025-04-15 | 2025-04-15 |  | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop | Drop | Drop
63 | CMI | RLC | Nasional | #NAME? | 2025-04-11 | R5100250 | ID-BA-10363 | Girisari Road | 16 | CMI | BALI | Kab. Badung | JL. RAYA ULUWATU, GG.GUNUNG BAYUR, BR. KANGIN PECATU. DESA PECATU | -8.83592 | 115.113869 | 608.52 | 12 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-03-12 | 2025-03-18 | Expired |  | 2025-04-15 |  | Drop | [8 empty] | Drop | Survey Only | 2025-08-19 | 2025-10-30 |  |  | 2025-10-30 | 2025-10-30 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-21 | 2025-04-21 | JSA No.09/TSA/HSE/04/2025 | 2025-04-21 | 2025-04-21 | SWP-HSE-36 | Approved | Approved |  |  | Dismantle Tower | CMIPO25-005364 | 2025-12-08 | Drop |  |  | Drop |  |  |  | Complete
64 | CMI | RLC | Nasional | #NAME? | 2025-04-11 | E3500266 | ID-JI-06433 | SAMBIKEREP | 13 | EMA | JAWA TIMUR | Kota Surabaya | JL. TAMAN MAISONETE BLOK I 16-22 CITRALAND KAWASAN G-WALK CITRALAND SURABAYA | -7.2899 | 112.65482 | 700.57 | 9 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-04-11 | 2025-04-18 | Expired |  | 2025-04-12 | 2025-04-21 |  | 2025-04-30 |  | 2025-05-23 |  |  |  |  | 2025-05-23 | BAST |  | 2025-05-02 | 2025-05-02 | 2025-05-02 |  | 2025-05-02 | 2025-05-09 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-21 | 2025-04-21 | JSA No.06/TSA/HSE/04/2025 | 2025-04-21 | 2025-04-21 | SWP-HSE-33 | Approved | Approved | 2025-05-23 | 2025-05-26 | Dismantle Tower | EMAPO25-000914 | 2025-05-22 | 13 |  |  | 0 |  |  |  | Complete
65 | CMI | RLC | Nasional | #NAME? | 2025-04-11 | R3100460 | ID-JK-01737 | RUMAH SAKIT HARAPAN BUNDA | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Timur | JL. RAYA BOGOR KM. 22 NO. 44, PASAR REBO, JAKARTA TIMUR | -6.30309 | 106.86785 | 654.45 | 6 |  | Rooftop | Pole | Dismantle Tower | saprudin | +6285959413356 | Dismantle | 2025-04-12 | 2025-04-19 | Expired |  | 2025-04-14 |  | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  |  |  | JSA No.08/TSA/HSE/04/2025 | 2025-04-21 | 2025-04-21 | SWP-HSE-34 | NY Submit | Approved |  |  | Dismantle Tower | Drop |  | Drop |  |  | Drop |  |  |  | Drop | CMI Project | CMI
66 | CMI | RLC | Nasional | #NAME? | 2025-04-11 | R1800058 | ID-LA-09507 | JL. IR. SUTAMI | 5 | CMI | LAMPUNG | Kab. Tulang Bawang | CENTRAL HOUSING PT. CPB KP. BRATASENA ADIWARNA KEC. DENTE TELADAS | -4.57106 | 105.81801 | 9996 | 52 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-04-11 | 2025-04-18 | Expired |  | 2025-04-14 |  |  | 2025-04-30 |  | 2025-05-11 |  |  |  |  | 2025-05-15 | BAST |  | 2025-04-30 | 2025-05-14 | 2025-05-02 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-21 | 2025-04-21 | JSA No.07/TSA/HSE/04/2025 | 2025-04-21 | 2025-04-21 | SWP-HSE-35 | Approved | Approved | 2025-05-15 | 2025-05-26 | Dismantle Tower | CMIPO25-002057 | 2025-05-21 | 7 |  |  | 0 |  |  |  | Complete
67 | CMI | RLC | Nasional | #NAME? | 2025-04-11 | E1200255 | ID-SB-04009 | SAWAH LUNTO | 3 | EMA | SUMATERA BARAT | Kab. Sawahlunto | PUNCAK BUKIT PARI KEC. BERANGIN | -0.66851 | 100.772 | 13067.712 | 55 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-04-11 | 2025-04-18 | Expired |  | 2025-04-12 | 2025-04-21 |  | 2025-05-05 |  | 2025-05-19 |  |  |  |  | 2025-05-23 | BAST |  | 2025-04-30 | 2025-05-14 | 2025-05-02 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-21 | 2025-04-21 | JSA No.05/TSA/HSE/04/2025 | 2025-04-21 | 2025-04-26 | SWP-HSE-37 | Approved | Approved | 2025-05-23 |  | Dismantle Tower | EMAPO25-001756 | 2025-08-28 | 15 |  |  | 0 |  |  |  | Complete
68 | CMI | RLC | Nasional | #NAME? | 2025-04-15 | R7300272 | ID-SN-08598 | LSP MCP Kayangan Sopeng | 19 | CMI | SULAWESI SELATAN | Kab. Soppeng | JL. KAYANGAN KELURAHAN BOTTO KECAMATAN LALABATA KABUPATEN SOPPENG | -4.35713 | 119.882 |  |  | IOH, Tsel, SF | Greenfield | Monopole | Dismantle Equipment | Aswar | +62 852-4268-5586 | Survey | 2025-04-16 | 2025-04-23 | Expired |  | 2025-04-18 |  |  |  | 2025-06-15 |  |  |  |  | 2025-09-03 |  | ATP App MS |  | 2025-05-16 | 2025-06-09 |  |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | Include Reloc |  | 0 |  |  | 0 |  |  |  | Complete | CMI Project | CMI | [6 empty] | XLWO-20250813-00000104
69 | CMI | RLC | Nasional | #NAME? | 2025-04-15 | R7300272 | ID-SN-08598 | LSP MCP Kayangan Sopeng | 19 | CMI | SULAWESI SELATAN | Kab. Soppeng | JL. KAYANGAN KELURAHAN BOTTO KECAMATAN LALABATA KABUPATEN SOPPENG | -4.35713 | 119.882 |  |  | IOH, Tsel, SF | Greenfield | Monopole | Relocation Equipment | Aswar | +62 852-4268-5586 | Survey | 2025-04-16 | 2025-04-23 | Expired |  | 2025-04-18 | [6 empty] | 2025-08-21 | 2025-09-03 | 2025-09-03 |  | ATP App MS |  | 2025-05-16 | 2025-06-09 |  | 2025-09-30 |  |  | BAN App | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | CMIPO26-000497 | 2026-02-13 | 0 |  |  | 0 |  |  |  | Complete | CMI Project | CMI | [6 empty] | XLWO-20250813-00000104
70 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | R1200056 | ID-SU-00605 | HAMDAN | 1 | CMI | SUMATERA UTARA | Kota Medan | JL. DAZAN RAYA NO. 10, KEL. PETISAH TENGAH, KEC. MEDAN KOTA, KOTA MEDAN, SUMATRA UTARA | 3.58662 | 98.66433 | 3713.64 | 25 |  | Rooftop | MT 4 Legs | Dismantle Tower | Defta Maulana | 085363615979 | Survey | 2025-04-22 | 2025-04-29 | Expired |  | 2025-04-25 | 2025-04-26 |  | 2025-05-08 |  | 2025-05-19 |  |  |  |  | 2025-05-23 | BAST |  | 2025-04-30 | 2025-04-30 | 2025-05-02 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-26 | 2025-04-26 | JSA No.11/TSA/HSE/04/2025 | 2025-04-26 | 2025-04-26 | SWP-HSE-39 | Approved | Approved | 2025-05-23 | 2025-05-23 | Dismantle Tower | CMIPO25-002056 | 2025-05-21 | 7 |  |  | 0 |  |  |  | Complete
71 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | E5100119 | ID-BA-07040 | NUSALEMBONGAN | 16 | EMA | BALI | Kab. Klungkung | DUSUN KANGIN, DESA JUNGUT BATU KEC. NUSA PENIDA, KAB. KLUNGKUNG | -8.6805 | 115.44864 | 22120.78 | 72 |  | Greenfield | SST 4 Legs | Dismantle Tower | Utut Wahyu Eka | 8112345378 | Survey | 2015-04-21 | 2025-04-28 | Expired |  | 2025-05-09 | 2025-05-19 |  | 2025-07-24 |  | 2025-10-05 |  |  |  |  | 2025-10-05 | BAST |  | 2025-09-24 | 2025-10-23 | 2025-09-16 | 2025-11-03 | 2025-11-06 | 2025-11-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-07-09 | 2025-07-23 | JSA No.02/TSA/HSE/05/2025 | 2025-07-09 | 2025-07-16 | SWP-HSE-44 | Approved | Approved | 2025-10-09 | 2025-10-13 | Dismantle Tower | EMAPO25-002241 | 2025-11-21 | #NUM! |  |  | 0 |  |  |  | Complete
72 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | E5100119 | ID-BA-07040 | NUSALEMBONGAN | 16 | EMA | BALI | Kab. Klungkung | DUSUN KANGIN, DESA JUNGUT BATU KEC. NUSA PENIDA, KAB. KLUNGKUNG | -8.6805 | 115.44864 | 22120.78 | 72 |  | Greenfield | SST 4 Legs | Dismantle Equipment | Utut Wahyu Eka | 8112345378 | Survey | 2015-04-21 | 2025-04-28 | Expired |  | 2025-05-09 | 2025-05-19 |  |  | 2025-10-01 |  |  |  |  | 2025-12-03 |  | ATP App MS |  | 2025-09-24 | 2025-10-23 |  | 2025-11-03 | 2025-11-06 | 2025-11-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-07-09 | 2025-07-23 | JSA No.02/TSA/HSE/05/2025 | 2025-07-09 | 2025-07-16 |  | Approved | Approved | 2025-12-03 | 2025-12-03 | Dismantle Equipment | Include Reloc | 2025-11-21 | #NUM! |  |  | 0 |  |  |  | Complete
73 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | E5100119 | ID-BA-07040 | NUSALEMBONGAN | 16 | EMA | BALI | Kab. Klungkung | DUSUN KANGIN, DESA JUNGUT BATU KEC. NUSA PENIDA, KAB. KLUNGKUNG | -8.6805 | 115.44864 | 22120.78 | 72 |  | Greenfield | SST 4 Legs | Relocation Equipment | Prolis Heru |  | Reloc |  |  | NY Submit |  | 2025-05-09 | 2025-05-19 | [5 empty] | 2025-10-02 | 2025-10-02 | 2025-12-03 |  | ATP App MS |  | 2025-09-24 | 2025-10-23 |  | 2025-11-03 | 2025-11-06 | 2025-11-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-07-09 | 2025-07-23 | JSA No.02/TSA/HSE/05/2025 | 2025-07-09 | 2025-07-16 |  | Approved | Approved | 2025-12-03 | 2025-12-03 | Relocation Equipment | EMAPO25-002244 | 2025-11-21 | #NUM! |  |  | 0 |  |  |  | Complete |  |  |  | ID-BA-16156 | NUSAPENIDA KLUNGKUNG
74 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | R3350220 | ID-JT-03515 | RUMAH SAKIT HERMINA SOLO | 11 | CMI | JAWA TENGAH | Kota Surakarta | JL. KOLONEL SUTARTO NO. 16. RW.002, JEBRES, SURAKARTA | -7.56039 | 110.84014 | 8232.14 | 3 | IOH | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-11-04 | 2025-11-17 | Expired |  | 2025-04-22 |  |  | 2025-12-10 |  | 2025-12-31 |  |  |  | 2025-12-31 | 2025-12-31 | BAST |  | 2025-12-04 | 2025-12-05 | 2025-12-04 |  | 2025-12-05 | 2025-12-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  |  |  | JSA No.01/TSA/HSE/11/2025 | 2025-11-17 | 2025-11-17 |  | NY Submit | Approved | 2026-01-05 | 2026-01-08 | Dismantle Tower | CMIPO25-005579 | 2025-12-17 | 12 |  |  | 0 |  |  |  | Complete
75 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | R3350220 | ID-JT-03515 | RUMAH SAKIT HERMINA SOLO | 11 | CMI | JAWA TENGAH | Kota Surakarta | JL. KOLONEL SUTARTO NO. 16. RW.002, JEBRES, SURAKARTA | -7.56039 | 110.84014 | 8232.14 | 3 | IOH | Rooftop | Pole | Dismantle Equipment |  |  | Survey | 2025-11-04 | 2025-11-17 | Expired |  | 2025-04-22 |  | Drop | [8 empty] | Drop |  | 2025-12-04 | 2025-12-05 | 2025-12-04 |  | 2025-12-05 | 2025-12-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  |  |  | JSA No.01/TSA/HSE/11/2025 | 2025-11-17 | 2025-11-17 |  | NY Submit | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2025-12-17 | Drop |  |  | Drop |  |  |  | Drop | CMI Project | CMI
76 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | R3350220 | ID-JT-03515 | RUMAH SAKIT HERMINA SOLO | 11 | CMI | JAWA TENGAH | Kota Surakarta | JL. KOLONEL SUTARTO NO. 16. RW.002, JEBRES, SURAKARTA | -7.56039 | 110.84014 | 8232.14 | 3 | IOH | Rooftop | Pole | Relocation Equipment |  |  | Survey | 2025-11-04 | 2025-11-17 | Expired |  | 2025-04-22 | 2025-11-04 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-11-04 | 2025-11-04 | JSA No.01/TSA/HSE/11/2025 | 2025-11-11 | 2025-11-17 | SWP-HSE-88 | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop | CMI Project | CMI
77 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | R6300019 | ID-KS-00288 | JL. KELAPA BJM | 18 | CMI | KALIMANTAN SELATAN | Kota Banjarmasin | JL. A YANI KM.3,7 NO.2 RT.33, KEL. KEBON BUNGA, KEC. BANJARMASIN TIMUR, KODYA BANJARMASIN, PROP. KALIMANTAN SELATAN | -3.3304 | 114.61279 | 2939.54 | 20 |  | Rooftop | MT 4 Legs | Dismantle Tower | Benny | +6285256666653 | Dismantle | 2026-05-11 | 2026-05-17 | Expired |  | 2025-04-23 | 2025-04-30 | 2026-05-26 | 2026-04-23 |  | 2026-05-21 | [5 empty] | Dismantle | 19.05.26 Start dismantle | 2026-03-31 | 2026-04-02 | 2026-04-03 |  | 2026-04-03 | 2026-04-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-30 | 2025-04-30 | JSA No.12/TSA/HSE/04/2025 | 2025-04-30 | 2025-04-30 | SWP-HSE-40 | Approved | Approved | 2026-06-02 | 2026-06-02 | Dismantle Tower | CMIPO26-001330 | 2026-04-15 | 9 |  |  | 0 |  |  |  | Complete
78 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | R6300019 | ID-KS-00288 | JL. KELAPA BJM | 18 | CMI | KALIMANTAN SELATAN | Kota Banjarmasin | JL. A YANI KM.3,7 NO.2 RT.33, KEL. KEBON BUNGA, KEC. BANJARMASIN TIMUR, KODYA BANJARMASIN, PROP. KALIMANTAN SELATAN | -3.3304 | 114.61279 | 2939.54 | 20 |  | Rooftop | MT 4 Legs | Dismantle Equipment | Benny | +6285256666653 | Survey | 2026-05-11 | 2026-05-17 | Expired |  | 2025-04-23 | 2025-04-30 |  | 2026-04-23 | 2026-05-11 |  | 2026-05-21 |  |  |  |  | Inbound | 11.05.26 start dismantle 13.05.26 MW XL dibawa RTS (need BA) 19.05.26 XLS done inbound 21.05.26 TSEL done inbound | 2026-03-31 | 2026-04-02 | 2026-04-03 |  | 2026-04-03 | 2026-04-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-04-30 | 2025-04-30 | JSA No.12/TSA/HSE/04/2025 | 2025-04-30 | 2025-04-30 |  | Approved | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2026-04-15 | 9 |  |  | 0 |  |  |  | Complete
79 | CMI | RLC | Nasional | #NAME? | 2025-04-21 | R6300019 | ID-KS-00288 | JL. KELAPA BJM | 18 | CMI | KALIMANTAN SELATAN | Kota Banjarmasin | JL. A YANI KM.3,7 NO.2 RT.33, KEL. KEBON BUNGA, KEC. BANJARMASIN TIMUR, KODYA BANJARMASIN, PROP. KALIMANTAN SELATAN | -3.3304 | 114.61279 | 2939.54 | 20 |  | Rooftop | MT 4 Legs | Relocation Equipment | Benny | +6285256666653 | Survey | 2026-05-11 | 2026-05-17 | Expired |  | 2025-04-23 | 2025-04-30 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-04-30 | 2025-04-30 | JSA No.12/TSA/HSE/04/2025 | 2025-04-30 | 2025-04-30 |  | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Dismantle Drop |  | TSA
80 | CMI | RLC | Nasional | #NAME? | 2025-04-30 | R3350113 | ID-JT-00831 | PLIKEN | 11 | CMI | JAWA TENGAH | Kab. Banyumas | PLIKENRT 004 RW002, DS PLIKEN KECAMATAN KEMBARAN KABUPATEN ,BANYUMAS,KABUPATEN BANYUMAS PROPINSI JAWA TENGAH | -7.4325 | 109.28854 | 6912.039 | 42 |  | Greenfield | SST 4 Legs | Dismantle Tower | Kusmana | +62 851-6953-0970 | Survey | 2025-12-06 | 2025-12-13 | Expired |  | 2025-12-18 | 2025-12-18 |  | 2026-01-19 |  | 2026-01-29 |  |  |  | 2026-01-29 | 2026-01-29 | BAST | 27.01.26 Start dism | 2026-01-05 | 2026-01-12 | 2026-01-05 |  | 2026-01-12 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-12-18 | 2025-12-19 | JSA No.06/TSA/HSE/12/2025 | 2025-12-28 | 2025-12-30 | SWP-HSE-97 | Approved | Approved | 2026-02-02 | 2026-02-02 | Dismantle Tower | CMIPO26-000311 | 2026-01-30 | 18 |  |  | 0 |  |  |  | Complete
81 | CMI | RLC | Nasional | #NAME? | 2025-04-30 | R3350113 | ID-JT-00831 | PLIKEN | 11 | CMI | JAWA TENGAH | Kab. Banyumas | PLIKENRT 004 RW002, DS PLIKEN KECAMATAN KEMBARAN KABUPATEN ,BANYUMAS,KABUPATEN BANYUMAS PROPINSI JAWA TENGAH | -7.4325 | 109.28854 | 6912.039 | 42 |  | Greenfield | SST 4 Legs | Dismantle Equipment | Kusmana | +62 851-6953-0970 | Survey | 2025-12-06 | 2025-12-13 | Expired |  | 2025-12-18 | 2025-12-18 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-12-18 | 2025-12-19 | JSA No.06/TSA/HSE/12/2025 | 2025-12-28 | 2025-12-30 |  | Approved | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2026-01-30 | Drop |  |  | Drop |  |  |  | Complete
82 | CMI | RLC | Nasional | #NAME? | 2025-04-30 | R3350113 | ID-JT-00831 | PLIKEN | 11 | CMI | JAWA TENGAH | Kab. Banyumas | PLIKENRT 004 RW002, DS PLIKEN KECAMATAN KEMBARAN KABUPATEN ,BANYUMAS,KABUPATEN BANYUMAS PROPINSI JAWA TENGAH | -7.4325 | 109.28854 | 6912.039 | 42 |  | Greenfield | SST 4 Legs | Relocation Equipment | Kusmana | +62 851-6953-0970 | Survey | 2025-12-06 | 2025-12-13 | Expired |  | 2025-12-18 | 2025-12-18 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-12-18 | 2025-12-19 | JSA No.06/TSA/HSE/12/2025 | 2025-12-28 | 2025-12-30 |  | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop
83 | CMI | RLC | Nasional | #NAME? | 2025-04-30 | E6400129 | ID-KI-07514 | SUSUK | 18 | EMA | KALIMANTAN TIMUR | Kab. Kutai Timur | JL. PERUSAHAAN MP, DESA SUSUK TENGAH, KEC. SANDARAN, KAB. KUTAI TIMUR, KAL-TIM | 0.89267 | 118.2037 | 26723.89 | 70 | IOH | Greenfield | SST 4 Legs | Dismantle Tower | Darman | +62 878-6524-7367 | Survey | 2025-05-05 | 2025-05-12 | Expired |  | 2025-05-08 | 2025-05-08 |  | 2026-01-06 |  | 2026-02-04 |  |  |  |  | 2026-02-05 | BAST | 28.01.26 Start dismantle | 2025-11-26 | 2025-12-10 | 2025-12-10 |  | 2025-12-10 | 2025-12-10 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-18 | 2025-06-24 | JSA No.09/TSA/HSE/06/2025 | 2025-06-26 | 2025-07-11 | SWP-HSE-43 | Approved | Approved | 2026-02-06 | 2026-02-06 | Dismantle Tower | EMAPO25-002343 | 2025-12-22 | 12 |  |  | 0 |  |  |  | Complete
84 | CMI | RLC | Nasional | #NAME? | 2025-04-30 | E6400129 | ID-KI-07514 | SUSUK | 18 | EMA | KALIMANTAN TIMUR | Kab. Kutai Timur | JL. PERUSAHAAN MP, DESA SUSUK TENGAH, KEC. SANDARAN, KAB. KUTAI TIMUR, KAL-TIM | 0.89267 | 118.2037 | 26723.89 | 70 | IOH | Greenfield | SST 4 Legs | Dismantle Equipment | Darman | +62 878-6524-7367 | Survey | 2025-05-05 | 2025-05-12 | Expired |  | 2025-05-08 | 2025-05-08 |  | 2026-01-06 | 2026-01-26 |  |  |  |  | 2026-02-02 |  | ATP App MS | 24.01.26 Start dismantle | 2025-11-26 | 2025-12-10 | 2025-12-10 |  | 2025-12-10 | 2025-12-10 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-18 | 2025-06-24 | JSA No.09/TSA/HSE/06/2025 |  |  |  | Approved | NY Submit |  |  | Dismantle Equipment | Include Reloc | 2025-12-16 | 6 |  |  | 0 |  |  |  | Complete
85 | CMI | RLC | Nasional | #NAME? | 2025-04-30 | E6400129 | ID-KI-07514 | SUSUK | 18 | EMA | KALIMANTAN TIMUR | Kab. Kutai Timur | JL. PERUSAHAAN MP, DESA SUSUK TENGAH, KEC. SANDARAN, KAB. KUTAI TIMUR, KAL-TIM | 0.89267 | 118.2037 | 26723.89 | 70 | IOH | Greenfield | SST 4 Legs | Relocation Equipment | Darman | +62 878-6524-7367 | Survey | 2025-05-05 | 2025-05-12 | Expired |  | 2025-05-08 | 2025-05-08 |  | 2026-01-06 |  |  |  | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | ATP App MS | 27.01.26 Start reinstall | 2025-11-26 | 2025-12-10 | 2025-12-10 |  | 2025-12-10 | 2025-12-10 | 1st BOQ App on ISAAC | 2026-01-13 |  |  | 2026-02-18 |  | 2026-02-19 | 2nd BOQ App on ISAAC |  | 2025-06-18 | 2025-06-24 | JSA No.09/TSA/HSE/06/2025 |  |  |  | Approved | NY Submit |  |  | Relocation Equipment | EMAPO25-002339 | 2025-12-16 | 6 | EMAPO26-000587 | 2025-12-16 | #NUM! |  |  |  | Complete |  |  |  | ID-KI-16319 | SANDARAN KALTIM |  |  | CR-20260122-00000296 CR-20260121-00000397 CR-20260124-00000058 CR-20260126-00000036
86 | CMI | RLC | Nasional | #NAME? | 2025-05-03 | E1200347 | ID-KR-04100 | JODOH | 2 | EMA | KEPULAUAN RIAU | Kota Batam | HOTEL OASIS KOMPLEX ORCHID MAS CENTRE, SEI JODOH, BATU AMPAR | 1.157056 | 104.003753 | 971.83 | 10 | IOH | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-05-04 | 2025-05-11 | Expired |  | 2025-05-07 | 2025-05-14 |  | 2025-08-13 |  | 2025-10-08 |  |  |  | 2025-11-05 | 2025-11-05 | BAST |  | 2025-12-12 | 2025-12-15 | 2025-12-12 | 2025-01-06 | 2026-01-07 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-18 | 2025-06-24 | JSA No.6/TSA/HSE/06/2025 | 2025-06-19 | 2025-06-19 | SWP-HSE-45 | Approved | Approved | 2025-11-05 | 2025-11-10 | Dismantle Tower | EMAPO26-000043 | 2026-01-13 | 1 |  |  | 0 |  |  |  | Complete |  |  |  | 05BTM0110 | JODOH_EP | 1.16611 | 104.04257
87 | CMI | RLC | Nasional | #NAME? | 2025-05-03 | E1200347 | ID-KR-04100 | JODOH | 2 | EMA | KEPULAUAN RIAU | Kota Batam | HOTEL OASIS KOMPLEX ORCHID MAS CENTRE, SEI JODOH, BATU AMPAR | 1.157056 | 104.003753 | 971.83 | 10 | IOH | Rooftop | Pole | Dismantle Equipment |  |  | Survey | 2025-05-04 | 2025-05-11 | Expired |  | 2025-05-07 | 2025-05-14 |  |  | 2025-10-08 |  |  |  |  | 2026-01-09 | 2026-01-09 | ATP App MS |  | 2025-12-12 | 2025-12-15 | 2025-12-12 | 2025-01-06 | 2026-01-07 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-18 | 2025-06-24 | JSA No.6/TSA/HSE/06/2025 |  |  |  | Approved | NY Submit | 2026-03-03 | 2026-03-03 | Dismantle Equipment | Include Reloc | 2026-01-30 | 18 |  |  | 0 |  |  |  | Complete |  |  |  | ID-KR-14656 | SUNGAI JODOH | 1.16611 | 104.04257
88 | CMI | RLC | Nasional | #NAME? | 2025-05-03 | E1200347 | ID-KR-04100 | JODOH | 2 | EMA | KEPULAUAN RIAU | Kota Batam | HOTEL OASIS KOMPLEX ORCHID MAS CENTRE, SEI JODOH, BATU AMPAR | 1.157056 | 104.003753 | 971.83 | 10 | IOH | Rooftop | Pole | Relocation Equipment |  |  | Survey | 2025-05-04 | 2025-05-11 | Expired |  | 2025-05-07 | 2025-05-14 | [5 empty] | 2025-10-17 |  | 2026-01-09 | 2026-01-09 | ATP App MS |  | 2025-12-12 | 2025-12-15 | 2025-12-12 | 2025-01-06 | 2026-01-07 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-18 | 2025-06-24 | JSA No.6/TSA/HSE/06/2025 |  |  |  | Approved | NY Submit | 2026-03-03 | 2026-03-03 | Relocation Equipment | EMAPO26-000079 | 2026-01-30 | 18 |  |  | 0 |  |  |  | Complete |  |  |  | ID-KR-14656 | SUNGAI JODOH | 1.16611 | 104.04257 | CR-20250925-00000432
89 | CMI | RLC | Nasional | #NAME? | 2025-05-13 | R6300038 | ID-KS-09713 | TRANS KALIMANTAN | 18 | CMI | KALIMANTAN SELATAN | Kab. Barito Kuala | JL. TRANS KALIMANTAN RT. 09 DS. HANDIL BAKTI KEC. ALALAK KAB. BARITO KUALA KALIMANTAN SELATAN | -3.27494 | 114.599 | 3713.64 | 25 | XL & IOH | Rooftop | MT 4 Legs | Dismantle Tower | Lingga | +62 822-3408-7449 | Dismantle | 2026-01-12 | 2026-01-19 | Expired |  | 2025-05-16 | 2025-05-19 |  | 2026-01-06 |  | 2026-01-26 |  |  |  | 2026-01-26 | 2026-01-26 | BAST | 20.01.26 Start dismantle | 2025-11-21 | 2025-12-05 | 2025-12-04 | 2026-04-06 | 2025-12-05 | 2025-12-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-18 | 2025-06-24 | JSA No.07/TSA/HSE/06/2025 | 2025-06-26 | 2025-07-11 | SWP-HSE-50 | Approved | Approved | 2026-01-27 | 2026-01-28 | Dismantle Tower | CMIPO25-005577 | 2025-12-17 | 12 |  |  | 0 |  |  |  | Complete
90 | CMI | RLC | Nasional | #NAME? | 2025-05-13 | R6300038 | ID-KS-09713 | TRANS KALIMANTAN | 18 | CMI | KALIMANTAN SELATAN | Kab. Barito Kuala | JL. TRANS KALIMANTAN RT. 09 DS. HANDIL BAKTI KEC. ALALAK KAB. BARITO KUALA KALIMANTAN SELATAN | -3.27494 | 114.599 | 3713.64 | 25 | XL & IOH | Rooftop | MT 4 Legs | Dismantle Equipment | Lingga | +62 822-3408-7449 | Dismantle | 2026-01-12 | 2026-01-19 | Expired |  | 2025-05-16 | 2025-05-19 |  |  | 2026-01-16 |  |  |  |  | 2026-01-26 |  | ATP App MS | 13.01.26 Dismantle equip IOH 16.01.26 Dismantle equip XLS | 2025-11-21 | 2025-12-05 | 2025-12-04 | 2026-04-06 | 2025-12-05 | 2025-12-05 | 1st BOQ App on ISAAC | 2026-02-06 |  |  | 2026-04-14 |  | 2026-04-24 | 2nd BOQ App on ISAAC |  | 2025-06-18 | 2025-06-24 | JSA No.07/TSA/HSE/06/2025 |  |  |  | Approved | NY Submit | 2026-02-11 |  | Dismantle Equipment | Include Reloc | 2025-12-17 | 12 |  |  | 103 |  |  |  | Complete | CMI Project | CMI
91 | CMI | RLC | Nasional | #NAME? | 2025-05-13 | R6300038 | ID-KS-09713 | TRANS KALIMANTAN | 18 | CMI | KALIMANTAN SELATAN | Kab. Barito Kuala | JL. TRANS KALIMANTAN RT. 09 DS. HANDIL BAKTI KEC. ALALAK KAB. BARITO KUALA KALIMANTAN SELATAN | -3.27494 | 114.599 | 3713.64 | 25 | XL & IOH | Rooftop | MT 4 Legs | Relocation Equipment | Lingga | +62 822-3408-7449 | Reloc | 2026-01-12 | 2026-01-19 | Expired |  | 2025-05-16 | 2025-05-19 | [5 empty] | 2026-01-18 | 2026-01-20 | 2026-01-26 |  | ATP App MS | 14.01.26 Reinstall IOH 16.01.26 OA IOH 17.01.26 Reinstall XLS 20.01.26 OA XLS | 2025-11-21 | 2025-12-05 | 2025-12-04 | 2026-04-06 | 2025-12-05 | 2025-12-05 | 1st BOQ App on ISAAC | 2026-02-06 |  |  | 2026-04-14 | 2026-04-24 | 2026-04-24 | 2nd BOQ App on ISAAC |  | 2025-06-18 | 2025-06-24 | JSA No.07/TSA/HSE/06/2025 |  |  |  | Approved | NY Submit | 2026-02-11 |  | Relocation Equipment | CMIPO25-005582 | 2025-12-17 | 12 | CMIPO26-002503 | 2026-07-27 | 94 |  |  |  | Waiting PO Variation | CMI Project | CMI |  | ID-KS-15363 | ALALAK BARITO | -3.2786 | 114.5995 | CR-20260111-00000093 CR-20260110-00000137 CR-20260110-00000138 CR-20260110-00000139 | XLWO-20260108-00000796
92 | CMI | RLC | Nasional | #NAME? | 2025-05-27 | R3600173 | ID-BT-00439 | KARANG SARI, NEGLASARI | 6 | CMI | BANTEN | Kota Tangerang | JL. BARIANG HILIR NO.14 RT01/01 KEL.KARANGSARI KEC. NEGLASARI TANGGERANG | -6.15594 | 106.63649 | 4839.86 | 20 |  | Greenfield | Monopole | Dismantle Tower |  |  | Survey | 2025-05-29 | 2025-06-04 | Expired |  | 2025-06-03 | 2025-06-05 |  | 2025-06-18 |  | 2025-07-19 |  |  |  | 2025-07-19 | 2025-07-23 | BAST |  | 2025-06-24 | 2025-08-13 | 2025-06-26 | 2025-08-14 | 2025-08-14 | 2025-08-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-12 | 2025-06-17 | JSA No.04/TSA/HSE/06/2025 | 2025-06-12 | 2025-06-13 | SWP-HSE-47 | Approved | Approved | 2025-07-23 | 2025-07-23 | Dismantle Tower | CMIPO25-003970 | 2025-08-28 | 14 |  |  | 0 |  |  |  | Complete
93 | CMI | RLC | Nasional | #NAME? | 2025-05-27 | R3600174 | ID-BT-00448 | PERIUK JAYA, PERIUK 1 | 6 | CMI | BANTEN | Kota Tangerang | JL. DADAP V NO. 104 RT 02 RW 08 KEL. PERIUK JAYA KEC. PERIUK, TANGERANG | -6,16462 | 106,60799 | 402.81 | 9 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-05-29 | 2025-06-04 | Expired |  | 2025-06-03 | 2025-06-05 |  | 2025-07-22 |  | 2025-07-23 |  |  |  | 2025-07-23 | 2025-07-25 | BAST |  | 2025-06-24 | 2025-06-26 | 2025-06-26 |  | 2025-06-26 | 2025-06-26 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-12 | 2025-06-17 | JSA No.05/TSA/HSE/06/2025 | 2025-06-12 | 2025-06-13 | SWP-HSE-48 | Approved | Approved | 2025-07-25 |  | Dismantle Tower | CMIPO25-003034 | 2025-07-16 | 20 |  |  | 0 |  |  |  | Complete
94 | CMI | RLC | Nasional | #NAME? | 2025-05-27 | E3500247 | ID-JI-06415 | MIC_PIRANHA | 15 | EMA | JAWA TIMUR | Kota Malang | JL. IKAN PIRANHA ATAS NO 63 RT/RW 02/03, KEL. LOWOK WARU, KEC. TANJUNG SEKAR, MALANG | -7.92965 | 112.633 | 461.03 | 6 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-05-29 | 2025-06-04 | Expired |  | 2025-05-30 | 2025-06-02 |  | 2025-06-18 |  | 2025-07-14 |  |  |  | 2025-07-14 | 2025-07-16 | BAST |  | 2025-06-24 | 2025-06-26 | 2025-06-26 |  | 2025-07-03 | 2025-07-04 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-12 | 2025-06-17 | JSA No.02/TSA/HSE/06/2025 | 2025-06-04 | 2025-06-09 | SWP-HSE-41 | Approved | Approved | 2025-07-14 | 2025-07-14 | Dismantle Tower | EMAPO25-001440 | 2025-07-14 | 10 |  |  | 0 |  |  |  | Complete
95 | CMI | RLC | Nasional | #NAME? | 2025-05-27 | E3500383 | ID-JI-06548 | RUNGKUT | 13 | EMA | JAWA TIMUR | Kota Surabaya | JL.RUNGKUTMENANGGALSELATANXIBLOKGA22NO.18SURABAYA | -7,33845 | 112,77723 | 7151.724 | 42.5 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-05-29 | 2025-06-04 | Expired |  | 2025-06-02 | 2025-06-04 |  | 2025-06-18 |  | 2025-07-10 |  |  |  | 2025-07-14 | 2025-07-16 | BAST |  | 2025-06-24 | 2025-07-02 | 2025-07-04 | 2025-07-22 | 2025-08-05 | 2025-08-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-12 | 2025-06-17 | JSA No.01/TSA/HSE/06/2025 | 2025-06-04 | 2025-06-09 | SWP-HSE-42 | Approved | Approved | 2025-07-14 | 2025-07-16 | Dismantle Tower | EMAPO25-001688 | 2025-08-13 | 7 |  |  | 0 |  |  |  | Complete
96 | CMI | RLC | Nasional | #NAME? | 2025-05-27 | E3100487 | ID-JK-04884 | MIC_TRMNL_PULO_GEBANG | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Timur | PULO GEBANG, CAKUNG, JAKARTA TIMUR | -6,21136 | 106,95349 | 386.97 | 6 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-05-29 | 2025-06-04 | Expired |  | 2025-06-02 | 2025-06-05 |  | 2025-06-18 |  | 2025-07-04 |  |  |  | 2025-07-11 | 2025-07-11 | BAST |  | 2025-06-24 | 2025-06-30 | 2025-06-30 |  | 2025-06-30 | 2025-07-16 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-06-12 | 2025-06-17 | JSA No.03/TSA/HSE/06/2025 | 2025-06-05 | 2025-06-09 | SWP-HSE-46 | Approved | Approved | 2025-07-11 |  | Dismantle Tower | EMAPO25-001439 | 2025-07-14 | #NUM! |  |  | 0 |  |  |  | Complete
97 | CMI | RLC | Nasional | #NAME? | 2025-05-27 | E6400029 | ID-KI-07418 | ITCI_DONGHWA | 18 | EMA | KALIMANTAN TIMUR | Kab. Penajam Paser Utara | PT.ITCI KARTIKA UTAMA KENANGAN, KEC. PENAJAM, KAB. PENAJAM PASER UTARA, KAL-TIM | -1.08965 | 116.68709 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-05-29 | 2025-06-04 | Expired |  | 2025-06-03 | 2025-06-05 | Drop | [8 empty] | Drop | Survey Only | 2026-04-13 | 2026-04-14 |  |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit |  | 2025-06-18 | 2025-06-24 | JSA No.08/TSA/HSE/06/2025 | 2025-06-19 | 2025-06-24 | SWP-HSE-49 | Approved | Approved |  |  | Dismantle Tower | NY release |  | Drop |  |  | Drop |  |  |  | PO NY Release | CMI Project
98 | CMI | RLC | Nasional | #NAME? | 2025-05-27 | E6400029 | ID-KI-07418 | ITCI_DONGHWA | 18 | EMA | KALIMANTAN TIMUR | Kab. Penajam Paser Utara | PT.ITCI KARTIKA UTAMA KENANGAN, KEC. PENAJAM, KAB. PENAJAM PASER UTARA, KAL-TIM | -1.08965 | 116.68709 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-05-29 | 2025-06-04 | Expired |  | 2025-06-03 | 2025-06-05 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-06-18 | 2025-06-24 | JSA No.08/TSA/HSE/06/2025 | 2025-06-19 | 2025-06-24 |  | Approved | Approved |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop
99 | CMI | RLC | Nasional | #NAME? | 2025-05-27 | E6400029 | ID-KI-07418 | ITCI_DONGHWA | 18 | EMA | KALIMANTAN TIMUR | Kab. Penajam Paser Utara | PT.ITCI KARTIKA UTAMA KENANGAN, KEC. PENAJAM, KAB. PENAJAM PASER UTARA, KAL-TIM | -1.08965 | 116.68709 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Relocation Equipment |  |  | Survey | 2025-05-29 | 2025-06-04 | Expired |  | 2025-06-03 | 2025-06-05 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-06-18 | 2025-06-24 | JSA No.08/TSA/HSE/06/2025 | 2025-06-19 | 2025-06-24 |  | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop
100 | CMI | RLC | Nasional | #NAME? | 2025-06-11 | E1200343 | ID-KR-04096 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | 2 | EMA | KEPULAUAN RIAU | Kota Batam | KP. PARADISE RT 07/3 DAERAH SUNGAI TEMIANG KEL. TIBAN ASRI KEC. SEKUPANG BATAM | 1.06381 | 103.97043 | 8236.656 | 40 | IOH, Tsel, XL | Greenfield | SST 4 Legs | Dismantle Tower | Abe Rizal |  | Survey | 2025-06-12 | 2025-06-19 | Expired |  | 2025-06-21 | 2025-06-26 |  | 2025-12-12 |  | 2025-12-29 |  |  |  | 2025-12-30 | 2025-12-30 | BAST |  | 2025-11-24 |  | 2025-12-03 |  | 2026-02-02 | 2026-02-02 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 29.12.25 Revisi BOQ non SL | 2025-07-03 | 2025-07-07 | JSA No.04/TSA/HSE/07/2025 | 2025-07-03 | 2025-07-04 | SWP-HSE-51 | Approved | Approved | 2025-12-31 | 2025-12-31 | Dismantle Tower | EMAPO26-000134 | 2026-02-10 | 8 |  |  | 0 |  |  |  | Complete
101 | CMI | RLC | Nasional | #NAME? | 2025-06-11 | E1200343 | ID-KR-04096 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | 2 | EMA | KEPULAUAN RIAU | Kota Batam | KP. PARADISE RT 07/3 DAERAH SUNGAI TEMIANG KEL. TIBAN ASRI KEC. SEKUPANG BATAM | 1.06381 | 103.97043 | 8236.656 | 40 | IOH, Tsel, XL | Greenfield | SST 4 Legs | Dismantle Equipment | Abe Rizal |  | Survey | 2025-06-12 | 2025-06-19 | Expired |  | 2025-06-21 | 2025-06-26 |  | 2025-12-12 | 2025-12-16 |  |  |  |  | 2025-12-27 |  | ATP App MS | 08.12.25 Dism Tsel 14.12.25 Dism XL 16.12.25 Dism IOH | 2025-11-24 |  | 2025-12-03 |  | 2026-02-02 | 2026-02-02 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-07-03 | 2025-07-07 | JSA No.04/TSA/HSE/07/2025 | 2025-07-03 | 2025-07-04 |  | Approved | Approved | 2026-01-30 |  | Dismantle Equipment | Include Reloc | 2026-02-10 | 8 |  |  | 0 |  |  |  | Complete
102 | CMI | RLC | Nasional | #NAME? | 2025-06-11 | E1200343 | ID-KR-04096 | TEMIANG_BATAM / BUKIT MATA KUCING 2 | 2 | EMA | KEPULAUAN RIAU | Kota Batam | KP. PARADISE RT 07/3 DAERAH SUNGAI TEMIANG KEL. TIBAN ASRI KEC. SEKUPANG BATAM | 1.06381 | 103.97043 | 8236.656 | 40 | IOH, Tsel, XL | Greenfield | SST 4 Legs | Relocation Equipment | Abe Rizal |  | Survey | 2025-06-12 | 2025-06-19 | Expired |  | 2025-06-21 | 2025-06-26 |  | 2025-12-12 |  |  |  |  | 2025-12-24 | 2025-12-27 |  | ATP App MS | 24.12.25 Tsel OA 15.12.25 XL OA 22.12.25 IOH OA | 2025-11-24 |  | 2025-12-03 |  | 2026-02-02 | 2026-02-02 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-07-03 | 2025-07-07 | JSA No.04/TSA/HSE/07/2025 | 2025-07-03 | 2025-07-04 |  | Approved | Approved | 2026-01-30 |  | Relocation Equipment | EMAPO26-000136 | 2026-02-10 | 8 |  |  | 0 |  |  |  | Complete |  |  |  | ID-KR-15629 | SEKUPANG BATAM |  |  |  | XLWO-20251118-00000014 | CRQ000001041435
103 | CMI | RLC | Nasional | #NAME? | 2025-01-12 | R3580657 | ID-JI-03692 | BUMIINDAH | 13 | CMI | JAWA TIMUR | Kota Surabaya |  | -7.26353 | 112.674 |  | 12 | IOH / SF | Rooftop | Pole | Dismantle Equipment | Rano Aprilian Werdhana | 89677996532 | Reloc | 2025-01-22 | 2025-02-21 | Expired |  | 2025-01-12 | 2025-01-23 |  |  | 2025-01-21 |  |  | 2025-01-21 | 2025-01-22 | 2025-01-23 |  | ATP App MS |  | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-02-26 | 2025-02-04 | 2025-06-17 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-01-23 | 2025-01-23 | JSA No.02/TSA/HSE/01/2025 | 2025-01-23 | 2025-01-23 | SWP-HSE-02 | Approved | Approved | 2025-03-15 | 2025-03-15 | Dismantle Equipment | CMIPO25-002317 | 2025-06-13 | #NUM! | CMIPO25-002318 | 2025-06-13 | 0 |  |  |  | Complete
104 | CMI | RLC | Nasional | #NAME? | 2025-01-12 | R3580657 | ID-JI-03692 | BUMIINDAH | 13 | CMI | JAWA TIMUR | Kota Surabaya |  | -7.26353 | 112.674 |  | 12 | IOH / SF | Rooftop | Pole | Relocation Equipment | Rano Aprilian Werdhana | 89677996532 | Reloc | 2025-01-22 | 2025-02-21 | Expired |  | 2025-01-12 | 2025-01-23 | [5 empty] | 2025-01-21 | 2025-01-22 | 2025-01-23 |  | ATP App MS |  | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-02-26 | 2025-02-04 | 2025-06-17 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-01-23 | 2025-01-23 | JSA No.02/TSA/HSE/01/2025 | 2025-01-23 | 2025-01-23 |  | Approved | Approved | 2025-03-15 | 2025-03-15 | Relocation Equipment | CMIPO25-002319 | 2025-06-13 | #NUM! |  |  | 0 |  |  |  | Complete
105 | CMI | RLC | Nasional | #NAME? | 2025-01-12 | R3580657 | ID-JI-03692 | BUMIINDAH | 13 | CMI | JAWA TIMUR | Kota Surabaya |  | -7.26353 | 112.674 |  | 12 | IOH / SF | Rooftop | Pole | Dismantle Tower | Rano Aprilian Werdhana | 89677996532 | Reloc | 2025-01-22 | 2025-02-21 | Expired |  | 2025-01-12 | 2025-01-23 | [5 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | Survey Report |  | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2025-02-26 | 2025-02-04 | 2025-06-17 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-01-23 | 2025-01-23 | JSA No.02/TSA/HSE/01/2025 | 2025-01-23 | 2025-01-23 |  | Approved | Approved | 2025-03-15 | 2025-03-15 | Dismantle Tower | CMIPO25-005450 | 2025-12-10 | 176 |  |  | 0 |  |  |  | Complete
106 | CMI | RLC | Nasional | #NAME? | 2025-06-23 | E3600061 | ID-BT-06774 | PARUNGSARI | 6 | EMA | BANTEN | Kab. Lebak | JL. RAYA CIPANAS KP. CURUNG PASIR | -6.36815 | 106.283 | 22120.78 | 70 | IOH, Tsel, SF | Greenfield | SST 4 Legs | Dismantle Tower | Andri Kurniawan | 85778921471 | Expired | 2025-06-24 | 2025-07-01 | Expired |  | 2025-07-28 | 2025-07-28 |  | 2025-08-27 |  | 2025-09-10 |  |  |  | 2025-09-10 | 2025-09-12 | BAST |  | 2025-09-03 | 2025-11-06 | 2025-09-04 | 2025-11-11 | 2025-11-06 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-07-28 | 2025-07-31 | JSA No.05/TSA/HSE/07/2025 | 2025-07-28 | 2025-07-31 | SWP-HSE-54 | Approved | Approved | 2025-09-12 |  | Dismantle Tower | EMAPO25-002240 | 2025-11-21 | 0 |  |  | 0 |  |  |  | Complete | [5 empty] | -6.36701 | 106.28291
107 | CMI | RLC | Nasional | #NAME? | 2025-06-23 | E3600061 | ID-BT-06774 | PARUNGSARI | 6 | EMA | BANTEN | Kab. Lebak | JL. RAYA CIPANAS KP. CURUNG PASIR | -6.36815 | 106.283 | 22120.78 | 70 | IOH, Tsel, SF | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-07-28 | 2025-07-28 |  |  | 2025-09-04 |  |  |  |  | 2025-09-10 |  | ATP App MS |  | 2025-09-03 | 2025-11-06 | 2025-09-04 |  | 2025-11-06 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-07-28 | 2025-07-31 | JSA No.05/TSA/HSE/07/2025 | 2025-07-28 | 2025-07-31 |  | Approved | Approved |  |  | Dismantle Equipment | Include Reloc | 2025-11-21 | 0 |  |  | 0 |  |  |  | Complete | CMI Project | CMI |  |  |  | -6.36701 | 106.28291
108 | CMI | RLC | Nasional | #NAME? | 2025-06-23 | E3600061 | ID-BT-06774 | PARUNGSARI | 6 | EMA | BANTEN | Kab. Lebak | JL. RAYA CIPANAS KP. CURUNG PASIR | -6.36815 | 106.283 | 22120.78 | 70 | IOH, Tsel, SF | Greenfield | SST 4 Legs | Relocation Equipment to Combat | Taufik Hidayat |  | Reloc | 2026-01-12 | 2026-01-19 | Expired |  | 2025-07-28 | 2025-07-28 | [5 empty] | 2025-09-05 |  | 2025-09-10 |  | ATP App MS |  | 2025-09-03 | 2025-11-06 | 2025-09-04 | 2025-11-11 | 2025-11-06 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-07-28 | 2025-07-31 | JSA No.05/TSA/HSE/07/2025 | 2025-07-28 | 2025-07-31 |  | Approved | Approved |  |  | Relocation Equipment | EMAPO25-002243 | 2025-11-21 | 0 |  |  | 0 |  |  |  | Complete | CMI Project | CMI |  | ID-BT-16555 | RANGKASBITUNG LEBAK | -6.36701 | 106.28291 |  |  | WO-GEN_PWO-240825-0853909
109 | CMI | RLC | Nasional | #NAME? | 2025-06-28 | E3200276 | ID-JB-05231 | ISTAKA | 10 | EMA | JAWA BARAT | Kota Bekasi | Bojong Rawalumbu, Kec. Rawalumbu, Kota Bks, Jawa Barat 17116 | -6.28726 | 106.98544 | 14671.33 |  |  | Greenfield | SST 4 Legs | Dismantle Tower | Andi Wawan |  |  |  |  | NY Submit |  | 2025-07-05 | 2025-07-05 |  | 2025-07-24 |  | 2025-08-11 |  |  |  | 2025-08-25 | 2025-08-25 | BAST |  | 2025-08-06 | 2025-08-13 | 2025-08-11 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-07-07 | 2025-07-23 | JSA No.02/TSA/HSE/07/2025 | 2025-05-16 | 2025-05-19 |  | Approved | Approved | 2025-08-26 | 2025-08-26 | Dismantle Tower | EMAPO25-001895 | 2025-09-17 | 30 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JB-16193 | RAWALUMBU BEKASI | -6.28813 | 106.98704
110 | CMI | RLC | Nasional | #NAME? | 2025-07-10 | E3200644 | ID-JB-05598 | JALAKSANA | 10 | EMA | JAWA BARAT | Kab. Kuningan | DUSUN MANIS RT 010 RW 002 DESA KALAPAGUNUNG KEC KRAMATMULYA KAB KUNINGAN JAWA BARAT | -6.93207 | 108.48000 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower | Andi Wawan | 81999101650 | Active | 2025-07-19 | 2025-07-26 | Expired |  | 2025-11-13 | 2025-11-17 | [9 empty] | Survey Report | Survey Only | 2026-02-03 | 2026-02-09 |  |  | 2026-02-25 | 2026-02-25 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | Pekerjaan cancel pengajuan BOQ Survey only 03.02.26 | 2025-11-17 | 2025-11-21 | JSA No.08/TSA/HSE/11/2025 | 2025-11-18 | 2025-11-21 | SWP-HSE-91 | Approved | Approved |  |  | Dismantle Tower | EMAPO26-000404 | 2026-03-16 | 19 |  |  | 0 |  |  |  | Complete
111 | CMI | RLC | Nasional | #NAME? | 2025-07-10 | E3200644 | ID-JB-05598 | JALAKSANA | 10 | EMA | JAWA BARAT | Kab. Kuningan | DUSUN MANIS RT 010 RW 002 DESA KALAPAGUNUNG KEC KRAMATMULYA KAB KUNINGAN JAWA BARAT | -6.93207 | 108.48000 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Dismantle Equipment | Andi Wawan |  |  |  |  | NY Submit |  | 2025-11-13 | 2025-11-17 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-11-17 | 2025-11-21 | JSA No.08/TSA/HSE/11/2025 | 2025-11-18 | 2025-11-21 |  | Approved | Approved |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop
112 | CMI | RLC | Nasional | #NAME? | 2025-07-10 | E3200644 | ID-JB-05598 | JALAKSANA | 10 | EMA | JAWA BARAT | Kab. Kuningan | DUSUN MANIS RT 010 RW 002 DESA KALAPAGUNUNG KEC KRAMATMULYA KAB KUNINGAN JAWA BARAT | -6.93207 | 108.48000 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Relocation Equipment | Andi Wawan |  |  |  |  | NY Submit |  | 2025-11-13 | 2025-11-17 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-11-17 | 2025-11-21 | JSA No.08/TSA/HSE/11/2025 | 2025-11-18 | 2025-11-21 |  | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop
113 | CMI | RLC | Nasional | #NAME? | 2025-07-10 | E3200182 | ID-JB-05137 | GEULIS_RESORT | 10 | EMA | JAWA BARAT | Kab. Bogor | Gn. Geulis, Kabupaten Bogor, Jawa Barat | -6.6269 | 106.86487 | 18868.812 | 70 | IOH & XLS | Greenfield | SST 4 Legs | Dismantle Tower | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-07-15 | 2025-07-16 | 2026-01-21 | [8 empty] | Survey Report |  | 2026-07-24 |  | 2026-07-24 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit |  | 2025-07-17 | 2025-07-23 | JSA No.03/TSA/HSE/07/2025 | 2025-07-17 | 2025-07-23 | SWP-HSE-53 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0 |  |  |  | BOQ NY Submit | Alfan | TSA |  | ID-JB-14444 | GEULIS SUKARAJA | -6.63167 | 106.8662
114 | CMI | RLC | Nasional | #NAME? | 2025-07-10 | E3200182 | ID-JB-05137 | GEULIS_RESORT | 10 | EMA | JAWA BARAT | Kab. Bogor | Gn. Geulis, Kabupaten Bogor, Jawa Barat | -6.6269 | 106.86487 | 18868.812 | 70 | IOH & XLS | Greenfield | SST 4 Legs | Dismantle Equipment | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-07-15 | 2025-07-16 | 2026-01-21 | [8 empty] | Survey Report |  | 2026-07-24 |  | 2026-07-24 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit |  | 2025-07-17 | 2025-07-23 | JSA No.03/TSA/HSE/07/2025 | 2025-07-17 | 2025-07-23 |  | Approved | Approved |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0 |  |  |  | BOQ NY Submit | Alfan | TSA |  | ID-JB-14444 | GEULIS SUKARAJA | -6.63167 | 106.8662
115 | CMI | RLC | Nasional | #NAME? | 2025-07-10 | E3200182 | ID-JB-05137 | GEULIS_RESORT | 10 | EMA | JAWA BARAT | Kab. Bogor | Gn. Geulis, Kabupaten Bogor, Jawa Barat | -6.6269 | 106.86487 | 18868.812 | 70 | IOH & XLS | Greenfield | SST 4 Legs | Relocation Equipment | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-07-15 | 2025-07-16 | 2026-01-21 | [8 empty] | Survey Report |  | 2026-07-24 |  | 2026-07-24 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit |  | 2025-07-17 | 2025-07-23 | JSA No.03/TSA/HSE/07/2025 | 2025-07-17 | 2025-07-23 |  | Approved | Approved |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0 |  |  |  | BOQ NY Submit | Alfan | TSA |  | ID-JB-14444 | GEULIS SUKARAJA | -6.63167 | 106.8662
116 | CMI | RLC | Nasional | #NAME? | 2025-07-10 | E3200269 | ID-JB-05224 | CILEUNGSIKIDUL | 10 | EMA | JAWA BARAT | Kab. Bogor | Cileungsi Kidul, Kabupaten Bogor, Jawa Barat | -6.40574 | 106.97561 | 16015.06 | 55 | IOH , SF & XL | Greenfield | SST 4 Legs | Dismantle Tower | Taufik Hidayat |  | Dismantle | 2026-04-15 | 2026-04-21 | Expired |  | 2025-07-12 | 2025-07-13 |  | 2026-04-10 |  | 2026-04-22 | [5 empty] | Dismantle | 20.04.26 Start dismantle | 2026-01-14 | 2026-02-09 | 2026-01-15 | 2026-04-06 | 2026-02-09 | 2026-02-09 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-07-17 | 2025-07-23 | JSA No.01/TSA/HSE/07/2025 | 2025-07-17 | 2025-07-23 | SWP-HSE-52 | Approved | Approved | 2026-05-04 | 2026-05-04 | Dismantle Tower | EMAPO26-000335 | 2026-02-25 | 16 |  |  | 0 |  |  |  | Complete | CMI Project | CMI |  | ID-JB-16165 | CILEUNGSI BOGOR | -6.40554 | 106.97553
117 | CMI | RLC | Nasional | #NAME? | 2025-07-10 | E3200269 | ID-JB-05224 | CILEUNGSIKIDUL | 10 | EMA | JAWA BARAT | Kab. Bogor | Cileungsi Kidul, Kabupaten Bogor, Jawa Barat | -6.40574 | 106.97561 | 16015.06 | 55 | IOH , SF & XL | Greenfield | SST 4 Legs | Dismantle Equipment | Taufik Hidayat |  | Dismantle | 2026-04-06 | 2026-04-12 | Expired |  | 2025-07-12 | 2025-07-13 |  | 2026-04-10 | 2026-04-15 |  | 2026-06-19 |  |  | 2026-04-17 | 2026-04-17 | ATP App MS | 07.04.26 Start Dismantle IOH 08.04.26 Start dismantle SF 15.04.26 Plan Dismantle XL 19.06.26 Inbound material XL yg tidak di reloc | 2026-01-14 | 2026-02-09 | 2026-01-15 | 2026-04-06 | 2026-02-09 | 2026-02-09 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-07-17 | 2025-07-23 | JSA No.01/TSA/HSE/07/2025 | 2025-07-17 | 2025-07-23 |  | Approved | Approved |  |  | Dismantle Equipment | Include Reloc | 2026-02-25 | 16 |  |  | 0 |  |  |  | 08.05.26 ATP XL & SF App 11.05.26 ATP IOH App | CMI Project | CMI |  | ID-JB-16165 | CILEUNGSI BOGOR | -6.40554 | 106.97553 | CR-20260406-00000060 CR-20260406-00000065 | XLWO-20260407-00000343
118 | CMI | RLC | Nasional | #NAME? | 2025-07-10 | E3200269 | ID-JB-05224 | CILEUNGSIKIDUL | 10 | EMA | JAWA BARAT | Kab. Bogor | Cileungsi Kidul, Kabupaten Bogor, Jawa Barat | -6.40574 | 106.97561 | 16015.06 | 55 | IOH , SF & XL | Greenfield | SST 4 Legs | Relocation Equipment | Taufik Hidayat |  | Dismantle | 2026-04-06 | 2026-04-12 | Expired |  | 2025-07-12 | 2025-07-13 |  | 2026-04-10 |  |  |  | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | ATP App MS | 08.04.26 Done Install IOH 10.04.26 Done Install SF 17.04.26 Done Install XL | 2026-01-14 | 2026-02-09 | 2026-01-15 | 2026-04-06 | 2026-02-09 | 2026-02-09 | 1st BOQ App on ISAAC | 2026-04-06 | 2026-04-28 | NA | 2026-05-05 | 2026-05-11 | 2026-05-11 | 2nd BOQ App on ISAAC |  | 2025-07-17 | 2025-07-23 | JSA No.01/TSA/HSE/07/2025 | 2025-07-17 | 2025-07-23 |  | Approved | Approved |  |  | Relocation Equipment | EMAPO26-000338 | 2026-02-25 | 16 | EMAPO26-000642 | 2026-05-29 | 18 |  |  |  | 08.05.26 ATP XL & SF App 11.05.26 ATP IOH App | CMI Project | CMI |  | ID-JB-16165 | CILEUNGSI BOGOR | -6.40554 | 106.97553 | CR-20260406-00000060 CR-20260406-00000065 | XLWO-20260407-00000343
119 | CMI | RLC | Nasional | #NAME? | 2025-07-24 | E3600214 | ID-BT-06924 | SUPERMAL | 6 | EMA | BANTEN | Kab. Tangerang | Jl. Boulevard Diponegoro No.105, Bencongan, Kec. Klp. Dua, Kabupaten Tangerang, Banten 15810 | -6.22686 | 106.60578 | 4519.52 |  |  | Rooftop | Pole | Dismantle Tower | Taufik + Kusmana |  | Dismantle | 2026-03-11 | 2026-03-17 | Expired |  | 2025-07-31 | 2025-07-31 |  | 2025-11-26 |  | 2026-03-17 |  |  |  |  | 2026-03-17 | BAST | 13.03.26 Start dismantle | 2025-10-29 | 2025-11-12 | 2025-10-30 | 2025-01-06 | 2025-11-20 | 2025-11-24 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-05 | 2025-08-05 | 06/TSA/HSE/07/2025 | 2025-08-05 | 2025-08-05 |  | Approved | Approved | 2026-03-17 | 2026-03-17 | Dismantle Tower | EMAPO25-002289 | 2025-12-03 | 9 |  |  | 0 |  |  |  | Complete |  |  |  | ID-BT-02965 | SITE KARAWACI ( PURI BETA ) | -6.22432 | 106.60764
120 | CMI | RLC | Nasional | #NAME? | 2025-07-24 | E3600214 | ID-BT-06924 | SUPERMAL | 6 | EMA | BANTEN | Kab. Tangerang | Jl. Boulevard Diponegoro No.105, Bencongan, Kec. Klp. Dua, Kabupaten Tangerang, Banten 15810 | -6.22686 | 106.60578 | 4519.52 |  |  | Rooftop | Pole | Dismantle Equipment | Taufik + Kusmana |  | Dismantle | 2025-10-29 | 2025-11-05 | Expired |  | 2025-07-31 | 2025-07-31 |  |  | 2025-11-24 |  |  |  |  | 2025-11-28 | 2025-11-28 | ATP App MS |  | 2025-10-29 | 2025-11-12 | 2025-10-30 | 2025-01-06 | 2025-11-20 | 2025-11-24 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-05 | 2025-08-05 | 06/TSA/HSE/07/2025 | 2025-08-05 | 2025-08-05 |  | Approved | Approved | 2026-01-06 | 2026-01-06 | Dismantle Equipment | Include Reloc | 2025-12-05 | 11 |  |  | 0 |  |  |  | PO add cost NY release | CMI Project | CMI |  | ID-BT-02965 | SITE KARAWACI ( PURI BETA ) | -6.22432 | 106.60764
121 | CMI | RLC | Nasional | #NAME? | 2025-07-24 | E3600214 | ID-BT-06924 | SUPERMAL | 6 | EMA | BANTEN | Kab. Tangerang | Jl. Boulevard Diponegoro No.105, Bencongan, Kec. Klp. Dua, Kabupaten Tangerang, Banten 15810 | -6.22686 | 106.60578 | 4519.52 |  |  | Rooftop | Pole | Relocation Equipment | Taufik Hidayat |  | Reloc | 2025-11-04 | 2025-11-10 | Expired | Puri beta | 2025-07-31 | 2025-07-31 | [5 empty] | 2025-11-30 | 2025-11-28 | 2025-11-28 | 2025-11-28 | ATP App MS |  | 2025-10-29 | 2025-11-12 | 2025-10-30 | 2025-01-06 | 2025-11-20 | 2025-11-24 | 1st BOQ App on ISAAC | 2025-01-06 |  |  | 2025-01-06 |  | 2026-04-15 | 2nd BOQ App on ISAAC |  | 2025-08-05 | 2025-08-05 | 06/TSA/HSE/07/2025 | 2025-08-05 | 2025-08-05 | SWP-HSE-55 | Approved | Approved | 2026-01-06 | 2026-01-06 | Relocation Equipment | CMIPO25-005254 | 2025-12-05 | 11 | CMIPO26-001672 | 2025-12-05 | #NUM! |  |  |  | Complete | CMI Project | CMI |  | ID-BT-02965 | SITE KARAWACI ( PURI BETA ) | -6.22432 | 106.60764
122 | CMI | RLC | Nasional | #NAME? | 2025-07-15 | E3300206 | ID-JT-05916 | GENUK | 11 | EMA | JAWA TENGAH | Kota Semarang | JL. DONG BIRU RT 07/03, GENUK SARI, GENUK, KODYA SEMARANG | -6.96484 | 110.47557 |  | 52 | Tsel | Greenfield | SST 4 Legs | Dismantle Equipment (BTS Only) | Arrys Yasir Z -KUS | 89612377850 | Survey | 2025-07-30 | 2025-08-05 | Expired |  | 2025-07-19 | 2025-07-19 |  |  | 2025-08-14 |  |  |  |  | 2025-08-14 |  | ATP App MS |  | 2025-07-24 | 2025-10-08 |  |  | 2025-10-27 | 2025-10-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | Include PO Colo | 2025-10-09 | #NUM! |  |  | 0 |  |  |  | PO Include Colo | CMI Project | CMI
123 | CMI | RLC | Nasional | #NAME? | 2025-07-15 | E3300206 | ID-JT-05916 | GENUK | 11 | EMA | JAWA TENGAH | Kota Semarang | JL. DONG BIRU RT 07/03, GENUK SARI, GENUK, KODYA SEMARANG | -6.96484 | 110.47557 |  | 52 | Tsel | Greenfield | SST 4 Legs | Relocation Equipment (BTS Only) | Arrys Yasir Z -KUS | 89612377850 | Survey | 2025-07-19 | 2025-07-25 | Expired |  | 2025-07-19 | 2025-07-19 | [5 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | ATP App MS |  | 2025-07-24 | 2025-10-08 |  |  | 2025-10-27 | 2025-10-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | Include PO Colo | 2025-10-09 | #NUM! |  |  | 0 |  |  |  | PO Include Colo | CMI Project | CMI
124 | CMI | RLC | Nasional | #NAME? | 2025-07-28 | E3500300 | ID-JI-06465 | DUKUH_KUPANG | 13 | EMA | JAWA TIMUR | Kota Surabaya | Jl. Dukuh Kupang Barat 19 Dukuh Kupang, Surabaya, Jawa Timur | -7.28236 | 112.70929 | 9236.076 | 52 | IOH, XL | Greenfield | SST 4 Legs | Dismantle Tower | Ilham Tirta |  | Active | 2025-07-30 | 2025-08-06 | Expired |  | 2025-08-04 | 2025-07-29 |  | 2025-07-15 |  | 2025-08-17 |  |  |  |  | 2025-08-21 | BAST |  | 2025-08-20 | 2025-08-22 | 2025-08-21 | 2025-11-04 | 2025-11-04 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | 006/TSA-SPH-CMI/VIII/2025 Done Revisi 1 Sept | [6 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | EMAPO25-002237 | 2025-11-21 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JI-15728 | DUKUH PAKIS | -7.28277 | 112.71079
125 | CMI | RLC | Nasional | #NAME? | 2025-07-28 | E3500300 | ID-JI-06465 | DUKUH_KUPANG | 13 | EMA | JAWA TIMUR | Kota Surabaya | Jl. Dukuh Kupang Barat Dukuh Kupang, Surabaya, Jawa Timur | -7.28236 | 112.70929 | 9236.076 | 52 | IOH, XL | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-08-04 | 2025-07-29 |  |  | 2025-08-04 |  |  |  |  | 2025-08-05 |  | ATP App MS |  | 2025-08-20 | 2025-08-22 | 2025-08-21 |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | Include Reloc | 2025-12-10 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JI-15728 | DUKUH PAKIS | -7.28277 | 112.71079
126 | CMI | RLC | Nasional | #NAME? | 2025-07-28 | E3500300 | ID-JI-06465 | DUKUH_KUPANG | 13 | EMA | JAWA TIMUR | Kota Surabaya | Jl. Dukuh Kupang Barat Dukuh Kupang, Surabaya, Jawa Timur | -7.28236 | 112.70929 | 9236.076 | 52 | IOH, XL | Greenfield | SST 4 Legs | Relocation Equipment | Abe Rizal |  | Active | 2025-07-31 | 2025-08-07 | Expired |  | 2025-08-04 | 2025-07-29 | [5 empty] | 2025-08-05 | 2025-08-05 | 2025-08-05 |  | ATP App MS |  | 2025-08-20 | 2025-08-22 | 2025-08-21 | 2025-11-04 | 2025-11-04 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | 006/TSA-SPH-CMI/VIII/2025 Done Revisi 1 Sept | [6 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | EMAPO25-002247 | 2025-12-10 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JI-15728 | DUKUH PAKIS | -7.28277 | 112.71079
127 | CMI | RLC | Nasional | #NAME? | 2025-08-04 | E3300323 | ID-JT-06033 | WIROSARI | 11 | EMA | JAWA TENGAH | Kab. Grobogan | Wirosari, Kabupaten Grobogan, Jawa Tengah | -7.07789 | 111.08836 | 18868.812 |  |  | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2025-08-05 | 2025-08-05 |  |  |  | 2025-08-12 |  |  |  | 2025-08-13 | 2025-08-18 | BAST |  | 2025-08-13 | 2025-08-20 | 2025-08-20 | 2025-09-17 | 2025-10-01 | 2025-10-16 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | Done Revisi 22 Sept | [6 empty] | NY Submit | NY Submit | 2025-08-18 | 2025-08-18 | Dismantle Tower | EMAPO25-002109 | 2025-10-28 | 12 |  |  | 0
128 | CMI | RLC | Nasional | #NAME? | 2025-07-24 | E3600214 | ID-BT-06924 | SUPERMAL | 6 | EMA | BANTEN | Kab. Tangerang | Jl. Boulevard Diponegoro No.105, Bencongan, Kec. Klp. Dua, Kabupaten Tangerang, Banten 15810 | -6.22686 | 106.60578 | 4519.52 |  |  | Rooftop | Pole | Rebuild_LOS Survey 11TGN0458 SUPERMAL_EP to 11TGN0466 PALEM_RATU_RAYA_PL | [5 empty] | NY Submit |  | 2025-08-01 | 2025-10-30 | [7 empty] | 2025-08-11 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | CMIPO25-004481 | 2025-10-13 | 0 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA |  | 11TGR0202 | MARIO_PL
129 | CMI | RLC | Nasional | #NAME? | 2025-08-11 | E3200297 | ID-JB-05252 | CILOTO | 10 | EMA | JAWA BARAT | Kab. Cianjur | Ciloto, Kabupaten Cianjur, Jawa Barat | -6.71249 | 107.00275 | 19733.4 |  | IOH, SF | Greenfield | SST 4 Legs | Dismantle Tower | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-08-12 |  |  |  |  | 2025-08-19 |  |  |  | 2025-08-20 | 2025-08-20 | BAST |  | 2025-08-13 | 2025-09-08 | 2025-08-19 | 2025-09-11 | 2025-09-16 | 2025-09-25 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | EMAPO25-002017 | 2025-10-14 | 19 |  |  | 0 |  |  |  | Payment Invoice | CMI Finance | CMI
130 | CMI | RLC | Nasional | #NAME? | 2025-08-11 | R7400025 | ID-SG-01914 | LASANDARA | 19 | CMI | SULAWESI TENGGARA | Kota Kendari | JL. LASANDARA - KOTA KENDARI, SULAWESI TENGGARA | -3.96497 | 122.52178 | 2435.61 | 18 |  | Greenfield | Monopole | Dismantle Tower | [5 empty] | NY Submit |  | 2025-08-12 | 2025-08-13 |  | 2025-09-02 |  | 2025-09-10 |  |  |  | 2025-10-15 | 2025-10-15 | BAST |  | 2025-09-03 | 2025-09-07 | 2025-09-04 | 2025-09-10 | 2025-09-22 | 2025-09-23 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-13 | 2025-08-13 | JSA No.01/TSA/HSE/08/2025 | 2025-08-13 | 2025-08-20 | SWP-HSE-56 | Approved | Approved | 2025-10-15 |  | Dismantle Tower | CMIPO25-004467 | 2025-10-07 | 14 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
131 | CMI | RLC | Nasional | #NAME? | 2025-08-11 | R7400027 | ID-SG-01916 | RS.KOREM | 19 | CMI | SULAWESI TENGGARA | Kota Kendari | JL.DRS. H. ABD. SILONDAE – JL. SYEH YUSUF (BANK BAHTERAMAS) - KOTA KENDARI, SULAWESI TENGGARA | -3.97033 | 122.51596 | 2435.61 | 18 |  | Greenfield | Monopole | Dismantle Tower | [5 empty] | NY Submit |  | 2025-08-12 | 2025-08-13 |  | 2025-09-02 |  | 2025-09-10 |  |  |  | 2025-10-15 | 2025-10-15 | BAST |  | 2025-09-03 | 2025-09-07 | 2025-09-04 | 2025-09-10 | 2025-09-22 | 2025-09-25 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | Quotation 3 vendor untuk crane | 2025-08-13 | 2025-08-13 | JSA No.02/TSA/HSE/08/2025 | 2025-08-13 | 2025-08-20 | SWP-HSE-57 | Approved | Approved |  |  | Dismantle Tower | CMIPO25-004468 | 2025-10-07 | 12 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
132 | CMI | RLC | Nasional | #NAME? | 2025-08-11 | R7400028 | ID-SG-01917 | BALAIKOTA | 19 | CMI | SULAWESI TENGGARA | Kota Kendari | JL. DRS. H ABD SILONDAE(BUNDARAN MTQ)- KOTA KENDARI, SULAWESI TENGGARA | -3.97441 | 122.51416 | 2435.61 | 18 |  | Greenfield | Monopole | Dismantle Tower | [5 empty] | NY Submit |  | 2025-08-12 | 2025-08-13 |  | 2025-09-02 |  | 2025-09-10 |  |  |  | 2025-10-15 | 2025-10-15 | BAST |  | 2025-09-03 | 2025-09-07 | 2025-09-04 | 2025-09-10 | 2025-09-22 | 2025-09-25 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | Quotation 3 vendor untuk crane | 2025-08-13 | 2025-08-13 | JSA No.03/TSA/HSE/08/2025 | 2025-08-13 | 2025-08-20 | SWP-HSE-58 | Approved | Approved |  |  | Dismantle Tower | CMIPO25-004469 | 2025-10-07 | 12 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
133 | CMI | RLC | Nasional | #NAME? | 2025-08-11 | E3600042 | ID-BT-06755 | TOL_CILEGON_SERANG | 6 | EMA | BANTEN | Kab. Serang | TOL MERAK SERANG, BLOK AMBON KEL. TERATE, KEC. KRAMATWATU, KAB. SERANG | -6.01744 | 106.08647 | 16015.06 | 55 |  | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2025-08-15 | 2025-08-15 |  |  |  | 2025-09-15 |  |  |  |  | 2025-09-17 | BAST |  | 2025-09-04 | 2025-10-07 |  | 2025-11-04 | 2025-11-04 | 2025-09-09 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 001/TSA‐SPH‐CMI/IX/2025 | 2025-08-15 | 2025-04-28 | JSA No.04/TSA/HSE/08/2025 | 2025-08-15 | 2025-04-30 |  | Approved | Approved | 2025-09-18 | 2025-10-07 | Dismantle Tower | EMAPO25-002239 | 2025-11-21 | 73 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
134 | CMI | RLC | Nasional | #NAME? | 2025-08-11 | E3600042 | ID-BT-06755 | TOL_CILEGON_SERANG | 6 | EMA | BANTEN | Kab. Serang | TOL MERAK SERANG, BLOK AMBON KEL. TERATE, KEC. KRAMATWATU, KAB. SERANG | -6.01744 | 106.08647 | 16015.06 | 55 |  | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-08-15 | 2025-08-15 |  |  | 2025-09-08 |  |  |  |  | 2025-09-09 |  | ATP App MS |  | 2025-09-04 | 2025-10-07 |  |  | 2025-11-04 | 2025-09-09 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-15 | 2025-04-28 | JSA No.04/TSA/HSE/08/2025 | 2025-08-15 | 2025-04-30 |  | Approved | Approved | 2025-10-21 | 2025-10-21 | Dismantle Equipment | Include Reloc | 2025-11-21 | 73 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
135 | CMI | RLC | Nasional | #NAME? | 2025-08-11 | E3600042 | ID-BT-06755 | TOL_CILEGON_SERANG | 6 | EMA | BANTEN | Kab. Serang | TOL MERAK SERANG, BLOK AMBON KEL. TERATE, KEC. KRAMATWATU, KAB. SERANG | -6.01744 | 106.08647 | 16015.06 | 55 |  | Greenfield | SST 4 Legs | Relocation Equipment | Abe Rizal |  |  |  |  | NY Submit |  | 2025-08-15 | 2025-08-15 | [5 empty] | 2025-09-09 | 2025-09-09 | 2025-09-09 |  | ATP App MS |  | 2025-09-04 | 2025-10-07 |  |  | 2025-11-04 | 2025-09-09 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-15 | 2025-04-28 | JSA No.04/TSA/HSE/08/2025 | 2025-08-15 | 2025-04-30 |  | Approved | Approved | 2025-10-21 | 2025-10-21 | Relocation Equipment | EMAPO25-002242 | 2025-11-21 | 73 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA |  | ID-BT-16193 | BOJONEGARA SERANG | -6.01866 | 106.08698 | CR-20250825-00000042
136 | CMI | RLC | Nasional | #NAME? | 2025-08-11 | E3600042 | ID-BT-06755 | TOL_CILEGON_SERANG | 6 | EMA | BANTEN | Kab. Serang | TOL MERAK SERANG, BLOK AMBON KEL. TERATE, KEC. KRAMATWATU, KAB. SERANG | -6.01744 | 106.08647 | 16015.06 | 55 |  | Greenfield | SST 4 Legs | Rebuild_LOS Survey JAW-BT-SRG-1198 BOJONEGARA_SERANG to JAW-BT-SRG-0833 TERATE BOJONEGARA | [5 empty] | NY Submit |  | 2025-08-24 | 2025-08-24 | [7 empty] | 2025-10-15 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  | 2025-10-15 | Rebuild_LOS Survey | EMAPO25-002021 | 2025-10-14 | 0 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA |  | JAW-BT-SRG-0833 | TERATE BOJONEGARA | -6.004039 | 106.089411
137 | CMI | RLC | Nasional | #NAME? | 2025-08-15 | R3270701 | ID-JB-02531 | SITE BOBOS | 10 | CMI | JAWA BARAT | Kab. Cirebon | Cikalahang, Kabupaten Cirebon, Jawa Barat | -6.77656 | 108.4096 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Dismantle Tower | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-08-24 | 2025-08-26 |  | 2025-10-18 |  | 2025-12-01 |  |  |  | 2025-12-03 | 2025-12-03 | BAST | 1-32 & 39 – 49.5 m (CMI konfirm center 49.5m sesuai ketinggian eksisting tersedia) | 2025-11-17 | 2025-11-19 | 2025-11-18 |  | 2025-11-24 | 2025-11-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 003/TSA-SPH-CMI/XI/2025 | 2025-08-28 | 2025-09-10 | JSA No.08/TSA/HSE/08/2025 | 2025-08-29 | 2025-09-02 | SWP-HSE-62 | Approved | Approved | 2025-12-03 | 2025-12-03 | Dismantle Tower | CMIPO25-005424 | 2025-12-09 | 12 |  |  | 0 |  |  |  | Complete |  |  |  | E3200633 | BOBOS | -6.77657 | 108.4098
138 | CMI | RLC | Nasional | #NAME? | 2025-08-15 | R3270701 | ID-JB-02531 | SITE BOBOS | 10 | CMI | JAWA BARAT | Kab. Cirebon | Cikalahang, Kabupaten Cirebon, Jawa Barat | -6.77656 | 108.4096 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Dismantle Equipment | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-08-24 | 2025-08-26 |  |  | 2025-11-27 | [6 empty] | Dismantle Perangkat | 05.12.25 KWH PLN geser ke new site | 2025-11-17 | 2025-11-19 | 2025-11-18 |  | 2025-11-24 | 2025-11-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-28 | 2025-09-10 | JSA No.08/TSA/HSE/08/2025 | 2025-08-29 | 2025-09-02 |  | Approved | Approved | 2026-03-06 | 2026-03-06 | Dismantle Equipment | Include Reloc | 2025-12-12 | 15 |  |  | 0 |  |  |  | Complete |  |  |  | E3200633 | BOBOS | -6.77657 | 108.4098
139 | CMI | RLC | Nasional | #NAME? | 2025-08-15 | R3270701 | ID-JB-02531 | SITE BOBOS | 10 | CMI | JAWA BARAT | Kab. Cirebon | Cikalahang, Kabupaten Cirebon, Jawa Barat | -6.77656 | 108.4096 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Relocation Equipment | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-08-24 | 2025-08-26 | [5 empty] | 2025-11-28 | 2025-11-28 | 2026-03-06 | 2026-03-06 | ATP App MS | 05.12.25 KWH PLN geser ke new site | 2025-11-17 | 2025-11-19 | 2025-11-18 |  | 2025-11-24 | 2025-11-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-28 | 2025-09-10 | JSA No.08/TSA/HSE/08/2025 | 2025-08-29 | 2025-09-02 |  | Approved | Approved | 2026-03-06 | 2026-03-06 | Relocation Equipment | EMAPO25-002332 | 2025-12-12 | 15 |  |  | 0 |  |  |  | Complete |  |  |  | E3200633 | BOBOS | -6.77657 | 108.4098 |  | XLWO-20251106-00001697 XLWO-20251106-00001701
140 | CMI | RLC | Nasional | #NAME? | 2025-08-12 | E7400025 | ID-SG-07834 | ISAT_KENDARI | 19 | EMA | SULAWESI TENGGARA | Kota Kendari | Jl. Drs. H. Abdullah Silondae, Mandonga, Kec. Mandonga, Kota Kendari, Sulawesi Tenggara | -3.96917 | 122.51697 |  |  |  | Rooftop | Pole | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-08-17 | 2025-08-17 |  |  | 2025-08-19 |  |  |  |  | 2025-08-19 |  | ATP App MS |  | 2025-08-20 | 2025-08-21 |  |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0 |  |  |  | PO NY Release (proses E Memo CMI) | CMI Project | CMI
141 | CMI | RLC | Nasional | #NAME? | 2025-08-12 | E7400025 | ID-SG-07834 | ISAT_KENDARI | 19 | EMA | SULAWESI TENGGARA | Kota Kendari | Jl. Drs. H. Abdullah Silondae, Mandonga, Kec. Mandonga, Kota Kendari, Sulawesi Tenggara | -3.96917 | 122.51697 |  |  |  | Rooftop | Pole | Relocation Equipment | [5 empty] | NY Submit |  | 2025-08-17 | 2025-08-17 | [5 empty] | 2025-08-19 | 2025-08-19 |  |  | OA/RFS |  | 2025-08-20 | 2025-08-21 |  |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0 |  |  |  | PO NY Release (proses E Memo CMI) | CMI Project | CMI
142 | CMI | RLC | Nasional | #NAME? | 2025-08-19 | R5100062 | ID-BA-00446 | SMPK_THOMAS_AQUINO | 16 | CMI | BALI | Kab. Badung | BANJAR BABAKAN DESA CANGGU KEC.KUTA UTARA KAB.BADUNG | -8.62888 | 115.15247 | 1193.68 | 12 |  | Rooftop | pole | Dismantle Tower |  |  | Dismantle | 2025-10-12 | 2025-10-18 | Expired |  | 2025-08-22 | 2025-08-22 |  | 2025-09-17 |  | 2025-10-21 |  |  |  |  | 2025-10-27 | BAST |  | 2025-10-09 | 2025-11-12 |  | 2025-12-09 | 2025-12-09 | 2025-12-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 10.11.25 upload revisi 006/TSA-SPH-CMI/X/2025 | 2025-08-23 | 2025-08-27 | JSA No.05/TSA/HSE/08/2025 | 2025-08-26 | 2025-08-29 | SWP-HSE-60 | Approved | Approved | 2025-11-04 | 2025-11-04 | Dismantle Tower | CMIPO25-005744 | 2025-12-31 | 19 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
143 | CMI | RLC | Nasional | #NAME? | 2025-08-19 | R5100062 | ID-BA-00446 | SMPK_THOMAS_AQUINO | 16 | CMI | BALI | Kab. Badung | BANJAR BABAKAN DESA CANGGU KEC.KUTA UTARA KAB.BADUNG | -8.62888 | 115.15247 | 1193.68 | 12 |  | Rooftop | pole | Dismantle Equipment |  |  | Dismantle | 2025-10-12 | 2025-10-18 | Expired |  | 2025-08-22 | 2025-08-22 |  |  | 2025-10-21 |  | 2025-10-12 |  |  | 2025-10-12 |  | ATP App MS | 12.10.25 done inbound | 2025-10-09 | 2025-11-12 |  |  | 2025-12-09 | 2025-12-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-23 | 2025-08-27 | JSA No.05/TSA/HSE/08/2025 | 2025-08-26 |  |  | Approved | Submit | 2025-11-04 | 2025-11-04 | Dismantle Equipment | Include Dism Tower | 2025-12-31 | 19 |  |  | 0 |  |  |  | SPH Delivery roaster | Prayudi | TSA
144 | CMI | RLC | Nasional | #NAME? | 2025-08-19 | E3200525 | ID-JB-05480 | GEDUNG_LIPPO | 10 | EMA | JAWA BARAT | Kota Bandung | JL. GATOT SUBROTO NO.2, MALABAR | -6.92289 | 107.61799 | 182.92 | 3 |  | Rooftop | Pole | Dismantle Tower | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-08-23 | 2025-08-24 |  |  |  | 2025-09-11 |  |  |  | 2025-09-11 | 2025-09-11 | BAST |  | 2025-09-09 | 2025-11-06 | 2025-09-09 |  | 2025-11-06 | 2025-11-10 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-23 | 2025-08-26 | JSA No.07/TSA/HSE/08/2025 |  |  |  | Approved | NY Submit |  |  | Dismantle Tower | EMAPO25-002204 | 2025-11-13 | 3 |  |  | 0 |  |  |  | Complete | [7 empty] | CR-20250909-00000434
145 | CMI | RLC | Nasional | #NAME? | 2025-08-19 | E3200525 | ID-JB-05480 | GEDUNG_LIPPO | 10 | EMA | JAWA BARAT | Kota Bandung | JL. GATOT SUBROTO NO.2, MALABAR | -6.92289 | 107.61799 | 182.92 | 3 |  | Rooftop | Pole | Dismantle Equipment | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-08-23 | 2025-08-24 |  |  | 2025-09-11 | [6 empty] | Dismantle Perangkat | Material in WH TSA | 2025-09-09 | 2025-11-06 | 2025-09-09 |  | 2025-11-06 | 2025-11-10 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-08-23 | 2025-08-26 | JSA No.07/TSA/HSE/08/2025 | 2025-08-25 | 2025-08-27 | SWP-HSE-59 | Approved | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2025-11-13 | 3 |  |  | 0 |  |  |  | Complete | [7 empty] | CR-20250909-00000434
146 | CMI | RLC | Nasional | #NAME? | 2025-08-19 | E3200525 | ID-JB-05480 | GEDUNG_LIPPO | 10 | EMA | JAWA BARAT | Kota Bandung | JL. GATOT SUBROTO NO.2, MALABAR | -6.92289 | 107.61799 | 182.92 | 3 |  | Rooftop | Pole | Relocation Equipment to R3270874 PAKUHAJI WETAN NGAMPRAH | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-08-23 | 2025-08-24 | [9 empty] | Survey Report |  | 2026-01-16 | 2026-02-09 |  | 2026-04-02 |  |  | BAN App | [6 empty] | NY Submit |  | 2025-08-23 | 2025-08-26 | JSA No.07/TSA/HSE/08/2025 | 2025-08-25 |  |  | Approved | Submit |  |  | Relocation Equipment | CMIPO26-001696 | 2026-05-20 | 0 |  |  | 0 |  |  |  | OG 1 sector PO need reset reloc all sector |  | CMI
147 | CMI | RLC | Nasional | #NAME? | 2025-08-19 | E3100485 | ID-JK-04882 | PEDONGKELAN | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Utara | KBN MARUNDA BLOK C3-2.1, KEL. MARUNDA, KEC. CILINCING, JAKARTA UTARA | -6.11436 | 106.94512 | 8487.28 | 42 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  |  | 2026-04-15 | 2026-04-21 | Expired |  | 2025-08-22 | 2025-08-23 |  | 2026-03-13 |  | 2026-04-25 |  |  |  |  | 2026-04-26 | BAST |  | 2026-01-08 | 2026-01-14 | 2026-01-08 |  | 2026-04-07 | 2026-04-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 30.04.26 DRM | 2025-08-22 | 2025-08-26 | JSA No.06/TSA/HSE/08/2025 | 2025-08-26 | 2025-08-27 | SWP-HSE-61 | Approved | Approved | 2026-04-28 | 2026-04-29 | Dismantle Tower | EMAPO26-000075 | 2026-01-30 | #NUM! |  |  | 0 |  |  |  | Complete | Prayudi | TSA
148 | CMI | RLC | Nasional | #NAME? | 2025-08-19 | E3100485 | ID-JK-04882 | PEDONGKELAN | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Utara | KBN MARUNDA BLOK C3-2.1, KEL. MARUNDA, KEC. CILINCING, JAKARTA UTARA | -6.11436 | 106.94512 | 8487.28 | 42 | - | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-08-22 | 2025-08-23 |  | 2026-03-13 | 2026-04-23 | [6 empty] | Dismantle Perangkat |  | 2026-01-08 | 2026-01-14 | 2026-01-08 |  | 2026-04-07 | 2026-04-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 30.04.26 DRM | 2025-08-22 | 2025-08-26 | JSA No.06/TSA/HSE/08/2025 | 2025-08-26 | 2025-08-27 |  | Approved | Approved |  |  | Dismantle Equipment | Include Reloc | 2026-01-30 | #NUM! |  |  | 0 |  |  |  | 06.05.26 ATP IOH full sign 28.04.26 ATP Submit to RTS Hwei XLS 06.05.26 ATP submit sign NOP TSEL | CMI Project | TSA | [7 empty] | CRQ000001106230
149 | CMI | RLC | Nasional | #NAME? | 2025-08-19 | E3100485 | ID-JK-04882 | PEDONGKELAN | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Utara | KBN MARUNDA BLOK C3-2.1, KEL. MARUNDA, KEC. CILINCING, JAKARTA UTARA | -6.11436 | 106.94512 | 8487.28 | 42 |  | Greenfield | SST 4 Legs | Relocation Equipment | [5 empty] | NY Submit |  | 2025-08-22 | 2025-08-23 |  | 2026-03-13 |  |  |  | 2026-04-24 | 2026-04-26 |  |  | OA/RFS | 26.04.26 XLS sign ATP | 2026-01-08 | 2026-01-14 | 2026-01-08 |  | 2026-04-07 | 2026-04-14 | 1st BOQ App on ISAAC | 2026-04-28 |  |  | 2026-05-07 |  | 2026-05-08 | 2nd BOQ App on ISAAC | 30.04.26 DRM | 2025-08-22 | 2025-08-26 | JSA No.06/TSA/HSE/08/2025 | 2025-08-26 | 2025-08-27 |  | Approved | Approved |  |  | Relocation Equipment | EMAPO26-000080 | 2026-01-30 | #NUM! | EMAPO26-000641 | 2026-05-29 | 21 |  |  |  | 06.05.26 ATP IOH full sign 28.04.26 ATP Submit to RTS Hwei XLS 06.05.26 ATP submit sign NOP TSEL | CMI Project | TSA |  | ID-JK-13069 | MARUNDA CILINCING |  |  | CR-20260417-00000605 CR-20260418-00000026 | NO XLWO | CRQ000001106230
150 | CMI | RLC | Nasional | #NAME? | 2025-08-20 | E3300214 | ID-JT-05924 | SALATIGA_SLT | 11 | EMA | JAWA TENGAH | Kota Salatiga | JL. KUMPUL REJO RT.006/03, KEL. GENDONGAN - SALATIGA SELATAN | -7.33688 | 110.509 | 13032.3 | 52 | IOH, XL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-05-11 | 2026-05-17 | Expired |  | 2026-05-12 | 2026-05-22 | 2026-08-17 | [8 empty] | Survey Report |  | 2026-07-24 |  | 2026-07-27 |  |  |  | Engineering Structural Manager App |  |  |  | DRM |  |  | need DRM | Reinstall Genset & Pondasi di 2nd BOQ | 2026-07-09 | 2026-07-23 | JSA No.41/TSA/HSE/07/2026 | 2026-07-09 | 2026-07-15 | SWP-HSE-141 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0 |  |  |  | Waiting Survey | Alfan | TSA
151 | CMI | RLC | Nasional | #NAME? | 2025-08-20 | E3300214 | ID-JT-05924 | SALATIGA_SLT | 11 | EMA | JAWA TENGAH | Kota Salatiga | JL. KUMPUL REJO RT.006/03, KEL. GENDONGAN - SALATIGA SELATAN | -7.33688 | 110.509 | 13032.3 | 52 |  | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2026-05-11 | 2026-05-17 | Expired |  | 2026-05-12 | 2026-05-22 | 2026-08-17 | [8 empty] | Survey Report |  | 2026-07-24 |  | 2026-07-27 |  |  |  | Engineering Structural Manager App |  |  |  | DRM |  |  | need DRM | Reinstall Genset & Pondasi di 2nd BOQ | 2026-07-09 | 2026-07-23 |  | 2026-07-09 | 2026-07-15 |  | Approved | Approved |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0 |  |  |  | Waiting Survey | Alfan | TSA
152 | CMI | RLC | Nasional | #NAME? | 2025-08-20 | E3300214 | ID-JT-05924 | SALATIGA_SLT | 11 | EMA | JAWA TENGAH | Kota Salatiga | JL. KUMPUL REJO RT.006/03, KEL. GENDONGAN - SALATIGA SELATAN | -7.33688 | 110.509 | 13032.3 | 52 | IOH, XL | Greenfield | SST 4 Legs | Relocation Equipment |  |  | Survey | 2026-05-11 | 2026-05-17 | Expired |  | 2026-05-12 | 2026-05-22 | 2026-08-17 | [8 empty] | Survey Report |  | 2026-07-24 |  | 2026-07-27 |  |  |  | Engineering Structural Manager App |  |  |  | DRM |  |  | need DRM | Reinstall Genset & Pondasi di 2nd BOQ | [6 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0 |  |  |  | Waiting Survey | Alfan | TSA
153 | CMI | RLC | Nasional | #NAME? | 2025-08-28 | E3300288 | ID-JT-05998 | PR KUDUS | 11 | EMA | JAWA TENGAH | Kab. Kudus | Jati Wetan, Kabupaten Kudus, Jawa Tengah | -6.83577 | 110.82246 | 322.3845 |  |  | Greenfield | Mobile Combat | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-08-30 |  |  |  | 2025-09-16 |  |  |  |  | 2025-09-18 |  | ATP App MS |  | 2025-09-02 | 2025-10-09 |  |  | 2025-11-06 | 2025-11-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  |  |  | JSA No.01/TSA/HSE/09/2025 |  |  |  | NY Submit | NY Submit | 2025-09-18 | 2025-10-03 | Dismantle Equipment | Include Reloc | 2025-12-16 | 40 |  |  | 0 |  |  |  | Complete | TSA |  |  |  |  | -6.83704 | 110.82167
154 | CMI | RLC | Nasional | #NAME? | 2025-08-28 | E3300288 | ID-JT-05998 | PR KUDUS | 11 | EMA | JAWA TENGAH | Kab. Kudus | Jati Wetan, Kabupaten Kudus, Jawa Tengah | -6.83577 | 110.82246 | 322.3845 |  |  | Greenfield | Mobile Combat | Relocation Equipment | Abe Rizal |  |  |  |  | NY Submit |  | 2025-08-30 | [6 empty] | 2025-09-17 | 2025-09-17 | 2025-09-18 |  | ATP App MS |  | 2025-09-02 | 2025-10-09 |  | 2025-11-04 | 2025-11-06 | 2025-11-06 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 001/TSA‐SPH‐CMI/IX/2025 |  |  | JSA No.01/TSA/HSE/09/2025 |  |  |  | NY Submit | NY Submit | 2025-09-18 | 2025-10-03 | Relocation Equipment | EMAPO25-002338 | 2025-12-16 | 40 |  |  | 0 |  |  |  | Complete | TSA |  |  |  |  | -6.83704 | 110.82167
155 | CMI | RLC | Nasional | #NAME? | 2025-09-03 | E3500376 | ID-JI-06541 | MANYAR_TIRTOYOSO | 13 | EMA | JAWA TIMUR | Kota Surabaya | JL.KARTIKA, MANYAR TIRTOYOSO SURABAYA | -7.28906 | 112.766 | 5987.15 | 30 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey |  |  | NY Submit |  | 2025-09-03 | 2025-09-15 |  | 2025-09-29 |  | 2025-10-10 |  |  |  | 2025-10-11 | 2025-10-11 | BAST |  | 2025-10-09 | 2026-01-26 | 2025-10-10 |  | 2026-01-27 | 2026-01-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-09-15 | 2025-09-16 | JSA No.02/TSA/HSE/09/2025 | 2025-09-15 | 2025-09-16 | SWP-HSE-65 | Approved | Approved | 2025-10-13 | 2025-10-17 | Dismantle Tower | EMAPO26-000118 | 2026-02-06 | 10 |  |  | 0 |  |  |  | Complete
156 | CMI | RLC | Nasional | #NAME? | 2025-03-19 | E3500148 | ID-JI-06316 | KEDUNGPRING | 15 | EMA | JAWA TIMUR | Kab. Lamongan | DESA TELANAK, KEC. KEDUNGPRING, KAB. LAMONGAN | -7.17095 | 112.198 | 18868.81 | 70 | XL | Greenfield | SST 4 Legs | Rebuild_LOS Survey JAW-JI-LMG-4290 KEDUNGPRING TLANAK (NE) to JAW-JI-LMG-4254 KEDUNGPRING NGLEBUR (FE) | [5 empty] | NY Submit |  | 2025-09-09 | 2025-09-09 | [7 empty] | 2025-09-12 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit |  |  |  | JSA No.10/TSA/HSE/04/2025 |  |  |  | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO25-002021 | 2025-10-14 | 0 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA |  | JAW-JI-LMG-4254 | KEDUNGPRING NGLEBUR | -7.184972 | 112.231472
157 | CMI | RLC | Nasional | #NAME? | 2025-09-08 | E3500352 | ID-JI-06517 | KAYOON_OFFICE | 15 | EMA | JAWA TIMUR | Kota Surabaya | Jl. Kayoon No.72, Embong Kaliasin, Kec. Genteng, Surabaya, Jawa Timur 60271 | -7.271732 | 112.744267 | 24838.144 | 120 | IOH | Greenfield | SST 4 Legs | Cutting Tower from 120 to 72m | Rizky | +62 896-9522-7013 | Dismantle Tower | 2026-01-13 | 2026-01-20 | Expired |  | 2025-08-22 | 2025-09-15 |  |  |  | 2026-05-04 |  |  |  |  | 2026-05-04 | BAST | 28.10.25 Start cutting tower 03.05.26 Finish cutting tower | 2025-09-09 |  |  | 2025-09-10 | 2025-10-01 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-09-15 | 2025-09-16 | JSA No.04/TSA/HSE/09/2025 | 2025-09-15 | 2025-09-16 | SWP-HSE-63 | Approved | Approved |  |  | Dismantle Tower | EMAPO25-002290 | 2025-12-01 | 0 |  |  | 0 |  |  |  | Complete |  | TSA
158 | CMI | RLC | Nasional | #NAME? | 2025-09-09 | E3300285 | ID-JT-05995 | JAYENGAN | 11 | EMA | JAWA TENGAH | Kota Surakarta | JL YOS SUDARSO NO 280 KELURAHAN KRATONAN, KECAMATAN SERENGAN, KOTA SURAKARTA PROPINSI JAWA TENGAH | -7.58174 | 110.82 | 773.94 | 6 |  | Rooftop | Pole | Dismantle Tower | abe / Yasir |  | Dismantle | 2025-11-04 | 2025-11-10 | Expired |  | 2025-09-23 | 2025-09-24 |  |  |  | 2025-11-10 |  |  |  |  | 2025-11-11 | BAST |  | 2025-11-17 | 2025-12-09 | 2025-11-18 | 2025-01-06 | 2025-12-09 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 18.11.25 Item mounting belum ada di boq 014/TSA-SPH-CMI/X/2025 | 2025-09-24 | 2025-09-26 | JSA No.06/TSA/HSE/09/2025 | 2025-09-24 | 2025-09-29 | SWP-HSE-68 | Approved | Approved | 2025-11-13 |  | Dismantle Tower | EMAPO26-000077 | 2026-01-30 | 18 |  |  | 0 |  |  |  | NY Pass TI | CMI Project | CMI
159 | CMI | RLC | Nasional | #NAME? | 2025-09-09 | R3580015 | ID-JI-00474 | KALI PECABEAN | 15 | CMI | JAWA TIMUR | Kab. Sidoarjo | KALIPECABEAN RT.06/02 DESA KALIPECABEAN KECAMATAN CANDI SIDOARJO JAWA TIMUR | -7,48268 | 112,74091 | 6159 | 42 |  | Greenfield | SST 4 Legs | Dismantle Tower | Ranu / Diki |  | Survey |  |  | NY Submit |  | 2025-09-11 | 2025-09-12 |  | 2025-09-29 |  | 2025-10-13 |  |  |  |  | 2025-10-13 | BAST |  | 2025-10-09 | 2025-10-20 |  | 2025-11-28 | 2025-12-05 | 2025-12-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 002/TSA-SPH-CMI/X/2025 | 2025-09-12 | 2025-09-12 | JSA No.03/TSA/HSE/09/2025 | 2025-09-15 | 2025-09-17 | SWP-HSE-64 | Approved | Approved | 2025-10-14 | 2025-10-20 | Dismantle Tower | CMIPO25-005580 | 2025-12-17 | 12 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
160 | CMI | RLC | Nasional | #NAME? | 2025-09-09 | R3350009 | ID-JT-00469 | KAROWELANG | 11 | CMI | JAWA TENGAH | Kab. Kebumen | DUSUN JURUTENGAH RT 04 RW 02, KEL/DESA KABUARAN, KEC. PREMBUN, KAB.KEBUMEN, JAWA TENGAH | -7,67228 | 109,78598 | 9996 |  |  | Greenfield |  | Dismantle Tower | abe / Yasir |  | Dismantle | 2025-10-28 | 2025-11-04 | Expired |  | 2025-09-25 | 2025-09-25 |  | 2025-10-08 |  | 2025-11-01 |  |  |  | 2025-11-01 | 2025-11-01 | BAST | start work 28-10-25 | 2025-10-28 | 2025-11-12 | 2025-10-30 | 2025-11-28 | 2025-12-01 | 2025-12-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 012/TSA-SPH-CMI/X/2025 | 2025-09-25 | 2025-09-26 | JSA No.08/TSA/HSE/09/2025 | 2025-09-25 | 2025-09-29 | SWP-HSE-69 | Approved | Approved | 2025-11-05 | 2025-11-05 | Dismantle Tower | CMIPO25-005575 | 2025-12-17 | 12 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
161 | CMI | RLC | Nasional | #NAME? | 2025-06-23 | E3600061 | ID-BT-06774 | PARUNGSARI | 6 | EMA | BANTEN | Kab. Lebak | JL. RAYA CIPANAS KP. CURUNG PASIR | -6.36815 | 106.283 | 22120.78 | 70 | SF | Greenfield | SST 4 Legs | Rebuild_LOS Survey ZJKT2_6397_PARUNGSARI 2 to ZJKT2_4032 SF_Rangkas Bitung_Corp | [5 empty] | NY Submit |  | 2025-08-14 | 2025-09-09 | [7 empty] | 2025-09-12 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO25-002021 | 2025-10-14 | 0 |  |  | 0 |  |  |  | Complete | Lifi | TSA |  | ZJKT2_4032 | SF_Rangkas Bitung_Corp | -6.34323 | 106.23833
162 | CMI | RLC | Nasional | #NAME? | 2025-09-10 | R3580803 | ID-JI-10052 | Trosobo Minaret | 15 | CMI | JAWA TIMUR | Kab. Sidoarjo | Masjid Al Ikhlash Wisma Trosobo, Kec. Taman, Kab. Sidoarjo (Cp : H. M. Ridwan), Propinsi Jawa Timur | -7.37508 | 112.643 | 3713.64 | 25 |  | Greenfield | Minaret | Dismantle Tower | Ranu / Diki |  | Survey |  |  | NY Submit |  | 2025-09-15 | 2025-09-16 |  |  |  | 2025-10-18 |  |  |  | 2025-10-20 | 2025-10-20 | BAST | Dismantle Mounting only | 2025-12-12 | 2025-12-19 | 2025-12-12 |  | 2025-12-19 | 2025-12-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-09-16 | 2025-09-19 | JSA No.05/TSA/HSE/09/2025 | 2025-09-16 | 2025-09-22 | SWP-HSE-66 | Approved | Approved | 2025-10-20 | 2025-10-20 | Dismantle Tower | CMIPO25-005751 | 2025-12-31 | 12 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
163 | CMI | RLC | Nasional | #NAME? | 2025-09-12 | R5200035 | ID-NB-03032 | PEMENANG BARAT | 16 | CMI | NUSA TENGGARA BARAT | Kab. Lombok Utara | TEBANGO DESA PEMENANG BARAT KECAMATAN TANJUNG, KAB LOMBOK BARAT | -8.4072 | 116.105 | 6828.53 | 51 |  | Greenfield | SST 4 Legs | Dismantle Tower | abe / Yasir |  | Dismantle | 2026-01-11 | 2026-01-18 | Expired |  | 2025-09-23 | 2025-09-24 |  | 2025-10-01 |  | 2026-01-23 |  |  |  | 2026-01-23 | 2026-01-23 | BAST | 16.01.26 Start dismantle | 2025-12-12 | 2026-01-12 | 2025-12-12 |  | 2026-01-12 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-09-24 | 2025-09-26 | JSA No.07/TSA/HSE/09/2025 | 2025-09-24 | 2025-09-29 | SWP-HSE-67 | Approved | Approved | 2026-01-26 | 2026-01-27 | Dismantle Tower | CMIPO26-000313 | 2026-01-30 | 18 |  |  | 0 |  |  |  | FAC Submit | Lifi | TSA
164 | CMI | RLC | Nasional | #NAME? | 2025-09-12 | E5300006 | ID-NT-07093 | V_LEMBOR | 16 | EMA | NUSA TENGGARA TIMUR | Kab. Manggarai | JL. MELAWAR-NANGLILI RT 11 RW 06, KEL. TANGGE, KEC. LEMBOR, KAB. MANGGARAI BARAT | -8.70902 | 120.17 | 22120.78 | 72 |  | Greenfield | SST 4 Legs | Dismantle Tower | abe / Yasir |  | Survey | 2026-04-16 | 2026-04-22 | Expired |  | 2025-09-24 | 2025-09-25 |  |  |  | 2026-04-25 |  |  |  | 2026-04-28 | 2026-04-28 | BAST | 20.04.26 Start dismantle | 2026-03-31 | 2026-04-02 | 2026-04-06 | DRM | 2026-04-06 | 2026-04-06 | 1st BOQ App on ISAAC | 2026-04-16 | 2026-04-29 |  | 2026-05-05 | 2026-05-11 | 2026-05-12 | 2nd BOQ App on ISAAC | 30.04.26 DRM | 2025-09-25 | 2025-09-29 | JSA No.09/TSA/HSE/09/2025 | 2025-09-25 | 2025-09-29 | SWP-HSE-70 | Approved | Approved | 2026-04-28 | 2026-04-28 | Dismantle Tower | EMAPO26-000483 | 2026-04-14 | 8 | EMAPO26-000640 |  | 85
165 | CMI | RLC | Nasional | #NAME? | 2025-09-22 | R3580804 | ID-JI-10043 | Jalan Ahmad Yani | 13 | CMI | JAWA TIMUR | Kota Surabaya | Ruko MBC (Depan Kantor Bulog), Jl. Jendral Ahmad Yani No. 151 Kav 13, Kel. Jemur Wonosari, Kec. Wonocolo, Kota Surabaya, Propinsi Jawa Timur | -7.32774 | 112.732 | 302.0175 | 6 | SF | Rooftop | pole | Dismantle Tower | Kusmana |  | Survey | 2025-11-12 | 2025-11-26 | Expired |  | 2025-10-09 | 2025-10-09 |  |  |  | 2025-11-17 |  |  |  | 2025-11-19 | 2025-11-19 | BAST |  | 2025-11-11 | 2026-01-12 | 2026-01-08 |  | 2026-01-12 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-09 | 2025-10-10 | JSA No.11/TSA/HSE/09/2025 | 2025-10-09 | 2025-10-10 | SWP-HSE-71 | Approved | Approved | 2025-11-19 | 2025-11-20 | Dismantle Tower | CMIPO26-000312 | 2026-01-30 | 18 |  |  | 0 |  |  |  | FAC Submit | Lifi | TSA
166 | CMI | RLC | Nasional | #NAME? | 2025-09-16 | E3200303 | ID-JB-05258 | DADANG_BEKASI | 10 | EMA | JAWA BARAT | Kota Bekasi | JL. MELATI RAYA 2 RT.006/01, KEL. BEKASI JAYA, BEKASI TIMUR | -6.24619 | 107.01023 |  |  | Tsel | Greenfield | SST 4 Legs | Dismantle Equipment (BTS Only) | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-09-18 |  |  |  | 2025-10-10 |  |  |  |  | 2025-10-21 |  | ATP App MS |  | 2025-09-30 | 2025-10-07 | 2025-10-08 |  | 2025-10-08 | 2025-10-08 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | Include PO Colo | 2025-10-17 | 9 |  |  | 0 |  |  |  | Include PO Colo | CMI Project | CMI
167 | CMI | RLC | Nasional | #NAME? | 2025-09-16 | E3200303 | ID-JB-05258 | DADANG_BEKASI | 10 | EMA | JAWA BARAT | Kota Bekasi | JL. MELATI RAYA 2 RT.006/01, KEL. BEKASI JAYA, BEKASI TIMUR | -6.24619 | 107.01023 |  |  | Tsel | Greenfield | SST 4 Legs | Relocation Equipment (BTS Only) | Taufik Hidayat |  |  |  |  | NY Submit |  | 2025-09-18 | [6 empty] | 2025-10-10 | 2025-10-10 | 2025-10-21 | 2025-10-21 | ATP App MS |  | 2025-09-30 | 2025-10-07 | 2025-10-08 |  | 2025-10-08 | 2025-10-08 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | Include PO Colo | 2025-10-17 | 9 |  |  | 0 |  |  |  | Include PO Colo | CMI Project | CMI | [7 empty] | CRQ000001033976
168 | CMI | RLC | Nasional | #NAME? | 2025-09-29 | E1200351 | ID-KR-04104 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2 | EMA | KEPULAUAN RIAU | Kota Batam | JL. IMAM BONJOL - NAGOYA/KOMP. NAGOYA DANA GRAHA NAGOYA | 1.14898 | 104.00901 | 1488.16 | 7 |  | Rooftop | pole | Dismantle Tower | [5 empty] | NY Submit |  | 2025-10-11 | 2025-10-11 |  | 2025-10-13 |  | 2025-10-27 |  |  |  | 2025-11-04 | 2025-11-04 | BAST |  | 2025-10-28 | 2025-11-20 | 2025-10-30 | 2025-12-10 | 2025-12-11 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | 11.11.25 done drm 10.11.25 upload revisi 001/TSA-SPH-CMI/XI/2025 | 2025-10-11 |  | JSA No.1/TSA/HSE/10/2025 | 2025-10-11 | 2025-10-12 | SWP-HSE-72 | Submit | Approved | 2025-11-11 | 2025-11-12 | Dismantle Tower | EMAPO25-002372 | 2025-12-30 | 0 |  |  | 0 |  |  |  | Complete | Lifi | TSA
169 | CMI | RLC | Nasional | #NAME? | 2025-09-29 | E1200351 | ID-KR-04104 | DANAGRAHA_BUILDING1 / DANA GRAHA | 2 | EMA | KEPULAUAN RIAU | Kota Batam | JL. IMAM BONJOL - NAGOYA/KOMP. NAGOYA DANA GRAHA NAGOYA | 1.14898 | 104.00901 | 1488.16 | 7 |  | Rooftop | pole | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-10-11 | 2025-10-11 |  | 2025-10-13 | 2025-10-27 |  |  |  |  | 2025-11-04 | 2025-11-04 | ATP App MS | Material diambil MS di site | 2025-10-28 | 2025-11-20 | 2025-10-30 |  | 2025-12-11 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-10-11 | 2025-10-12 |  |  |  |  | Approved | NY Submit | 2025-11-11 | 2025-11-12 | Dismantle Equipment | Include Dism Tower | 2025-12-30 | 0 |  |  | 0 |  |  |  | Complete | CMI Project | CMI
170 | CMI | RLC | Nasional | #NAME? | 2025-09-30 | E1200372 | ID-KR-04123 | NONGSA_RESORT_1 | 2 | EMA | KEPULAUAN RIAU | Kota Batam | Jl. Hang Jebat Sambau, Kota Batam, Kepulauan Riau | 1.19336 | 104.10190 | 13067.712 |  |  | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | NA |  |  | 2025-08-13 |  | 2025-11-25 |  |  |  |  | 2025-12-29 | BAST |  | 2025-11-06 | 2025-11-12 | 2025-11-18 | 2025-12-10 | 2025-12-11 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit | 2025-12-29 | 2025-12-29 | Dismantle Tower | EMAPO25-002374 | 2025-12-30 | 0 |  |  | 0 |  |  |  | Complete
171 | CMI | RLC | Nasional | #NAME? | 2025-09-30 | E1200372 | ID-KR-04123 | NONGSA_RESORT_1 | 2 | EMA | KEPULAUAN RIAU | Kota Batam | Jl. Hang Jebat Sambau, Kota Batam, Kepulauan Riau | 1.19336 | 104.10190 | 13067.712 |  |  | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | NA |  |  | 2025-08-13 | 2025-10-20 |  |  |  |  | 2025-10-20 |  | ATP App MS | 21.10.25 Dism Equip XL 24.10.25 Dism Equip IOH 23.10.25 Dism Equip Tsel | 2025-11-06 | 2025-11-12 | 2025-11-18 |  | 2025-12-11 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit | 2026-01-19 | 2026-01-19 | Dismantle Equipment | Include Reloc | 2025-12-30 | 0 |  |  | 0 |  |  |  | Complete
172 | CMI | RLC | Nasional | #NAME? | 2025-09-30 | E1200372 | ID-KR-04123 | NONGSA_RESORT_1 | 2 | EMA | KEPULAUAN RIAU | Kota Batam | Jl. Hang Jebat Sambau, Kota Batam, Kepulauan Riau | 1.19336 | 104.10190 | 13067.712 |  |  | Greenfield | SST 4 Legs | Relocation Equipment | [5 empty] | NY Submit |  | NA |  |  | 2025-08-13 |  |  |  | 2025-11-25 | 2025-10-30 |  |  | OA/RFS | 21.10.25 OA XL 30.10.25 OA IOH 30.10.25 OA IOH | 2025-11-06 | 2025-11-12 | 2025-11-18 | 2025-12-10 | 2025-12-11 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit | 2026-01-19 | 2026-01-19 | Relocation Equipment | EMAPO25-002376 | 2025-12-30 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | ID-KR-14200 | Nongsa Sambu |  |  |  | XLWO-20251014-00000059 | CRQ000001035472
173 | CMI | RLC | Nasional | #NAME? | 2025-09-30 | E3500375 | ID-JI-06540 | MERPATI | 15 | EMA | JAWA TIMUR | Kab. Sidoarjo | MERPATI AIRPORT, BANDARA UDARA JUANDA, SURABAYA | -7.38106 | 112.766 | 7491.54 |  |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Dismantle | 2026-10-03 | 2026-03-10 | Expired |  | 2026-02-20 | 2026-02-18 |  | 2026-03-04 |  | 2026-03-13 |  |  |  |  | 2026-03-12 | BAST | 19.02.25 Plan survey 09.03.26 Start dismantle 11.03.26 Power off MDP ke KWH | 2026-02-23 | 2026-02-25 | 2026-02-23 |  | 2026-02-25 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-02-21 | 2026-03-02 | JSA No.06/TSA/HSE/02/2026 | 2026-02-21 | 2026-02-21 | SWP-HSE-106 | Approved | Approved | 2026-03-16 | 2026-03-16 | Dismantle Tower | EMAPO26-000403 | 2026-03-16 | 0 |  |  | 0 |  |  |  | Complete
174 | CMI | RLC | Nasional | #NAME? | 2025-09-30 | E3500375 | ID-JI-06540 | MERPATI | 15 | EMA | JAWA TIMUR | Kab. Sidoarjo | MERPATI AIRPORT, BANDARA UDARA JUANDA, SURABAYA | -7.38106 | 112.766 | 7491.54 |  |  | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-02-20 | 2026-02-18 |  |  | 2026-03-03 |  | 2026-07-14 |  |  |  |  | Inbound | 03.03.26 done dism XLS 03.03.26 done dism Tsel 04.03.26 Inbound Tsel 08.03.26 IOH done dism by MNO 14.07.26 Inbound XLS | 2026-02-23 | 2026-02-25 | 2026-02-23 |  | 2026-02-25 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-02-21 | 2026-03-02 |  | 2026-02-21 | 2026-02-21 |  | Approved | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2026-03-16 | 0 |  |  | 0 |  |  |  | 04.03.26 done Inbound Tsel XLS NY Inbound | TSA
175 | CMI | RLC | Nasional | #NAME? | 2025-09-30 | R5100118 | ID-BA-09698 | PENYARINGAN RELOC | 16 | CMI | BALI | Kota Denpasar | JL. TUNJUNG SARI,GG MELATI, BANJAR MADURA SANUR KAUH DENPASAR. (80231) | -8.69005 | 115.251 |  | 15 | IOH, Tsel, XL | Rooftop | Pole | Dismantle Tower |  |  | Reloc | 2026-01-14 | 2026-01-21 | Expired |  | 2025-10-09 | 2025-10-09 |  | 2026-01-06 |  | 2026-02-06 |  |  |  |  | 2026-02-06 | BAST | 03.02.26 Start dismantle | 2025-11-21 | 2025-12-09 | 2025-12-08 |  | 2025-12-09 | 2025-12-09 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-09 | 2025-10-10 | JSA No.10/TSA/HSE/09/2025 | 2025-10-09 | 2025-10-10 | SWP-HSE-73 | Approved | Approved | 2026-02-06 | 2026-02-09 | Dismantle Tower | CMIPO25-005578 | 2025-12-17 | 8 |  |  | 0 |  |  |  | Complete | CMI Project | CMI
176 | CMI | RLC | Nasional | #NAME? | 2025-09-30 | R5100118 | ID-BA-09698 | PENYARINGAN RELOC | 16 | CMI | BALI | Kota Denpasar | JL. TUNJUNG SARI,GG MELATI, BANJAR MADURA SANUR KAUH DENPASAR. (80231) | -8.69005 | 115.251 |  | 15 | IOH, Tsel, XL | Rooftop | Pole | Dismantle Equipment |  |  | Reloc | 2026-01-14 | 2026-01-21 | Expired |  | 2025-10-09 | 2025-10-09 |  |  | 2026-01-29 | [6 empty] | Dismantle Perangkat | 14.01.26 Dismantle equip Tsel 26.01.26 Dismantle equip IOH 29.01.26 Dismantle equip XLS | 2025-11-21 | 2025-12-09 | 2025-12-08 |  | 2025-12-09 | 2025-12-09 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-09 | 2025-10-10 |  | 2025-10-09 | 2025-10-10 |  | Approved | Approved |  |  | Dismantle Equipment | Include Reloc | 2026-05-28 | 170 |  |  | 0 |  |  |  | Complete
177 | CMI | RLC | Nasional | #NAME? | 2025-09-30 | R5100118 | ID-BA-09698 | PENYARINGAN RELOC | 16 | CMI | BALI | Kota Denpasar | JL. TUNJUNG SARI,GG MELATI, BANJAR MADURA SANUR KAUH DENPASAR. (80231) | -8.69005 | 115.251 |  | 15 | IOH, Tsel, XL | Rooftop | Pole | Relocation Equipment |  |  | Reloc | 2026-01-14 | 2026-01-21 | Expired |  | 2025-10-09 | 2025-10-09 | [5 empty] | 2026-02-04 | 2026-02-23 |  |  | OA/RFS | 16.01.26 OA Tsel 28.01.26 OA IOH 04.02.26 install done 23.02.26 OA XL (done install FO) | 2025-11-21 | 2025-12-09 | 2025-12-08 | 2026-04-02 | 2025-12-09 | 2025-12-09 | 1st BOQ App on ISAAC | 2026-02-10 |  |  | 2026-05-07 |  | 2026-05-08 | 2nd BOQ App on ISAAC | 30.04.26 DRM | 2025-10-09 | 2025-10-10 |  | 2025-10-09 | 2025-10-10 |  | Approved | Approved |  |  | Relocation Equipment | CMIPO26-001877 | 2026-05-28 | 170 | CMIPO26-001963 | 2026-05-28 | 20 |  |  |  | Complete |  |  |  | ID-BA15315 | DENPASAR SELATAN |  |  | CR-20260122-00000255 CR-20260122-00000256 CR-20260122-00000258 CR-20260122-00000262 | XLWO-20260127-00000224
178 | CMI | RLC | Nasional | #NAME? | 2025-09-30 | E3200727 | ID-JB-05681 | KEBAKTIAN | 10 | EMA | JAWA BARAT | Kota Bandung | JL. PSM,SUKAPURA, KEC. KIARACONDONG, KOTA BANDUNG, JAWA BARAT | -6.9297 | 107.649 | 8236.656 | 40 |  | Greenfield | SST 4 Legs | Dismantle Tower | Taufik Hidayat |  |  |  |  | NY Submit |  |  |  | 2026-10-01 | [8 empty] | NY Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | 09.06.26 boq mentahan | [6 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
179 | CMI | RLC | Nasional | #NAME? | 2025-10-01 | R6400134 | ID-KI-03116 | BATUAH KM.45 | 18 | CMI | KALIMANTAN TIMUR | Kab. Kutai Kartanegara | Batuah, Kec. Loa Janan, Kabupaten Kutai Kartanegara, Kalimantan Timur 75262 | -0.7551 | 117.0518 |  | 71 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Dismantle | 2026-01-12 | 2026-01-19 | Expired |  | 2025-10-14 | 2025-10-14 |  |  |  | 2026-01-22 |  |  |  | 2026-01-21 | 2026-01-21 | BAST | 16.01.26 start dismantle tower | 2026-01-14 | 2026-01-19 | 2026-01-16 |  | 2026-01-19 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-10-14 | 2025-11-16 | JSA No.04/TSA/HSE/10/2025 | 2025-10-14 | 2025-10-15 | SWP-HSE-74 | Approved | Approved | 2026-02-02 | 2026-02-02 | Dismantle Tower | CMIPO26-000309 | 2026-02-02 | 0 |  |  | 0 |  |  |  | Waiting Approval BAST | CMI Project | CMI
180 | CMI | RLC | Nasional | #NAME? | 2025-10-01 | R6400134 | ID-KI-03116 | BATUAH KM.45 | 18 | CMI | KALIMANTAN TIMUR | Kab. Kutai Kartanegara | Batuah, Kec. Loa Janan, Kabupaten Kutai Kartanegara, Kalimantan Timur 75262 | -0.7551 | 117.0518 |  | 71 |  | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Dismantle | 2026-01-12 | 2026-01-19 | Expired |  | 2025-10-14 | 2025-10-14 |  |  | 2026-01-16 |  |  |  |  | 2026-01-16 |  | ATP App MS | 14.01.26 Dismantle equip XLS | 2026-01-14 | 2026-01-19 | 2026-01-16 |  | 2026-01-19 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-10-14 |  |  | 2025-10-14 | 2025-10-15 |  | Submit | Approved | 2026-02-02 | 2026-02-02 | Dismantle Equipment | Include Reloc | 2026-01-30 | 0 |  |  | 0 |  |  |  | Waiting boram PLN | Endra | TSA
181 | CMI | RLC | Nasional | #NAME? | 2025-10-01 | R6400134 | ID-KI-03116 | BATUAH KM.45 | 18 | CMI | KALIMANTAN TIMUR | Kab. Kutai Kartanegara | Batuah, Kec. Loa Janan, Kabupaten Kutai Kartanegara, Kalimantan Timur 75262 | -0.7551 | 117.0518 |  | 71 |  | Greenfield | SST 4 Legs | Relocation Equipment |  |  | Dismantle | 2026-01-12 | 2026-01-19 | Expired |  | 2025-10-14 | 2025-10-14 | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-21 | 2026-02-02 | ATP App MS | 16.01.26 OA XLS | 2026-01-14 | 2026-01-19 | 2026-01-16 |  | 2026-01-19 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-10-14 |  |  | 2025-10-14 | 2025-10-15 |  | Submit | Approved | 2026-02-02 | 2026-02-02 | Relocation Equipment | EMAPO26-000081 | 2026-01-30 | 0 |  |  | 0 |  |  |  | Waiting boram PLN | Endra | TSA |  | ID-KI-07454 | KM80_BALIKPAPAN | -0.75455 | 117.05177
182 | CMI | RLC | Nasional | #NAME? | 2025-05-03 | E1200347 | ID-KR-04100 | JODOH | 2 | EMA | KEPULAUAN RIAU | Kota Batam | HOTEL OASIS KOMPLEX ORCHID MAS CENTRE, SEI JODOH, BATU AMPAR | 1.157056 | 104.003753 | 971.83 | 10 | IOH | Rooftop | Pole | Rebuild_LOS Survey 05BTM0110 JODOH_EP to 05BTM0187 JLTJ_BUNTUNG_PL | [5 empty] | NY Submit |  | 2025-10-13 | 2025-10-21 | [7 empty] | 2025-11-17 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO25-002021 | 2025-10-14 | 0 |  |  | 0 |  |  |  | Complete |  |  |  | 05BTM0187 | JLTJ_BUNTUNG_PL | 1.1638 | 104.03036 |  |  |  | Protelindo
183 | CMI | RLC | Nasional | #NAME? | 2025-10-07 | E3500389 | ID-JI-06554 | BURNEH | 15 | EMA | JAWA TIMUR | Kab. Bangkalan | JL KH MUNIF NO 26 DESA BURNEH KECAMATAN BURNEH KAB BANGKALAN | -7.05249 | 112.785 | 22120.78 | 70 | IOH, Tsel, SF | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2025-10-03 | 2024-10-07 |  | 2026-01-06 |  | 2026-02-18 |  |  |  |  | 2026-02-18 | BAST | 12.02.26 Start dismantle | 2025-12-11 | 2025-12-19 | 2025-12-12 |  | 2025-12-19 | 2025-12-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-07 | 2025-10-07 | JSA No.08/TSA/HSE/10/2025 | 2025-10-07 | 2024-10-07 | SWP-HSE-81 | Approved | Approved | 2026-02-19 |  | Dismantle Tower | EMAPO25-002405 | 2025-12-31 | 12 |  |  | 0 |  |  |  | Complete
184 | CMI | RLC | Nasional | #NAME? | 2025-10-07 | R7300461 | ID-SN-09959 | Nuri Rajawali | 19 | CMI | SULAWESI SELATAN | Kab. Gowa | Masjid Jami, Jl. Nuri No. 12, Kel. Mariso, Kec. Mariso, Kab. Gowa, Propinsi Sulawesi Selatan | -5.15895 | 119.41 | 725.49 | 5 | XL | Rooftop | Minaret | Dismantle Tower |  |  | Survey | 2025-10-09 | 2025-10-22 | Expired |  | 2025-10-14 | 2025-10-14 |  | 2025-10-18 |  | 2025-10-30 |  |  |  |  | 2025-10-30 | BAST |  | 2025-10-29 | 2025-11-10 | 2025-10-30 |  | 2025-11-27 | 2025-12-02 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  |  |  | JSA No.05/TSA/HSE/10/2025 | 2025-10-14 | 2025-10-15 | SWP-HSE-75 | NY Submit | Approved | 2025-12-01 | 2025-12-03 | Dismantle Tower | CMIPO25-005422 | 2025-12-09 | 7 |  |  | 0 |  |  |  | Payment Invoice | CMI Finance | CMI
185 | CMI | RLC | Nasional | #NAME? | 2025-10-07 | R7300461 | ID-SN-09959 | Nuri Rajawali | 19 | CMI | SULAWESI SELATAN | Kab. Gowa | Masjid Jami, Jl. Nuri No. 12, Kel. Mariso, Kec. Mariso, Kab. Gowa, Propinsi Sulawesi Selatan | -5.15895 | 119.41 | 725.49 | 5 | XL | Rooftop | Minaret | Dismantle Equipment |  |  | Survey | 2025-10-09 | 2025-10-22 | Expired |  | 2025-10-14 | 2025-10-14 |  |  | 2025-10-27 |  | 2025-10-27 |  |  | 2025-10-30 |  | ATP App MS | 27.10.25 Inbound XLS | 2025-10-29 | 2025-11-10 | 2025-10-30 |  | 2025-11-27 | 2025-12-02 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-14 | 2025-10-16 |  | 2025-10-14 | 2025-10-15 |  | Approved | Approved | 2025-12-01 | 2025-12-03 | Dismantle Equipment | Include Dism Tower | 2025-12-09 | 7 |  |  | 0 |  |  |  | Payment Invoice | CMI Finance | CMI
186 | CMI | RLC | Nasional | #NAME? | 2025-10-08 | R3100496 | ID-JK-02429 | KELAPA DUA WETAN | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Timur | JL KELAPA DUA WETAN NO 42 RT01/08 , KEL.KELAPA DUA WETAN, KEC.CIRACAS | -6.34497 | 106.884 | 3152.7775 | 32 | XL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-10-09 | 2025-10-22 | Expired |  | 2025-10-21 | 2025-10-21 |  | 2025-11-04 |  | 2025-12-04 |  |  |  | 2025-12-11 | 2025-12-11 | BAST |  | 2025-11-14 | 2025-11-25 | 2025-11-14 |  | 2025-11-25 | 2025-11-26 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 005/TSA-SPH-CMI/XI/2025 | 2025-10-21 | 2025-10-23 | JSA No.10/TSA/HSE/09/2025 | 2025-10-21 | 2025-10-23 | SWP-HSE-79 | Approved | Approved | 2026-01-11 | 2026-01-12 | Dismantle Tower | CMIPO25-005420 | 2025-12-09 | 13 |  |  | 0 |  |  |  | Complete
187 | CMI | RLC | Nasional | #NAME? | 2025-10-08 | R3100496 | ID-JK-02429 | KELAPA DUA WETAN | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Timur | JL KELAPA DUA WETAN NO 42 RT01/08 , KEL.KELAPA DUA WETAN, KEC.CIRACAS | -6.34497 | 106.884 | 3152.7775 | 32 | XL | Greenfield | SST 4 Legs | Dismantle Equipment | Taufik Hidayat |  | Survey | 2025-10-09 | 2025-10-22 | Expired |  | 2025-10-21 | 2025-10-21 |  | 2025-11-04 | 2025-11-30 |  | 2026-03-04 |  |  |  |  | Inbound | 04.03.26 done inbound | 2025-11-14 | 2025-11-25 | 2025-11-14 |  | 2025-11-25 | 2025-11-26 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-21 |  |  | 2025-10-21 |  |  | Submit | Submit |  |  | Dismantle Equipment | Include Dism Tower | 2025-12-09 | 13 |  |  | 0 |  |  |  | Complete
188 | CMI | RLC | Nasional | #NAME? | 2025-10-08 | R3100496 | ID-JK-02429 | KELAPA DUA WETAN | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Timur | JL KELAPA DUA WETAN NO 42 RT01/08 , KEL.KELAPA DUA WETAN, KEC.CIRACAS | -6.34497 | 106.884 | 3152.7775 | 32 | XL | Greenfield | SST 4 Legs | Relocation Equipment |  |  | Survey | 2025-10-09 | 2025-10-22 | Expired |  | 2025-10-21 | 2025-10-21 | drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-10-21 |  |  | 2025-10-21 |  |  | Submit | Submit |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop
189 | CMI | RLC | Nasional | #NAME? | 2025-10-09 | E1600040 | ID-SS-04261 | MUARA_BELITI | 4 | EMA | SUMATERA SELATAN | Kab. Musi Rawas | KEL MUARA BELITI KEC MUARA BELITI KAB MUARA RAWAS PROP SUMATERA SELATAN | -3.2452 | 103.04 | 22120.8 | 70 | IOH & TSEL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Dismantle | 2025-10-14 | 2025-10-20 | Expired |  | 2025-10-11 | 2025-10-14 |  |  |  | 2025-10-31 |  |  |  | 2025-11-19 | 2025-11-19 | BAST |  | 2025-10-23 | 2025-10-27 | 2025-10-27 | 2025-12-12 | 2025-12-11 | 2025-12-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 009/TSA-SPH-CMI/X/2025 | 2025-10-14 | 2025-10-16 | JSA No.03/TSA/HSE/10/2025 | 2025-10-14 | 2025-10-14 | SWP-HSE-76 | Approved | Approved | 2025-11-19 | 2025-11-19 | Dismantle Tower | EMAPO25-002373 | 2025-12-29 | 17 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
190 | CMI | RLC | Nasional | #NAME? | 2025-10-09 | E1600040 | ID-SS-04261 | MUARA_BELITI | 4 | EMA | SUMATERA SELATAN | Kab. Musi Rawas | KEL MUARA BELITI KEC MUARA BELITI KAB MUARA RAWAS PROP SUMATERA SELATAN | -3.2452 | 103.04 | 22120.8 | 70 | IOH & TSEL | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Dismantle | 2025-10-14 | 2025-10-20 | Expired |  | 2025-10-11 | 2025-10-14 |  |  | 2025-10-25 |  | 2025-11-04 |  |  | 2025-11-19 | 2025-11-19 | ATP App MS | 25.10.25 Done HO material Tsel 04.11.25 Done HO material IOH | 2025-10-23 | 2025-10-27 | 2025-10-27 |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit |  | 2025-10-14 | 2025-10-16 |  |  |  |  | Approved | NY Submit |  |  | Dismantle Equipment | Include Dism Tower | 2025-12-29 | 0 |  |  | 0 |  |  |  | BAN NY App | CMI Project | CMI
191 | CMI | RLC | Nasional | #NAME? | 2025-10-09 | R3350446 | ID-JT-02710 | WURYANTORO | 11 | CMI | JAWA TENGAH | Kab. Wonogiri | JL WURYANTORO LOR RT01/02 , KL WURYANTORO KB WONOGIRI JATENG | -7.90697 | 110.864 |  | 71 | XL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-10-10 | 2025-10-24 | Expired |  | 2025-10-17 | 2025-10-20 |  | 2025-12-01 |  | 2025-12-02 |  |  |  | 2025-12-02 | 2025-12-02 | BAST |  | 2025-11-05 | 2025-11-17 | 2025-11-25 |  | 2025-11-24 | 2025-11-26 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 14.11.25 upload revisi 10.11.25 upload revisi 002/TSA-SPH-CMI/XI/2025 | 2025-10-20 | 2025-10-24 | JSA No.06/TSA/HSE/10/2025 | 2025-10-21 | 2025-10-24 | SWP-HSE-78 | Approved | Approved | 2025-12-03 |  | Dismantle Tower | CMIPO25-005423 | 2025-12-09 | 13 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JT-06011 | E3300301 WURYANTORO
192 | CMI | RLC | Nasional | #NAME? | 2025-10-09 | R3350446 | ID-JT-02710 | WURYANTORO | 11 | CMI | JAWA TENGAH | Kab. Wonogiri | JL WURYANTORO LOR RT01/02 , KL WURYANTORO KB WONOGIRI JATENG | -7.90697 | 110.864 |  | 71 | XL | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-10-10 | 2025-10-24 | Expired |  | 2025-10-17 | 2025-10-20 |  |  | 2025-11-27 |  |  |  |  | 2025-11-29 |  | ATP App MS |  | 2025-11-05 | 2025-11-17 | 2025-11-25 |  | 2025-11-24 | 2025-11-26 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-20 | 2025-10-24 | JSA No.06/TSA/HSE/10/2025 | 2025-10-21 | 2025-10-24 |  | Approved | Approved | 2026-04-21 | 2026-04-21 | Dismantle Equipment | Include Reloc | 2025-12-10 | 14 |  |  | 0 |  |  |  | Complete | yasir | TSA |  | ID-JT-06011 | E3300301 WURYANTORO
193 | CMI | RLC | Nasional | #NAME? | 2025-10-09 | R3350446 | ID-JT-02710 | WURYANTORO | 11 | CMI | JAWA TENGAH | Kab. Wonogiri | JL WURYANTORO LOR RT01/02 , KL WURYANTORO KB WONOGIRI JATENG | -7.90697 | 110.864 |  | 71 | XL | Greenfield | SST 4 Legs | Relocation Equipment | Abe Rizal |  | Survey | 2025-10-10 | 2025-10-24 | Expired |  | 2025-10-17 | 2025-10-20 | [5 empty] | 2025-11-28 | 2025-11-29 | 2025-11-29 |  | ATP App MS |  | 2025-11-05 | 2025-11-17 | 2025-11-25 |  | 2025-11-24 | 2025-11-26 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-20 | 2025-10-24 | JSA No.06/TSA/HSE/10/2025 | 2025-10-21 | 2025-10-24 |  | Approved | Approved | 2026-04-21 | 2026-04-21 | Relocation Equipment | EMAPO25-002323 | 2025-12-10 | 14 |  |  | 0 |  |  |  | Complete |  |  |  | ID-JT-06011 | E3300301 WURYANTORO
194 | CMI | RLC | Nasional | #NAME? | 2025-08-15 | E3200633 | ID-JB-05588 | BOBOS | 10 | CMI | JAWA BARAT | Kab. Cirebon | Cikalahang, Kabupaten Cirebon, Jawa Barat | -6.77656 | 108.4096 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Rebuild_LOS Survey JAW-JB-SBR-1890 to JAW-JB-MJL-3028 | Taufik Hidayat |  |  |  |  | NY Submit | Permit by MS |  |  | drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | Drop |  | Drop |  |  | Drop |  |  |  | Drop
195 | CMI | RLC | Nasional | #NAME? | 2025-08-15 | E3200633 | ID-JB-05588 | BOBOS | 10 | CMI | JAWA BARAT | Kab. Cirebon | Cikalahang, Kabupaten Cirebon, Jawa Barat | -6.77656 | 108.4096 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Rebuild_LOS Survey JAW-JB-SBR-1890 to JAW-JB-SBR-1904 | Taufik Hidayat |  |  |  |  | NY Submit | Permit by MS | 2025-10-22 | 2025-10-31 | [7 empty] | 2025-12-12 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO25-002329 | 2025-12-10 | 0 |  |  | 0 |  |  |  | Complete
196 | CMI | RLC | Nasional | #NAME? | 2025-08-15 | E3200633 | ID-JB-05588 | BOBOS | 10 | CMI | JAWA BARAT | Kab. Cirebon | Cikalahang, Kabupaten Cirebon, Jawa Barat | -6.77656 | 108.4096 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Rebuild_LOS Survey JAW-JB-SBR-1890 to JAW-JB-MJL-1493 | Taufik Hidayat |  |  |  |  | NY Submit | Permit by MS | 2025-10-22 | 2025-10-31 | [7 empty] | 2025-12-12 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO25-002329 | 2025-12-10 | 0 |  |  | 0 |  |  |  | Complete
197 | CMI | RLC | Nasional | #NAME? | 2025-08-15 | E3200633 | ID-JB-05588 | BOBOS | 10 | CMI | JAWA BARAT | Kab. Cirebon | Cikalahang, Kabupaten Cirebon, Jawa Barat | -6.77656 | 108.4096 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Rebuild_LOS Survey JAW-JB-SBR-1890 to JAW-JB-MJL-3026 | Taufik Hidayat |  |  |  |  | NY Submit | Permit by MS | 2025-10-22 | 2025-10-31 | [7 empty] | 2025-12-12 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO25-002329 | 2025-12-10 | 0 |  |  | 0 |  |  |  | Complete
198 | CMI | RLC | Nasional | #NAME? | 2025-08-15 | E3200633 | ID-JB-05588 | BOBOS | 10 | CMI | JAWA BARAT | Kab. Cirebon | Cikalahang, Kabupaten Cirebon, Jawa Barat | -6.77656 | 108.4096 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Rebuild_LOS Survey JAW-JB-SBR-1890 to JAW-JB-MJL-8006 | Taufik Hidayat |  |  |  |  | NY Submit | Permit by MS | 2025-10-22 | 2025-10-31 | [7 empty] | 2025-12-12 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO25-002329 | 2025-12-10 | 0 |  |  | 0 |  |  |  | Complete
199 | CMI | RLC | Nasional | #NAME? | 2025-10-10 | E1600065 | ID-SS-04286 | TANJUNG_ENIM | 4 | EMA | SUMATERA SELATAN | Kab. Muara Enim | JL. BTN KEBAN AGUNG BLOK AE / DESA TANJUNG ENIM KAB MUARA ENIMSUMSEL | -3.7765 | 103.8 | 37254.736 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Dismantle | 2025-10-14 | 2025-10-20 | Expired |  | 2025-10-12 | 2025-10-14 |  | 2025-10-20 |  | 2025-10-31 |  |  |  | 2025-11-19 | 2025-11-19 | BAST |  | 2025-10-27 | 2025-11-12 | 2025-11-13 | 2025-12-09 | 2025-12-09 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | 011/TSA-SPH-CMI/X/2025 | 2025-10-14 | 2025-10-16 | JSA No.02/TSA/HSE/10/2025 | 2025-10-15 | 2025-10-15 | SWP-HSE-77 | Approved | Approved | 2025-11-19 |  | Dismantle Tower | EMAPO25-002370 | 2025-12-30 | 0 |  |  | 0
200 | CMI | RLC | Nasional | #NAME? | 2025-08-19 | R5100062 | ID-BA-00446 | SMPK_THOMAS_AQUINO | 16 | CMI | BALI | Kab. Badung | BANJAR BABAKAN DESA CANGGU KEC.KUTA UTARA KAB.BADUNG | -8.62888 | 115.15247 | 1193.68 | 12 |  | Rooftop | Pole | Relocation Equipment | Prayudi |  | Dismantle | 2025-10-12 | 2025-10-18 | Expired |  | 2025-08-22 | 2025-08-22 | drop | [8 empty] | Drop |  | 2025-10-09 | [5 empty] | 1st BOQ Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop
201 | CMI | RLC | Nasional | #NAME? | 2025-10-16 | R1200054 | ID-SU-00665 | PUSAT PASAR | 1 | CMI | SUMATERA UTARA | Kota Medan | JL. DURIAN NO 2 S KEL. PERINTIS, KEC. MEDAN TIMUR, KOTA MEDAN, SUMATRA UTARA | 3.59866 | 98.68378 | 3713.64 | 25 | SF | Rooftop | MT 4 Legs | Dismantle Tower |  |  | Survey | 2025-10-17 | 2025-10-31 | Expired |  | 2025-10-19 | 2025-10-21 |  |  |  | 2025-10-30 |  |  |  | 2025-11-04 | 2025-11-04 | BAST |  | 2025-10-22 | 2025-12-15 | 2025-10-28 |  | 2025-12-15 | 2025-12-15 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 008/TSA-SPH-CMI/X/2025 | 2025-10-23 | 2025-10-24 | JSA No.07/TSA/HSE/10/2025 | 2025-10-23 | 2025-10-24 | SHP-HSE-80 | Approved | Approved | 2025-11-05 | 2025-11-05 | Dismantle Tower | CMIPO25-005744 | 2025-12-31 | 16 |  |  | 0 |  |  |  | Invoice Submit | Lifi | TSA
202 | CMI | RLC | Nasional | #NAME? | 2025-10-08 | R3100496 | ID-JK-02429 | KELAPA DUA WETAN | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Timur | JL KELAPA DUA WETAN NO 42 RT01/08 , KEL.KELAPA DUA WETAN, KEC.CIRACAS | -6.34497 | 106.884 | 3152.7775 | 32 | XL | Greenfield | SST 4 Legs | Rebuild_LOS Survey JAW-JK-CKG-0211 to JAW-JK-CKG-0184 | [5 empty] | NY Submit |  |  |  | drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | Drop |  | Drop |  |  | Drop |  |  |  | Drop
203 | CMI | RLC | Nasional | #NAME? | 2025-10-16 | R1200054 | ID-SU-00665 | PUSAT PASAR | 1 | CMI | SUMATERA UTARA | Kota Medan | JL. DURIAN NO 2 S KEL. PERINTIS, KEC. MEDAN TIMUR, KOTA MEDAN, SUMATRA UTARA | 3.59866 | 98.68378 | 3713.64 | 25 | SF | Rooftop | MT 4 Legs | Dismantle Equipment |  |  | Survey | 2025-10-17 | 2025-10-31 | Expired |  | 2025-10-19 | 2025-10-19 |  |  | 2025-10-29 |  | 2025-11-01 |  |  | 2025-11-04 | 2025-11-04 | ATP App MS | 01.11.25 Done HO material XLS | 2025-10-22 | 2025-12-15 | 2025-10-28 |  | 2025-12-15 | 2025-12-15 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit | 2025-11-05 | 2025-11-05 | Dismantle Equipment | Include Dism Tower | 2025-12-31 | 16 |  |  | 0
204 | CMI | RLC | Nasional | #NAME? | 2025-10-22 | R3300369 | ID-JT-00008 | NUSUKAN I | 11 | CMI | JAWA TENGAH | Kota Surakarta | BONOREJO, BANJARSARI, SURAKARTA | -7.54489 | 110.822 | 4864.94 | 35 | IOH & XL | Greenfield | SST 3 Legs | Dismantle Tower | Joko Dedoyo | +62 878-6109-5209 | Survey | 2026-05-13 | 2026-05-19 | Expired |  | 2026-05-18 | 2026-05-22 | 2026-09-29 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | 23.05.26 BOQ mentahan | 2026-07-28 |  | JSA No.49/TSA/HSE/07/2026 | 2026-07-28 |  | SWP-HSE-149 | Submit | Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
205 | CMI | RLC | Nasional | #NAME? | 2025-10-22 | R3300369 | ID-JT-00008 | NUSUKAN I | 11 | CMI | JAWA TENGAH | Kota Surakarta | BONOREJO, BANJARSARI, SURAKARTA | -7.54489 | 110.822 | 4864.94 | 35 | IOH & XL | Greenfield | SST 3 Legs | Dismantle Equipment | Joko Dedoyo | +62 878-6109-5209 | Survey | 2026-05-13 | 2026-05-19 | Expired |  | 2026-05-18 | 2026-05-22 | 2026-09-29 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | 23.05.26 BOQ mentahan | [6 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
206 | CMI | RLC | Nasional | #NAME? | 2025-10-22 | R3300369 | ID-JT-00008 | NUSUKAN I | 11 | CMI | JAWA TENGAH | Kota Surakarta | BONOREJO, BANJARSARI, SURAKARTA | -7.54489 | 110.822 | 4864.94 | 35 | IOH & XL | Greenfield | SST 3 Legs | Relocation Equipment | Joko Dedoyo | +62 878-6109-5209 | Survey | 2026-05-13 | 2026-05-19 | Expired |  | 2026-05-18 | 2026-05-22 | 2026-09-29 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | 23.05.26 BOQ mentahan | [6 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0
207 | CMI | RLC | Nasional | #NAME? | 2025-10-28 | R3270659 | ID-JB-02490 | PERUMNAS CIJERAH | 10 | CMI | JAWA BARAT | Kota Bandung | JL.MEKAR ASIH AF9 NO. 9 KEC.CIJERAH , KOTA BANDUNG,JABAR | -6.92317 | 107.565 | 3068.8915 | 31 | XL | Greenfield | SST 4 Legs | Dismantle Tower | Taufik Hidayat |  | Dismantle | 2025-11-14 | 2025-11-21 | Expired |  | 2025-10-30 | 2025-10-30 |  |  |  | 2025-12-02 |  |  |  |  | 2025-12-03 | BAST |  | 2025-11-19 | 2025-11-26 | 2025-11-27 |  | 2025-11-27 | 2025-11-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-30 | 2025-11-01 | JSA No.09/TSA/HSE/10/2025 | 2025-10-30 | 2025-11-01 | SWP-HSE-82 | Approved | Approved |  |  | Dismantle Tower | CMIPO25-005421 | 2025-12-09 | 12 |  |  | 0
208 | CMI | RLC | Nasional | #NAME? | 2025-10-28 | R7300203 | ID-SN-03168 | KIMA 2 | 19 | CMI | SULAWESI SELATAN | Kota Makassar | JL PROF SUTAMI NO42 , KOTA MAKASSAR | -5.08581 | 119.49287 | 6828.525 | 51 | IOH,XL&SF | Greenfield | SST 3 Legs | Dismantle Tower |  |  | Survey | 2025-11-04 | 2025-11-17 | Expired |  | 2025-11-08 | 2025-11-14 |  | 2026-01-21 |  | 2026-02-19 | [5 empty] | Dismantle | 13.02.26 start dismantle | 2025-12-05 | 2025-12-10 | 2025-12-08 | 2026-04-06 | 2025-12-10 | 2025-12-11 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  |  |  | JSA No.07/TSA/HSE/11/2025 | 2025-11-17 | 2025-11-17 | SWP-HSE-90 | NY Submit | Approved |  |  | Dismantle Tower | CMIPO25-005743 | 2025-12-31 | 20 |  |  | 0 |  |  |  | Waiting Sign BAST PMD | CMI Project | CMI
209 | CMI | RLC | Nasional | #NAME? | 2025-10-28 | R7300203 | ID-SN-03168 | KIMA 2 | 19 | CMI | SULAWESI SELATAN | Kota Makassar | JL PROF SUTAMI NO42 , KOTA MAKASSAR | -5.08581 | 119.49287 | 6828.525 | 51 | IOH,XL&SF | Greenfield | SST 3 Legs | Dismantle Equipment |  |  | Survey | 2025-11-04 | 2025-11-17 | Expired |  | 2025-11-08 | 2025-11-14 |  | 2026-01-21 | 2026-02-08 |  |  |  |  | 2026-02-16 | 2026-02-16 | ATP App MS | 06.02.26 Start Dismantle IOH 08.02.26 Start Dismantle XL | 2025-12-05 | 2025-12-10 | 2025-12-08 | 2026-04-06 | 2025-12-10 | 2025-12-11 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit | 2026-03-03 | 2026-03-03 | Dismantle Equipment | Include Reloc | 2025-12-31 | 20 |  |  | 0 |  |  |  | Complete | CMI Project | CMI
210 | CMI | RLC | Nasional | #NAME? | 2025-10-28 | R7300203 | ID-SN-03168 | KIMA 2 | 19 | CMI | SULAWESI SELATAN | Kota Makassar | JL PROF SUTAMI NO42 , KOTA MAKASSAR | -5.08581 | 119.49287 | 6828.525 | 51 | IOH,XL&SF | Greenfield | SST 3 Legs | Relocation Equipment |  |  | Survey | 2025-11-04 | 2025-11-17 | Expired |  | 2025-11-08 | 2025-11-14 |  | 2026-01-21 |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-16 | 2026-02-16 | ATP App MS | 07.02.26 OA IOH 11.02.26 OA XL | 2025-12-05 | 2025-12-10 | 2025-12-08 | 2026-04-06 | 2025-12-10 | 2025-12-11 | 1st BOQ App on ISAAC | 2026-02-12 |  |  | 2026-02-18 |  | 2026-04-24 | 2nd BOQ App on ISAAC | [7 empty] | NY Submit | NY Submit | 2026-03-03 | 2026-03-03 | Relocation Equipment | CMIPO25-005745 | 2025-12-31 | 20 | NY release |  | 103 |  |  |  | Waiting PO Variation | CMI Project | CMI |  | ID-SN-15289 | BIRA TAMALANREA |  |  | CR-20260204-00000222 CR-20260204-00000224 CR-20260205-00000252 CR-20260205-00000256 | XLWO-20260205-00000686
211 | CMI | RLC | Nasional | #NAME? | 2025-10-28 | R7200006 | ID-ST-01430 | NALU | 20 | CMI | SULAWESI TENGAH | Kab. Toli-Toli | JL.POROS TIMBALANI TOLI TOLI KEL NALU KECAMATAN BAOLAN | 1.02319 | 120.79765 | 8909.32 | 52 | IOH & XL | Greenfield | SST 3 Legs | Dismantle Tower |  |  | dismantle | 2026-04-14 | 2026-04-20 | Expired |  | 2025-11-09 | 2025-11-10 | 2026-01-31 | 2026-01-19 | [7 empty] | RFD App | Waiting instruksi | 2025-12-08 | 2025-12-18 | 2025-12-08 |  | 2025-12-19 | 2025-12-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | Need DRM Ticket (BOQ & SPH NY email) | 2025-11-10 | 2025-11-14 | JSA No.06/TSA/HSE/11/2025 | 2025-11-10 | 2025-11-14 | SWP-HSE-84 | Approved | Approved |  |  | Dismantle Tower | CMIPO25-005751 | 2025-12-31 | 12 |  |  | 0 |  |  |  |  | CMI Project | CMI
212 | CMI | RLC | Nasional | #NAME? | 2025-10-28 | R7200006 | ID-ST-01430 | NALU | 20 | CMI | SULAWESI TENGAH | Kab. Toli-Toli | JL.POROS TIMBALANI TOLI TOLI KEL NALU KECAMATAN BAOLAN | 1.02319 | 120.79765 | 8909.32 | 52 | IOH & XL | Greenfield | SST 3 Legs | Dismantle Equipment |  |  | dismantle | 2026-04-14 | 2026-04-20 | Expired |  | 2025-11-09 | 2025-11-10 |  | 2026-01-19 | 2026-04-18 | [6 empty] | Dismantle Perangkat | 16.04.26 Dismantle IOH 18.04.26 Dismantle Tsel | 2025-12-08 | 2025-12-18 | 2025-12-08 |  | 2025-12-19 | 2025-12-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | Need DRM | 2025-11-10 | 2025-11-14 | JSA No.06/TSA/HSE/11/2025 | 2025-11-10 | 2025-11-14 |  | Approved | Approved | 2026-05-05 | 2026-05-05 | Dismantle Equipment | Include Reloc | 2025-12-31 | 12 |  |  | 0 |  |  |  | Complete | CMI Project | CMI
213 | CMI | RLC | Nasional | #NAME? | 2025-10-28 | R7200006 | ID-ST-01430 | NALU | 20 | CMI | SULAWESI TENGAH | Kab. Toli-Toli | JL.POROS TIMBALANI TOLI TOLI KEL NALU KECAMATAN BAOLAN | 1.02319 | 120.79765 | 8909.32 | 52 | IOH & XL | Greenfield | SST 3 Legs | Relocation Equipment IOH H:50 Az:35,180,250 LB:-30,3 XL H:50 Az:70,170,235 LB:-29,9 |  |  | dismantle | 2026-04-14 | 2026-04-20 | Expired |  | 2025-11-09 | 2025-11-10 |  | 2026-01-19 |  |  |  | 2026-04-22 | 2026-04-22 | 2026-04-24 |  | ATP App MS | 21.04.26 OA Tsel 22.04.26 OA IOH 11.06.26 ATP XLS full sign | 2025-12-08 | 2025-12-18 | 2025-12-08 |  | 2025-12-19 | 2025-12-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | Need DRM | 2025-11-10 | 2025-11-14 | JSA No.06/TSA/HSE/11/2025 | 2025-11-10 | 2025-11-14 |  | Approved | Approved | 2026-05-05 | 2026-05-05 | Relocation Equipment | CMIPO25-005753 | 2025-12-31 | 12 |  |  | 0 |  |  |  | Complete | CMI Project | CMI |  | ID-ST-16473 | BAOLAN | 1.02000 | 120.7966 | CR-20260413-00000271 CR-20260413-00000273 | XLWO-20260413-00000188
214 | CMI | RLC | Nasional | #NAME? | 2025-11-03 | E3200034 | ID-JB-04989 | CIPANGAUR | 10 | EMA | JAWA BARAT | Kab. Bogor | KAMPUNG CIPANGAUR RT005 RW011 DESA CINTA MANIK KEC CIGUDEK KAB BOGOR JAWA BARAT | -6.51494 | 106.533 | 1080.8615 | 32 |  | Greenfield | Guyed Mast | Dismantle Tower | Taufik Hidayat |  | Survey | 2025-11-05 | 2025-11-18 | Expired |  | 2025-11-11 | 2025-11-11 | [9 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-11-11 | 2025-11-13 | JSA No.07/TSA/HSE/11/2025 | 2025-11-14 | 2025-11-17 | SWP-HSE-89 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0 |  |  |  | NY Submit BOQ | Alfan | TSA
215 | CMI | RLC | Nasional | #NAME? | 2025-11-03 | E3100424 | ID-JK-04825 | SUNTER_B | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Utara | KOMPLEK TNI AL KODAMAR JL. SENTOSA RAYA, KEL. KELAPA GADING BARAT, KEC. KELAPA GADING, JAKARTA UTARA. ALAMAT BM/LL : PRIMKOPAL LANTAMAL III, JL. GUNUNG SAHARI ANCOL, KEC. SUNTER, JAKARTA UTARA | -6.16315 | 106.888 | 3220.428 | 32 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-11-05 | 2025-11-18 | Expired |  | 2025-11-08 |  | 2026-06-30 | [8 empty] | Survey |  | 2026-05-05 | 2026-06-04 | 2026-05-06 |  | 2026-06-04 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  |  |  | JSA No.03/TSA/HSE/11/2025 | 2025-11-12 | 2025-11-12 | SWP-HSE-83 | NY Submit | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
216 | CMI | RLC | Nasional | #NAME? | 2025-11-03 | R3100450 | ID-JK-01538 | KEBON SIRIH | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Pusat | Jl. Kebon Sirih No.1, RT.1/RW.7, Kb. Sirih, Kec. Menteng, Kota Jakarta Pusat, Daerah Khusus Ibukota Jakarta | -6.18313 | 106.833 | 853.6005 | 6 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-11-05 | 2025-11-18 | Expired |  | 2025-10-08 | 2025-11-10 |  |  |  | 2025-12-17 |  |  |  | 2025-12-24 | 2025-12-24 | BAST |  | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 2025-12-15 | 2025-12-15 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-11-10 | 2025-11-11 | JSA No.05/TSA/HSE/11/2025 | 2025-11-10 | 2025-11-12 | SWP-HSE-86 | Approved | Approved | 2025-12-29 | 2025-12-29 | Dismantle Tower | CMIPO25-005743 | 2025-12-31 | 16 | CMIPO26-000487 | 2025-12-31 | 0 |  |  |  | Complete |  |  |  | ID-JK-04921 | BIMANTARA | -6.183870 | 106.833383
217 | CMI | RLC | Nasional | #NAME? | 2025-11-03 | R3100533 | ID-JK-02464 | PELEPAH INDAH | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Utara | JL.RAYA BOULEVARD BLOK LB 3 NO.6 , KEL.KELAPA GADING,KEC.KELAPA GADING | -6.15563 | 106.908 | 2906.38 | 20 |  | Rooftop | MT 4 Legs | Dismantle Tower |  |  | dismantle | 2025-12-14 | 2025-12-21 | Expired |  | 2025-11-08 | 2025-11-10 |  | 2025-11-26 |  | 2025-12-28 |  |  |  | 2026-03-04 | 2026-03-04 | BAST |  | 2025-11-25 | 2025-12-01 | 2025-12-04 |  | 2025-12-04 | 2025-12-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-11-10 | 2025-11-11 | JSA No.04/TSA/HSE/11/2025 | 2025-11-10 | 2025-11-12 | SWP-HSE-85 | Approved | Approved | 2026-03-04 | 2026-03-04 | Dismantle Tower | CMIPO25-005576 | 2025-12-17 | 12 |  |  | 0 |  |  |  | Complete
218 | CMI | RLC | Nasional | #NAME? | 2025-11-05 | E1200395 | ID-KR-04146 | KM 6 TG.PINANG / SUNGAI JANG SEAFOOD | 2 | EMA | KEPULAUAN RIAU | Kota Tanjung Pinang | JL. PEMUDA - GG. AKASIA NO.19 B TANJUNG PINANG / JL. PEMUDA TG AYUN SAKTI BUKIT BESTARI TANJUNG PINANG | 0.90467 | 104.464 | 9236.076 | 52 |  | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-04-08 | 2026-04-08 | 2026-01-10 | [8 empty] | Survey Report | 20.04.26 Start dismantle | 2026-04-09 | 2026-04-14 | 2026-04-09 |  | 2026-04-14 | 2026-04-15 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-04-09 | 2026-04-14 | JSA No.13/TSA/HSE/04/2026 | 2026-04-09 | 2026-04-10 | SWP-HSE-113 | Approved | Approved | 2026-05-28 | 2026-05-28 | Dismantle Tower | EMAPO26-000499 | 2026-04-20 | 5 |  |  | 0 |  |  |  | Complete
219 | CMI | RLC | Nasional | #NAME? | 2025-11-06 | R3580695 | ID-JI-10335 | 3G_Kupang Krajan Sawahan | 15 | CMI | JAWA TIMUR | Kota Surabaya | Jl. Banyu Urip 344 Rt.02/01 Kel.Kupang Krajan Kec. Sawahan surabaya, Ja-Tim 60253 | -7.26834 | 112.715 | 3713.64 | 25 |  | Rooftop | MT 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2025-12-08 | 2025-12-08 |  | 2026-02-13 |  | 2026-03-08 |  |  |  |  | 2026-03-08 | BAST | 05.03.26 Start dismantle | 2026-01-08 | 2026-02-09 | 2026-01-21 |  | 2026-02-09 | 2026-02-09 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-12-08 | 2025-12-10 | JSA No.01/TSA/HSE/12/2025 | 2025-12-09 | 2025-12-11 | SWP-HSE-92 | Approved | Approved | 2026-03-11 | 2026-03-12 | Dismantle Tower | CMIPO26-000869 | 2026-02-26 | 17 |  |  | 0
220 | CMI | RLC | Nasional | #NAME? | 2025-11-10 | E6400049 | ID-KI-07436 | WADUK MANGGAR | 18 | EMA | KALIMANTAN TIMUR | Kota Balikpapan | Karang Joang, Kota Balikpapan, Kalimantan Timur | -1.176000 | 116.879800 | 16015.06 | 52 | TSEL & SF | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-11-05 | 2025-11-18 | Expired |  | 2025-11-07 | 2025-11-07 |  |  |  | 2025-12-05 |  |  |  | 2025-12-15 | 2025-12-15 | BAST |  | 2025-11-14 | 2025-12-01 |  | 2025-01-06 | 2025-12-02 | 2025-12-02 | 1st BOQ App on ISAAC | 2025-12-15 |  |  | 2026-01-06 |  | 2026-01-07 | 2nd BOQ App on ISAAC | 004/TSA-SPH-CMI/XI/2025 | 2025-11-07 | 2025-11-14 | JSA No.02/TSA/HSE/11/2025 | 2025-11-12 | 2025-11-12 | SWP-HSE-87 | Approved | Approved | 2025-12-15 | 2025-12-18 | Dismantle Tower | EMAPO25-002304 | 2025-12-09 | 7 | EMAPO26-000071 | 2025-12-09 | #NUM! |  |  |  | Invoice Submit | Lifi | TSA
221 | CMI | RLC | Nasional | #NAME? | 2025-11-10 | E6400049 | ID-KI-07436 | WADUK MANGGAR | 18 | EMA | KALIMANTAN TIMUR | Kota Balikpapan | Karang Joang, Kota Balikpapan, Kalimantan Timur | -1.176000 | 116.879800 | 16015.06 | 52 | TSEL & SF | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-11-05 | 2025-11-18 | Expired |  | 2025-11-07 | 2025-11-07 |  |  | 2025-12-03 |  |  |  |  | 2025-12-03 |  | ATP App MS | 27.11.25 Done HO material Tsel 03.12.25 Done HO material SF | 2025-11-14 | 2025-12-01 |  | 2025-01-06 | 2025-12-02 | 2025-12-02 | 1st BOQ App on ISAAC | 2025-12-15 |  |  | 2026-01-06 |  | 2026-01-07 | 2nd BOQ App on ISAAC |  | 2025-11-07 | 2025-11-14 | JSA No.02/TSA/HSE/11/2025 | 2025-11-12 | 2025-11-12 |  | Approved | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2025-12-09 | 7 |  |  | 210
222 | CMI | RLC | Nasional | #NAME? | 2025-11-10 | E3100287 | ID-JK-04693 | KAMPUNG_SAWAH | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Selatan | Jl. Raya Depok Ps.Minggu, Srengseng Sawah, Kec. Jagakarsa, Jakarta, Daerah Khusus Ibukota Jakarta | -6.34532 | 106.8338 | 9236.07 | 52 | IOH & XL | Greenfield | SST 4 Legs | Dismantle Tower | Taufik Hidayat |  | Dismantle | 2026-03-11 | 2026-03-17 | Expired |  | 2025-12-24 | 2026-01-05 | 2026-03-15 |  |  | 2026-04-01 |  |  |  | 2026-04-01 | 2026-04-01 | BAST | 25.03.26 Start dismantle | 2026-01-15 | 2026-02-18 | 2026-01-15 |  | 2026-02-19 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-01-05 | 2026-01-05 | JSA No.01/TSA/HSE/01/2026 | 2026-01-05 | 2026-01-06 | SWP-HSE-99 | Approved | Approved | 2026-04-28 | 2026-04-29 | Dismantle Tower | EMAPO26-000334 | 2026-06-25 | 0 |  |  | 0 |  |  |  | Complete | CMI Project | CMI
223 | CMI | RLC | Nasional | #NAME? | 2025-11-10 | E3100287 | ID-JK-04693 | KAMPUNG_SAWAH | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Selatan | Jl. Raya Depok Ps.Minggu, Srengseng Sawah, Kec. Jagakarsa, Jakarta, Daerah Khusus Ibukota Jakarta | -6.34532 | 106.8338 | 9236.07 | 52 | IOH & XL | Greenfield | SST 4 Legs | Dismantle Equipment | Taufik Hidayat |  | Dismantle | 2026-03-11 | 2026-03-17 | Expired |  | 2025-12-24 | 2026-01-05 | 2026-03-15 |  | 2026-03-14 | [6 empty] | Dismantle Perangkat | 11.03.26 Start dismantle XLS 14.03.26 Start dismantle IOH | 2026-01-15 | 2026-02-18 | 2026-01-15 |  | 2026-02-19 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | Need DRM | 2026-01-05 | 2026-01-05 | JSA No.01/TSA/HSE/01/2026 | 2026-01-05 | 2026-01-06 |  | Approved | Approved | 2026-07-01 | 2026-07-01 | Dismantle Equipment | Include Reloc | 2026-02-26 | 0 |  |  | 0 |  |  |  | Complete | CMI Project | CMI
224 | CMI | RLC | Nasional | #NAME? | 2025-11-10 | E3100287 | ID-JK-04693 | KAMPUNG_SAWAH | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Selatan | Jl. Raya Depok Ps.Minggu, Srengseng Sawah, Kec. Jagakarsa, Jakarta, Daerah Khusus Ibukota Jakarta | -6.34532 | 106.8338 | 9236.07 | 52 | IOH & XL | Greenfield | SST 4 Legs | Relocation Equipment | Taufik Hidayat |  | Dismantle | 2026-03-11 | 2026-03-17 | Expired |  | 2025-12-24 | 2026-01-05 | 2026-03-15 |  |  |  |  | 2026-03-18 |  |  |  | Install | 11.03.26 done reinstall XLS 18.03.26 done reinstall & OA IOH | 2026-01-15 | 2026-02-18 | 2026-01-15 |  | 2026-02-19 |  | Upload 1st BOQ & BAN Isaac | 2026-04-07 |  |  | 2026-07-24 | 2026-07-28 | 2026-07-28 | 2nd BOQ App on ISAAC | Need DRM | 2026-01-05 | 2026-01-05 | JSA No.01/TSA/HSE/01/2026 | 2026-01-05 | 2026-01-06 |  | Approved | Approved | 2026-07-01 | 2026-07-01 | Relocation Equipment | CMIPO26-000870 | 2026-02-26 | 0 | NY release |  | 8 |  |  |  | PO Variation NY Release | CMI Project | CMI |  | ID-JK-00059 | R3100395 SRENGSENG SAWAH
225 | CMI | RLC | Nasional | #NAME? | 2025-10-28 | R3270659 | ID-JB-02490 | PERUMNAS CIJERAH | 10 | CMI | JAWA BARAT | Kota Bandung | JL.MEKAR ASIH AF9 NO. 9 KEC.CIJERAH , KOTA BANDUNG,JABAR | -6.92317 | 107.565 | 3068.8915 | 31 | XL | Greenfield | SST 4 Legs | Dismantle Equipment | Taufik Hidayat |  | Dismantle | 2025-11-14 | 2025-11-21 | Expired |  | 2025-10-30 | 2025-10-30 |  |  | 2025-12-02 |  | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 | ATP App MS | 10.03.26 done inbound WH XLS | 2025-11-19 | 2025-11-26 | 2025-11-27 |  | 2025-11-27 | 2025-11-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-30 | 2025-11-01 | JSA No.09/TSA/HSE/10/2025 | 2025-10-30 | 2025-11-01 |  | Approved | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2025-12-09 | 12 |  |  | 0
226 | CMI | RLC | Nasional | #NAME? | 2025-11-20 | R7100006 | ID-SU-09718 | KAMPUNG ISLAM | 20 | CMI | SULAWESI UTARA | Kota Manado | JL. HASANUDIN 7, LING.III, KEL. SINGKIL I, KEC. SINGKIL, KOTA MANADO | 1.5014 | 124.847 | 805.62 | 2 x 9 |  | Rooftop | Pole | Dismantle Tower | [5 empty] | NY Submit |  | 2025-12-05 | 2025-12-08 |  | 2025-12-23 |  | 2026-01-28 | [5 empty] | Dismantle |  | 2025-12-23 | 2026-01-08 | 2025-12-23 |  | 2026-01-08 | 2026-01-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | SPH Reject | 2025-12-08 | 2025-12-12 | JSA No.02/TSA/HSE/12/2025 | 2025-12-12 | 2025-12-12 | SWP-HSE-93 | Approved | Approved | 2026-02-02 | 2026-02-02 | Dismantle Tower | CMIPO26-000147 | 2026-01-15 | 1 |  |  | 0 |  |  |  | Complete | CMI Project | CMI
227 | CMI | RLC | Nasional | #NAME? | 2025-11-03 | R3100533 | ID-JK-02464 | PELEPAH INDAH | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Utara | JL.RAYA BOULEVARD BLOK LB 3 NO.6 , KEL.KELAPA GADING,KEC.KELAPA GADING | -6.15563 | 106.908 | 2906.38 | 20 |  | Rooftop | MT 4 Legs | Dismantle Equipment |  |  | dismantle | 2025-12-14 | 2025-12-21 | Expired |  | 2025-11-08 | 2025-11-08 |  |  | 2025-12-25 |  | 2026-03-04 |  |  |  |  | Inbound | 26.12.25 IDU 2pcs dipinjam MS 04.03.26 done inbound | 2025-11-25 | 2025-12-01 | 2025-12-04 |  | 2025-12-04 | 2025-12-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | Include Dism Tower | 2025-12-17 | 12 |  |  | 0 |  |  |  | Complete
228 | CMI | RLC | Nasional | #NAME? | 2025-12-04 | R3270472 | ID-JB-09610 | THE EDGE SUPERBLOCK | 10 | CMI | JAWA BARAT | Kota Cimahi | JL. RAYA BAROS NO. 57, KOTA CIMAHI, JAWA BARAT 40521 | -6.89755 | 107.537 | 436.3 | 6 |  | Rooftop | Pole | Dismantle Tower | Taufik Hidayat |  |  |  |  | NY Submit |  |  |  | drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | Drop |  | Drop |  |  | Drop |  |  |  | Drop
229 | CMI | RLC | Nasional | #NAME? | 2025-10-07 | E3500389 | ID-JI-06554 | BURNEH | 15 | EMA | JAWA TIMUR | Kab. Bangkalan | JL KH MUNIF NO 26 DESA BURNEH KECAMATAN BURNEH KAB BANGKALAN | -7.05249 | 112.785 | 22120.78 | 70 | IOH, Tsel, SF | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-10-03 | 2024-10-07 |  |  | 2026-02-11 |  | 2026-04-12 |  |  | 2026-02-18 |  | ATP App MS | 10.02.26 dism tsel 11.02.26 done HO equip tsel - dism IOH 12.02.26 done HO equip IOH 12.04.26 Inbound IOH | 2025-12-11 | 2025-12-19 | 2025-12-12 |  | 2025-12-19 | 2025-12-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-10-07 | 2025-10-07 | JSA No.08/TSA/HSE/10/2025 | 2025-10-07 | 2024-10-07 |  | Approved | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2025-12-31 | 12 |  |  | 0 |  |  |  | Complete | [9 empty] | CRQ000001052138
230 | CMI | RLC | Nasional | #NAME? | 2025-11-03 | R3100450 | ID-JK-01538 | KEBON SIRIH | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Pusat | Jl. Kebon Sirih No.1, RT.1/RW.7, Kb. Sirih, Kec. Menteng, Kota Jakarta Pusat, Daerah Khusus Ibukota Jakarta | -6.18313 | 106.833 | 853.6005 | 6 |  | Rooftop | Pole | Dismantle Equipment |  |  | Survey | 2025-11-05 | 2025-11-18 | Expired |  | 2025-10-08 | 2025-11-10 |  |  | 2025-12-16 |  |  |  |  | 2026-04-27 | 2026-04-27 | ATP App MS | 16.12.25 start dism equip | 2025-12-12 | 2025-12-15 | 2025-12-12 |  | 2025-12-15 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-11-10 | 2025-11-11 | JSA No.05/TSA/HSE/11/2025 | 2025-11-10 | 2025-11-12 |  | Approved | Approved |  |  | Dismantle Equipment | Include Reloc | 2026-01-28 | 0 |  |  | 0 |  |  |  | Complete
231 | CMI | RLC | Nasional | #NAME? | 2025-11-03 | R3100450 | ID-JK-01538 | KEBON SIRIH | 7 | CMI | DKI JAKARTA | Kota Administrasi Jakarta Pusat | JL. JENDRAL SUDIRMAN NO. 22 SEMPUR, BOGOR TENGAH | -6.18313 | 106.833 | 853.6005 | 6 |  | Rooftop | Pole | Relocation Equipment | Taufik Hidayat |  | Survey | 2025-11-05 | 2025-11-18 | Expired |  | 2025-10-08 | 2025-11-10 | [5 empty] | 2025-12-17 |  | 2026-04-27 | 2026-04-27 | ATP App MS | 17.12.25 start reinstall temporary 09.02.26 Perangkat done MOCN XLS | 2025-12-12 | 2025-12-15 | 2025-12-12 |  | 2025-12-15 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2025-11-10 | 2025-11-11 | JSA No.05/TSA/HSE/11/2025 | 2025-11-10 | 2025-11-12 |  | Approved | Approved |  |  | Relocation Equipment | EMAPO26-000056 | 2026-02-10 | 0 | EMAPO26-000138 | 2026-02-10 | 0 |  |  |  | Complete |  |  |  | ID-JK-04921 | E3100526 BIMANTARA
232 | CMI | RLC | Nasional | #NAME? | 2025-12-11 | R1200302 | ID-SU-02192 | BANGUN PURBA | 1 | CMI | SUMATERA UTARA | Kab. Deli Serdang | DSN/LINK.III,KEL.BANGUN PURBA , KEC.BANGUN PURBA,KAB.DELI SERDANG | 3.37203 | 98.8141 | 13212.913 | 71 | XL | Greenfield | SST 3 Legs | Dismantle Tower |  |  | Survey | 2025-12-13 | 2025-12-27 | Expired |  | 2025-12-16 | 2025-12-16 | 2026-06-01 | 2026-05-18 |  | 2026-06-11 |  |  |  |  | 2026-06-12 | BAST | 08.06.26 Start dismantle | 2026-04-08 | 2026-04-13 | 2026-04-09 | 2026-05-06 | 2026-05-08 | 2026-05-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 30.04.26 DRM 1 | 2025-12-16 | 2025-12-18 | JSA No.03/TSA/HSE/12/2025 | 2025-12-28 | 2025-12-31 | SWP-HSE-95 | Approved | Approved | 2026-06-12 | 2026-06-12 | Dismantle Tower | CMIPO26-002315 | 2026-07-07 | 56 |  |  | 0 |  |  |  | Complete | CMI Project |  |  | ID-SU-03892 | BANGUN PURBA | 3.37141 | 98.8149
233 | CMI | RLC | Nasional | #NAME? | 2025-12-11 | R1200302 | ID-SU-02192 | BANGUN PURBA | 1 | CMI | SUMATERA UTARA | Kab. Deli Serdang | DSN/LINK.III,KEL.BANGUN PURBA , KEC.BANGUN PURBA,KAB.DELI SERDANG | 3.37203 | 98.8141 | 13212.913 | 71 | XL | Greenfield | SST 3 Legs | Dismantle Equipment |  |  | Survey | 2025-12-13 | 2025-12-27 | Expired |  | 2025-12-16 | 2025-12-16 | 2026-06-01 |  | 2026-05-26 |  |  |  |  | 2026-06-18 |  | ATP App MS |  | 2026-04-08 | 2026-04-13 | 2026-04-09 | 2026-05-06 | 2026-05-08 | 2026-05-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 30.04.26 DRM 1 | 2025-12-16 | 2025-12-18 | JSA No.03/TSA/HSE/12/2025 | 2025-12-28 | 2025-12-31 |  | Approved | Approved |  |  | Dismantle Equipment | Include Reloc | 2026-07-07 | 56 |  |  | 0 |  |  |  | Complete | TSA |  |  | ID-SU-03892 | BANGUN PURBA | 3.37141 | 98.8149 |  | XLWO-20260522-00000051
234 | CMI | RLC | Nasional | #NAME? | 2025-12-11 | R1200302 | ID-SU-02192 | BANGUN PURBA | 1 | CMI | SUMATERA UTARA | Kab. Deli Serdang | DSN/LINK.III,KEL.BANGUN PURBA , KEC.BANGUN PURBA,KAB.DELI SERDANG | 3.37203 | 98.8141 | 13212.913 | 71 | XL | Greenfield | SST 3 Legs | Relocation Equipment |  |  | Survey | 2025-12-13 | 2025-12-27 | Expired |  | 2025-12-16 | 2025-12-16 | 2026-06-01 |  | 2026-05-26 |  |  | 2026-05-27 | 2026-05-28 | 2026-06-18 |  | ATP App MS |  | 2026-04-08 | 2026-04-13 | 2026-04-09 | 2026-05-06 | 2026-05-08 | 2026-05-12 | 1st BOQ App on ISAAC | 2026-05-21 |  |  | 2026-07-24 | 2026-07-28 | 2026-07-28 | 2nd BOQ App on ISAAC | 30.04.26 DRM 1 03.06.26 DRM 2 | 2025-12-16 | 2025-12-18 | JSA No.03/TSA/HSE/12/2025 | 2025-12-28 | 2025-12-31 |  | Approved | Approved |  |  | Relocation Equipment | EMAPO26-000871 | 2026-07-07 | 56 | NY release |  | 8 |  |  |  | PO Variation NY release ATP sirkulir operator | TSA |  |  | ID-SU-03892 | BANGUN PURBA | 3.37141 | 98.8149 |  | XLWO-20260522-00000051
235 | CMI | RLC | Nasional | #NAME? | 2025-12-15 | R3350436 | ID-JT-02700 | CIMANGGU CILACAP | 11 | CMI | JAWA TENGAH | Kab. Cilacap | BANTAR PANJANG RT003/005 , DS.BANTAR PANJANG KEC.CIMANGGU | -7.36012 | 108.854 | 13212.913 | 71 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-12-17 | 2025-12-23 | Expired |  | 2025-12-18 | 2025-12-18 |  | 2026-01-06 |  | 2026-01-24 |  |  |  | 2026-01-26 | 2026-01-26 | BAST | 20.01.26 Start dismantle | 2026-01-05 | 2026-01-14 | 2026-01-06 |  | 2026-01-14 | 2026-01-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-12-18 | 2025-12-19 | JSA No.05/TSA/HSE/12/2025 | 2025-12-28 | 2025-12-31 | SWP-HSE-96 | Approved | Approved | 2026-01-27 | 2026-01-28 | Dismantle Tower | CMIPO26-000315 | 2026-01-30 | 16 |  |  | 0 |  |  |  | FAC Submit | Lifi | TSA
236 | CMI | RLC | Nasional | #NAME? | 2025-12-15 | E1200357 | ID-KR-04110 | BENGKONG_HARAPAN | 2 | EMA | KEPULAUAN RIAU | Kota Batam | JL. BENGKONG HARAPAN I PERUM ESQARADA BATAM / KOMP. ESQARADA BENGKONG HARAPAN I BLOK C NO.1&2 BATU AMPAR | 1.15136 | 104.027 | 6803.725 | 37 | IOH | Greenfield | SST 4 Legs | Dismantle Tower | Darsim | +62 858-4610-2645 | Survey | 2025-12-17 | 2025-12-23 | Expired |  | 2025-12-20 | 2025-12-20 |  | 2026-01-26 |  | 2026-03-03 |  |  |  | 2026-03-05 | 2026-03-05 | BAST | 14.02.26 Start dismantle | 2026-01-08 | 2026-01-14 | 2026-01-08 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-12-20 | 2025-12-22 | JSA No.07/TSA/HSE/12/2025 | 2025-12-28 | 2025-01-02 | SWP-HSE-98 | Approved | Approved | 2026-03-05 |  | Dismantle Tower | EMAPO26-000078 | 2026-01-30 | 15 |  |  | 0 |  |  |  | Complete | CMI Project | CMI
237 | CMI | RLC | Nasional | #NAME? | 2025-12-15 | E1200391 | ID-KR-04142 | PINANG_IM3 | 2 | EMA | KEPULAUAN RIAU | Kota Tanjung Pinang | BUKIT CERMIN TAMAN BAHAGIA TANJUNG PINANG, KEC. TANJUNG PINANG BARAT, KOTA TANJUNG PINANG, PROV. KEPULAUAN RIAU | 0.92437 | 104.448 | 9236.076 | 52 |  | Greenfield | SST 4 Legs | Dismantle Tower | Darman | +62 878-6524-7367 | Survey | 2025-12-17 | 2025-12-23 | Expired |  | 2025-12-17 | 2025-12-17 |  | 2026-01-26 |  | 2026-03-03 |  |  |  | 2026-03-03 | 2026-03-03 | BAST | 14.02.26 Start dismantle | 2026-01-08 | 2026-01-08 | 2026-01-08 | NA | 2026-01-08 | 2026-01-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2025-12-17 | 2025-12-19 | JSA No.04/TSA/HSE/12/2025 | 2025-12-22 | 2025-12-22 | SWP-HSE-94 | Approved | Approved | 2026-03-04 | 2026-03-05 | Dismantle Tower | EMAPO26-000044 | 2026-01-13 | #NUM! |  |  | 0 |  |  |  | Complete
238 | CMI | RLC | Nasional | #NAME? | 2025-12-15 | E9400005 | ID-PA-07931 | TVRI BIAK | 20 | EMA | PAPUA | Kab. Biak Numfor | DESA YAFDAS KEC. SAMOFA KAB. BIAK NUMFOR PAPUA | -1.16222 | 136.072 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Dismantle | 2026-03-10 | 2026-03-16 | Expired |  | 2025-12-22 | 2026-01-07 | 2026-03-24 | 2026-02-11 |  | 2026-06-08 |  |  |  |  | 2026-06-15 | BAST | 10.03.26 Plan Exe | 2026-01-08 | 2026-01-14 | 2026-01-08 | 2026-06-02 | 2026-07-02 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-01-07 | 2026-01-08 | JSA No.03/TSA/HSE/01/2026 | 2026-01-12 | 2026-01-13 | SWP-HSE-101 | Approved | Approved | 2026-06-18 | 2026-06-18 | Dismantle Tower | NY release | 2026-02-02 | 0 |  |  | 0 |  |  |  | waiting boq app on ISAAC | CMI Project
239 | CMI | RLC | Nasional | #NAME? | 2025-12-22 | R7300040 | ID-SN-00590 | AL MARKAS ISLAMI | 19 | CMI | SULAWESI SELATAN | Kota Makassar | JL. ALMARKAS AL ISLAMI NO.8 , RT 003/RW 004, KELURAHAN LEMBO, KECAMATAN TALLO, KOTA MAKASSAR, SULAWESI SELATAN | -5.12453 | 119.426 | 335.3425 | 12 | IOH | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2025-12-27 | 2025-12-30 | Expired |  | 2025-12-24 | 2026-01-05 |  | 2026-01-26 |  | 2026-02-04 |  |  |  | 2026-02-04 | 2026-02-04 | BAST | 31.01.26 Start Dismantle | 2026-01-08 | 2026-01-14 | 2026-01-09 |  | 2026-01-14 | 2026-01-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-01-05 |  | JSA No.02/TSA/HSE/01/2026 | 2026-01-05 | 2025-01-06 |  | Submit | Approved | 2026-02-06 | 2026-02-06 | Dismantle Tower | CMIPO26-000314 | 2026-01-30 | 16 |  |  | 0 |  |  |  | Complete
240 | CMI | RLC | Nasional | #NAME? | 2025-12-22 | E3300153 | ID-JT-05864 | GISIKDRONO | 11 | EMA | JAWA TENGAH | Kota Semarang | JL. SRI REJEKI I/2 KEC. GISIKDRONO SEMARANG | -6.99276 | 110.384 | 8487.28 | 42 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2025-12-27 | 2025-12-30 | Expired |  | 2025-12-24 | 2026-01-07 | drop | [8 empty] | Drop | Survey only | 2026-01-08 | 2026-01-12 | 2026-01-08 |  | 2026-01-12 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | BOQ Survey only | 2026-01-07 |  | JSA No.05/TSA/HSE/01/2026 | 2026-01-12 | 2026-01-13 | SWP-HSE-102 | Submit | Approved |  |  | Dismantle Tower | EMAPO26-000072 PO cancel | 2026-01-30 | Drop | NY release |  | Drop |  |  |  | Suervey only, PO cancel waiting PO Survey release | CMI Project | CMI
241 | CMI | RLC | Nasional | #NAME? | 2025-12-22 | R3350421 | ID-JT-02685 | KARANGJUNTI | 11 | CMI | JAWA TENGAH | Kab. Brebes | KARANG JUNTI RT05/02 , KB BREBES - JAWA TENGAH | -6.91628 | 108.793 | 13212.913 | 71 |  | Greenfield | SST 3 Legs | Dismantle Tower |  |  | Survey | 2025-12-27 | 2025-12-30 | Expired |  | 2025-12-31 | 2026-01-07 | 2026-02-10 |  |  | 2026-06-30 |  |  |  |  | 2026-06-30 | BAST |  | 2026-01-08 | 2026-02-25 | 2026-01-08 |  | 2026-02-25 | 2026-02-25 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-01-07 | 2026-01-13 | JSA No.04/TSA/HSE/01/2026 | 2026-01-12 | 2026-01-13 | SWP-HSE-103 | Approved | Approved | 2026-07-06 | 2026-07-07 | Dismantle Tower | CMIPO26-001081 | 2026-03-16 | 19 |  |  | 0 |  |  |  | Complete | CMI Project
242 | CMI | RLC | Nasional | #NAME? | 2025-12-15 | R3350436 | ID-JT-02700 | CIMANGGU CILACAP | 11 | CMI | JAWA TENGAH | Kab. Cilacap | BANTAR PANJANG RT003/005 , DS.BANTAR PANJANG KEC.CIMANGGU | -7.36012 | 108.854 | 13212.913 | 71 |  | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-12-17 | 2025-12-23 | Expired |  | 2025-12-18 | 2025-12-18 | drop | [8 empty] | Drop | Dismantle Equipment by MS XLS | [6 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-12-18 | 2025-12-19 | JSA No.05/TSA/HSE/12/2025 | 2025-12-28 | 2025-12-31 |  | Approved | Approved |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Dismantle Equipment by MS XLS
243 | CMI | RLC | Nasional | #NAME? | 2025-12-22 | E3300153 | ID-JT-05864 | GISIKDRONO | 11 | EMA | JAWA TENGAH | Kota Semarang | JL. SRI REJEKI I/2 KEC. GISIKDRONO SEMARANG | -6.99276 | 110.384 | 8487.28 | 42 |  | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-12-24 | 2026-01-07 | drop | [8 empty] | Drop |  | 2026-01-08 | 2026-01-12 | 2026-01-08 |  | 2026-01-12 | 2026-01-12 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-01-07 |  | JSA No.05/TSA/HSE/01/2026 | 2026-01-12 | 2026-01-13 |  | Submit | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2026-01-30 | Drop |  |  | Drop |  |  |  | Drop | CMI Project | CMI
244 | CMI | RLC | Nasional | #NAME? | 2025-12-22 | R3350421 | ID-JT-02685 | KARANGJUNTI | 11 | CMI | JAWA TENGAH | Kab. Brebes | KARANG JUNTI RT05/02 , KB BREBES - JAWA TENGAH | -6.91628 | 108.793 | 13212.913 | 71 |  | Greenfield | SST 3 Legs | Dismantle Equipment |  |  | Survey | 2025-12-27 | 2025-12-30 | Expired |  | 2025-12-31 | 2026-01-07 | 2026-02-10 |  | 2026-06-22 | [6 empty] | Dismantle Perangkat | 31.05.26 dismantle IOH 22.06.26 dismantle XLS | 2026-01-08 | 2026-02-25 | 2026-01-08 |  | 2026-02-25 | 2026-02-25 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-01-07 | 2026-01-13 | JSA No.04/TSA/HSE/01/2026 | 2026-01-12 | 2026-01-13 |  | Approved | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2026-03-16 | 19 |  |  | 0 |  |  |  | 03.07.26 ATP IOH done upload ISAAC XLS NY take data ATP | TSA |  |  | ID-JT-17956 | LOSARI KARANGJUNTI | -6.9143 | 108.7942 | CR-20260529-00000297
245 | CMI | RLC | Nasional | #NAME? | 2025-12-15 | E9400005 | ID-PA-07931 | TVRI BIAK | 20 | EMA | PAPUA | Kab. Biak Numfor | DESA YAFDAS KEC. SAMOFA KAB. BIAK NUMFOR PAPUA | -1.16222 | 136.072 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-12-17 | 2025-12-23 | Expired |  | 2025-12-22 | 2026-01-07 | drop | [8 empty] | Drop | Dismantle Equipment by MNO | [6 empty] | NY Submit | [6 empty] | NY Submit |  | 2026-01-07 |  | JSA No.03/TSA/HSE/01/2026 | 2026-01-12 |  |  | Submit | Submit |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Dismantle Equipment by Operator
246 | CMI | RLC | Nasional | #NAME? | 2025-12-15 | E1200357 | ID-KR-04110 | BENGKONG_HARAPAN | 2 | EMA | KEPULAUAN RIAU | Kota Batam | JL. BENGKONG HARAPAN I PERUM ESQARADA BATAM / KOMP. ESQARADA BENGKONG HARAPAN I BLOK C NO.1&2 BATU AMPAR | 1.15136 | 104.027 | 6803.725 | 37 | IOH | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Survey | 2025-12-17 | 2025-12-23 | Expired |  | 2025-12-20 | 2025-12-20 | drop | [8 empty] | Drop | Dismantle Equipment by MNO | [6 empty] | NY Submit | [6 empty] | NY Submit |  | 2025-12-20 | 2025-12-22 | JSA No.07/TSA/HSE/12/2025 | 2025-12-28 | 2025-01-02 |  | Approved | Approved |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Dismantle Equipment by MNO
247 | CMI | RLC | Nasional | #NAME? | 2025-11-06 | R3580695 | ID-JI-10335 | 3G_Kupang Krajan Sawahan | 14 | CMI | JAWA TIMUR | Kota Surabaya | Jl. Banyu Urip 344 Rt.02/01 Kel.Kupang Krajan Kec. Sawahan surabaya, Ja-Tim 60253 | -7.26834 | 112.715 | 3713.64 | 25 |  | Rooftop | MT 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2025-12-08 | 2025-12-08 |  |  | 2026-03-02 |  | 2026-07-14 |  |  |  |  | Inbound | 14.07.26 Inbound Material | 2026-04-13 | 2026-04-15 |  |  |  | 2026-04-22 | 1st BOQ App on ISAAC | 2026-04-15 |  |  |  |  | 2026-04-22 | 2nd BOQ App on ISAAC |  | 2025-12-08 | 2025-12-10 | JSA No.01/TSA/HSE/12/2025 | 2025-12-09 | 2025-12-11 |  | Approved | Approved |  |  | Dismantle Equipment | CMIPO26-001561 | 2026-05-07 | 15 |  |  | 105 |  |  |  | Complete | TSA
248 | CMI | RLC | Nasional | #NAME? | 2025-12-22 | R7300040 | ID-SN-00590 | AL MARKAS ISLAMI | 19 | CMI | SULAWESI SELATAN | Kota Makassar | JL. ALMARKAS AL ISLAMI NO.8 , RT 003/RW 004, KELURAHAN LEMBO, KECAMATAN TALLO, KOTA MAKASSAR, SULAWESI SELATAN | -5.12453 | 119.426 | 335.3425 | 12 | IOH | Rooftop | Pole | Dismantle Equipment |  |  | Survey | 2025-12-27 | 2025-12-30 | Expired |  | 2025-12-24 | 2026-01-05 | drop | [8 empty] | Drop | Dismantle Equipment by MNO | [6 empty] | NY Submit | [6 empty] | NY Submit |  | 2026-01-05 |  | JSA No.02/TSA/HSE/01/2026 | 2026-01-05 | 2026-01-06 | SWP-HSE-100 | Submit | Approved |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Dismantle Equipment by MNO
249 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3500264 | ID-JI-06431 | WATUKOSEK2 | 15 | EMA | JAWA TIMUR | Kab. Mojokerto | PUSAT PENDIDIKAN DAN PELATIHAN BRIMOB, JL. RAYA WATUKOSEK GEMPOL PASURUAN | -7.58376 | 112.654 |  | 52 | IOH | Greenfield | SST 3 Legs | Dismantle Tower | [5 empty] | NY Submit |  |  |  | drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | Drop |  | Drop |  |  | Drop |  |  |  | Drop
250 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3500264 | ID-JI-06431 | WATUKOSEK2 | 15 | EMA | JAWA TIMUR | Kab. Mojokerto | PUSAT PENDIDIKAN DAN PELATIHAN BRIMOB, JL. RAYA WATUKOSEK GEMPOL PASURUAN | -7.58376 | 112.654 |  | 52 | IOH | Greenfield | SST 3 Legs | Dismantle Equipment | [5 empty] | NY Submit |  |  |  | drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop
251 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3500264 | ID-JI-06431 | WATUKOSEK2 | 15 | EMA | JAWA TIMUR | Kab. Mojokerto | PUSAT PENDIDIKAN DAN PELATIHAN BRIMOB, JL. RAYA WATUKOSEK GEMPOL PASURUAN | -7.58376 | 112.654 |  | 52 | IOH | Greenfield | SST 3 Legs | Relocation Equipment | [5 empty] | NY Submit |  |  |  | drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Drop
252 | CMI | RLC | Nasional | #NAME? | 2025-06-23 | E3600061 | ID-BT-06774 | PARUNGSARI | 6 | EMA | BANTEN | Kab. Lebak | JL. RAYA CIPANAS KP. CURUNG PASIR | -6.36815 | 106.283 | 22120.78 | 70 | IOH, Tsel, SF | Greenfield | Combat | Relocation Equipment to Permanent Site | Taufik Hidayat |  | Reloc | 2026-01-12 | 2026-01-19 | Expired |  | 2025-07-28 | 2025-07-28 | [5 empty] | 2026-01-18 | 2026-01-18 | 2026-01-27 |  | ATP App MS | 13.01.26 Dismantle equip XLS 14.01.26 Reinstall equip XLS 16.01.26 OA XLS 17.01.26 Dismantle equip IOH 18.01.26 OA IOH | [6 empty] | NY Submit | 2026-01-14 | 2026-01-21 |  | 2026-04-02 | 2026-04-23 | 2026-04-24 | 2nd BOQ App on ISAAC | 01.04.26 done DRM | 2025-07-28 | 2025-07-31 | JSA No.05/TSA/HSE/07/2025 | 2025-07-28 | 2025-07-31 |  | Approved | Approved | 2026-06-02 | 2026-06-02 | Relocation Equipment |  |  | 0 | NY release |  | 103 |  |  |  | PO NY Release | CMI Project | CMI |  | ID-BT-16555 | RANGKASBITUNG LEBAK | -6.367087 | 106.283023 | CR-20260107-00000380 CR-20260109-00000299 CR-20260109-00000359 CR-20260109-00000372 | XLWO-20260107-00000501 | CRQ000001045499
253 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | R3580021 | ID-JI-00517 | SUNGKONO | 15 | CMI | JAWA TIMUR | Kota Malang | JL. TUTUT IV, RT 07 RW 01, KEL. ARJOWINANGUN, KEC.KEDUNG KANDANG, KOTA MALANG, JAWA TIMUR | -8.04061 | 112.6416 | 6159 | 42 |  | Greenfield | SST 3 Legs | Dismantle Tower |  |  | Survey | 2026-05-06 | 2026-05-12 | Expired |  | 2026-03-13 | 2026-04-02 | 2026-06-03 |  |  | 2026-05-09 |  |  |  |  | 2026-05-09 | BAST | 08.05.26 Start Dismantle | 2026-04-15 | 2026-04-27 | 2026-04-15 |  | 2026-04-27 | 2026-04-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-04-06 | 2026-04-14 | JSA No.11/TSA/HSE/04/2026 | 2026-04-06 | 2026-04-08 | SWP-HSE-111 | Approved | Approved | 2026-05-11 | 2026-05-11 | Dismantle Tower | CMIPO26-001560 | 2026-05-07 | 10 |  |  | 0 |  |  |  | Complete
254 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3100328 | ID-JK-04732 | MIC_ST_KRL_ANCOL | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Utara | Ancol, Pademangan Bar., Kec. Pademangan, Jkt Utara, Daerah Khusus Ibukota Jakarta | -6.12795 | 106.8454 | 91.46 | 3 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-04-17 | 2026-04-23 | Expired |  | 2026-03-31 | 2026-04-06 | 2026-05-13 | 2026-04-16 |  | 2026-04-17 |  |  |  | 2026-04-17 | 2026-04-17 | BAST |  | 2026-04-09 | 2026-04-13 | 2026-04-09 |  | 2026-04-13 | 2026-04-14 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-04-06 | 2026-04-13 | JSA No.10/TSA/HSE/04/2026 | 2026-04-06 | 2026-04-08 | SWP-HSE-110 | Approved | Approved | 2026-04-21 | 2026-04-21 | Dismantle Tower | EMAPO26-000503 | 2026-04-20 | 6 |  |  | 0 |  |  |  | Complete
255 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | R3350028 | ID-JT-00913 | AGUNG SELATAN | 11 | CMI | JAWA TENGAH | Kota Surakarta |  | -7.5556 | 110.8382 | 218.15 | 6 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-04-14 | 2026-04-27 | Expired |  | 2026-04-16 | 2026-04-16 | drop | [8 empty] | Drop | Survey only | 2026-04-17 |  | 2026-04-21 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit |  | 2026-04-17 | 2026-04-22 | JSA No.15/TSA/HSE/04/2026 | 2026-04-17 | 2026-04-17 | SWP-HSE-115 | Approved | Approved |  |  | Dismantle Tower | NY release |  | Drop |  |  | Drop |  |  |  | Pole masih ada tenant - pengajuan BOQ survey only | TSA
256 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3300036 | ID-JT-05749 | HOTEL_ALEXANDER | 11 | EMA | JAWA TENGAH | Kota Tegal |  | -6.86966 | 109.1342 | 1234.512 | 12 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-04-14 | 2026-04-27 | Expired |  | 2026-04-16 | 2026-04-16 | 2026-06-08 | 2026-06-04 |  | 2026-06-10 |  |  |  |  | 2026-06-10 | BAST |  | 2026-05-05 | 2026-05-28 | 2026-05-06 |  | 2026-05-28 | 2026-05-29 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-04-23 | 2026-04-24 | JSA No.17/TSA/HSE/04/2026 | 2026-04-23 | 2026-04-23 | SWP-HSE-117 | Approved | Approved | 2026-06-11 | 2026-06-11 | Dismantle Tower | EMAPO26-000790 | 2026-06-19 | 21 |  |  | 0 |  |  |  | Complete
257 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3300056 | ID-JT-05769 | PURWOKERTO_NEW | 11 | EMA | JAWA TENGAH | Kab. Banyumas |  | -7.42596 | 109.2347 | 1234.512 | 12 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-04-14 | 2026-04-27 | Expired |  | 2026-04-16 | 2026-04-16 | 2026-05-01 | 2026-04-29 |  | 2026-04-30 |  |  |  |  | 2026-04-30 | BAST |  | 2026-04-17 | 2026-04-24 | 2026-04-21 |  | 2026-04-24 | 2026-04-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-04-17 | 2026-04-22 | JSA No.16/TSA/HSE/04/2026 | 2026-04-17 | 2026-04-17 | SWP-HSE-116 | Approved | Approved | 2026-05-05 | 2026-05-05 | Dismantle Tower | EMAPO26-000557 | 2026-05-06 | 9 |  |  | 0 |  |  |  | Complete
258 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E7100022 | ID-SU-07561 | HOTEL_QUALITY | 20 | EMA | SULAWESI UTARA | Kota Manado | Sario Tumpaan, Kota Manado, Sulawesi Utara | 1.46481 | 124.8288 | 274.38 | 3 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-05-05 | 2026-05-17 | Expired |  | 2026-03-15 | 2026-04-16 | 2026-06-30 | 2026-06-09 |  | 2026-06-17 |  |  |  |  | 2026-06-17 | BAST | 13.06.26 Start dismantle 17.06.26 BAST sign, lanjut perapihan | 2026-05-05 | 2026-06-04 | 2026-05-06 |  | 2026-06-04 | 2026-06-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-04-30 | 2026-05-02 | JSA No.18/TSA/HSE/04/2026 | 2026-04-30 | 2026-05-02 | SWP-HSE-118 | Approved | Approved | 2026-06-23 | 2026-06-23 | Dismantle Tower | EMAPO26-000789 | 2026-06-19 | 14 |  |  | 0 |  |  |  | Complete
259 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E7100037 | ID-SU-07576 | ROAD TO TAMAKO | 20 | EMA | SULAWESI UTARA | Kab. Kepulauan Sangihe | Belengang, Kabupaten Kepulauan Sangihe, Sulawesi Utara | 3.4854 | 125.4893 | 57199.8 | 100 |  | Greenfield | SST | Dismantle Tower |  |  | Survey | 2026-03-12 | 2026-03-17 | Expired |  | 2026-03-16 | 2026-04-10 | 2026-05-22 | 2026-04-23 |  | 2026-06-08 | [5 empty] | Dismantle | 09.05.26 Start Dismantle | 2026-04-14 | 2026-04-17 | 2026-04-14 | 2026-06-02 | 2026-07-02 | 2026-07-13 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-04-15 |  | JSA No.14/TSA/HSE/04/2026 | 2026-04-15 |  | SWP-HSE-114 | Submit | Submit | 2026-07-01 | 2026-07-02 | Dismantle Tower | EMAPO26-000556 | 2026-05-05 | #NUM! |  |  | 0 |  |  |  | PO EMAPO26-000556 cancel waiting release new PO | CMI Project
260 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | R3580019 | ID-JI-00505 | GLADAKBIDUNG | 15 | CMI | JAWA TIMUR | Kab. Jember | Jl. Dusun Sumuran, Durenan, Klompangan, Kec. Ajung, Kabupaten Jember | -8.23315 | 113.6826 | 3637.98 | 32 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-04-03 | 2026-04-16 | Expired |  | 2026-04-10 | 2026-05-03 | 2026-07-27 |  |  | 2026-07-03 |  |  |  |  | 2026-07-03 | BAST | 29.06.26 start dismantle | 2026-05-12 | 2026-06-04 | 2026-05-13 |  | 2026-06-04 | 2026-06-04 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-05-19 | 2026-05-22 | JSA No.22/TSA/HSE/05/2026 | 2026-05-19 | 2026-05-20 | SWP-HSE-122 | Approved | Approved | 2026-07-08 | 2026-07-08 | Dismantle Tower | CMIPO26-002158 | 2026-06-19 | 15 |  |  | 0 |  |  |  | Complete
261 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | R3580020 | ID-JI-00506 | KLOMPANGAN | 15 | CMI | JAWA TIMUR | Kab. Jember | Sumuran, Klompangan, Kec. Ajung, Kabupaten Jember | -8.2368 | 113.6553 | 6159 | 42 |  | Greenfield | SST 3 Legs | Dismantle Tower |  |  | Survey | 2026-04-03 | 2026-04-16 | Expired |  | 2026-04-10 | 2026-05-03 | 2026-07-19 | 2026-06-08 |  | 2026-07-07 |  |  |  |  | 2026-07-07 | BAST | 03.07.26 start dismantle | 2026-05-12 | 2026-06-04 | 2026-05-13 |  | 2026-06-04 | 2026-06-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-05-18 | 2026-05-22 | JSA No.20/TSA/HSE/05/2026 | 2026-05-18 | 2026-05-18 | SWP-HSE-120 | Approved | Approved | 2026-07-08 | 2026-07-14 | Dismantle Tower | CMIPO26-002158 | 2026-06-19 | 14 |  |  | 0 |  |  |  | Complete
262 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3500374 | ID-JI-06539 | PT_NEWCON | 15 | EMA | JAWA TIMUR | Kota Surabaya | Twenty - One Building, Mojo, Kec. Gubeng, Surabaya, Jawa Timur 60285 | -7.2656 | 112.7649 | 2490.696 | 20 |  | Rooftop | MT 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-06-19 | 2026-06-22 | 2026-07-08 | 2026-07-01 |  | 2026-07-11 |  |  |  |  | 2026-07-28 | BAST | 03.07.26 Plan dismantle | 2026-06-24 | 2026-06-25 | 2026-06-24 |  | 2026-06-25 | 2026-06-30 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-06-23 | 2026-06-27 | JSA No.37/TSA/HSE/06/2026 | 2026-06-23 | 2026-06-25 | SWP-HSE-137 | Approved | Approved | 2026-07-28 |  | Dismantle Tower | EMAPO26-000989 | 2026-07-27 | 27 |  |  | 0 |  |  |  | Complete
263 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | R3300363 | ID-JT-00007 | HOTEL HORIZON | 11 | CMI | JAWA TENGAH | Kota Semarang | Jl. Kyai H. Ahmad Dahlan No.2, Karangkidul, Kec. Semarang Tengah, Kota Semarang, Jawa Tengah 50136 | -6.98995 | 110.4246 | 218.15 | 6 | XL | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-05-11 | 2026-05-17 | Expired |  | 2026-05-13 | 2026-05-13 | 2026-08-23 | 2026-07-15 |  | 2026-07-24 |  |  |  |  | 2026-07-27 | BAST | waiting BAST dari joko dedoyo | 2026-06-30 | 2026-07-03 | 2026-07-04 |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | 28.05.26 BOQ mentahan | 2026-06-03 | 2026-06-04 | JSA No.30/TSA/HSE/06/2026 | 2026-06-03 | 2026-06-05 | SWP-HSE-130 | Approved | Approved | 2026-07-28 | 2026-07-28 | Dismantle Tower | NY release |  | 0 |  |  | 0 |  |  |  | PO NY Release
264 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3300295 | ID-JT-06005 | SUDIROPRAJAN | 11 | EMA | JAWA TENGAH | Kota Surakarta |  | -7.57059 | 110.8334 | 598.092 | 4 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-05-11 | 2026-05-17 | Expired |  | 2026-05-11 | 2026-05-20 | 2026-08-14 | 2026-07-01 |  | 2026-07-24 | [5 empty] | Dismantle | waiting BAST dari joko dedoyo | 2026-05-20 | 2026-06-24 | 2026-05-21 |  | 2026-06-24 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | 18.05.16 BOQ mentahan | 2026-06-03 | 2026-06-04 | JSA No.27/TSA/HSE/06/2026 | 2026-06-03 | 2026-06-05 | SWP-HSE-127 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0 |  |  |  | waiting BAST from team
265 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E7400036 | ID-SG-07844 | V_WANCI | 20 | EMA | SULAWESI TENGGARA | Kab. Wakatobi | Mandati II, Kabupaten Wakatobi, Sulawesi Tenggara | -5.32734 | 123.541 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  |  | 2026-04-17 | 2026-04-23 | Expired |  | 2026-02-16 | 2026-02-18 | 2026-08-17 |  |  | 2026-05-16 |  |  |  |  | 2026-05-16 | BAST |  | 2026-03-31 | 2026-04-02 | 2026-04-03 | 2026-06-02 | 2026-07-02 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-02-18 |  | JSA No.06/TSA/HSE/02/2026 | 2026-02-18 |  | SWP-HSE-105 | Submit | Submit | 2026-05-19 | 2026-05-19 | Dismantle Tower | NY release | 2026-04-14 | 0 |  |  | 0 |  |  |  | waiting boq app on ISAAC | CMI Project
266 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | R3580028 | ID-JI-00589 | LESTARI UTARA | 15 | CMI | JAWA TIMUR | Kota Batu | Ngaglik, Kota Batu, Jawa Timur | -7.86299 | 112.5196 | 6159 | 42 |  | Greenfield | SST 3 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-03-13 | 2026-04-02 | 2026-12-08 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | 22.05.26 boq mentahan | 2026-04-06 | 2026-04-16 | JSA No.12/TSA/HSE/04/2026 | 2026-04-06 | 2026-04-08 | SWP-HSE-112 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
267 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3500077 | ID-JI-06245 | TULUNGAGUNG_KOTA | 15 | EMA | JAWA TIMUR | Kab. Tulungagung | Mangunsari, Kabupaten Tulungagung, Jawa Timur | -8.05376 | 111.8935 | 8462.04 | 40 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-04-13 | 2026-04-26 | Expired |  | 2026-04-13 | 2026-04-14 | 2026-11-08 | [8 empty] | Survey Report |  | 2026-05-20 | 2026-06-24 | 2026-05-21 |  | 2026-06-24 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-06-10 | 2026-06-27 | JSA No.34/TSA/HSE/06/2026 | 2026-06-10 | 2026-06-18 | SWP-HSE-134 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
268 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | R3500027 | ID-JI-11514 | SUKOSARI | 15 | CMI | JAWA TIMUR | Kab. Ponorogo |  | -7.79537 | 111.4473 | 6781.005 | 42 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-04-03 | 2026-04-16 | Expired |  | 2026-04-13 | 2026-05-03 | 2026-10-31 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | 14.04.26 boq mentahan | 2026-06-05 | 2026-06-05 | JSA No.31/TSA/HSE/06/2026 | 2026-06-05 | 2026-06-05 | SWP-HSE-131 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
269 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E3300157 | ID-JT-05868 | MENOREH_NEW | 11 | EMA | JAWA TENGAH | Kota Semarang |  | -7.01101 | 110.3918 | 773.94 | 6 |  | Rooftop | Pole | Dismantle Tower |  |  |  | 2026-04-17 | 2026-04-30 | Expired |  | 2026-04-18 | 2026-04-18 | 2026-11-30 | [8 empty] | Survey Report |  | 2026-05-21 |  | 2026-05-26 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit |  | 2026-06-10 | 2026-06-22 | JSA No.33/TSA/HSE/06/2026 | 2026-06-10 | 2026-06-18 | SWP-HSE-133 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
270 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E6400083 | ID-KI-07469 | RUKO_BELIBIS | 18 | EMA | KALIMANTAN TIMUR | Kota Samarinda |  | -0.48381 | 117.1524 | 14671.332 | 12 |  | Rooftop | Pole | Dismantle Tower | [5 empty] | NY Submit |  |  |  | 2026-12-31 | [8 empty] | NY Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
271 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | E7100038 | ID-SU-07577 | V_TAHUNA | 20 | EMA | SULAWESI UTARA | Kab. Kepulauan Sangihe | Soataloara II, Kabupaten Kepulauan Sangihe, Sulawesi Utara | 3.61121 | 125.4899 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-05-07 | 2026-05-13 | Expired |  | 2026-05-09 | 2026-05-09 | 2026-12-02 | [8 empty] | Survey Report |  | 2026-05-18 | 2026-07-07 | 2026-07-07 | 2026-07-14 |  |  | BAN App | [6 empty] | NY Submit | Waiting BAN App | 2026-05-21 | 2026-05-22 | JSA No.23/TSA/HSE/05/2026 | 2026-05-21 | 2026-05-22 | SWP-HSE-123 | Approved | Approved | 2026-07-24 |  | Dismantle Tower | NY release |  | 0 |  |  | 0 |  |  |  | Waiting PO release & BAN App | CMI Project
272 | CMI | RLC | Nasional | #NAME? | 2025-08-06 | E3500373 | ID-JI-06538 | HOTEL CORE SBY | 15 | EMA | JAWA TIMUR | Kota Surabaya | JL MANYAR KERTOARJO 5 NO 62 SURABAYA | -7.27909 | 112.765 | 805.62 | 2 x 9 | IOH | Rooftop | Pole | Dismantle Tower | [5 empty] | NY Submit |  | 2026-01-13 | 2026-01-14 | 2026-08-10 | 2026-07-01 | [7 empty] | RFD App | 02.08.26 Start dismantle | 2026-01-30 | 2026-02-18 | 2026-02-10 |  | 2026-02-19 | 2026-02-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-01-14 | 2026-01-15 | JSA No.05/TSA/HSE/01/2026 | 2026-01-15 | 2026-01-21 | SWP-HSE-104 | Approved | Approved |  |  | Dismantle Tower | EMAPO26-000336 | 2026-02-25 | 6 |  |  | 0 |  |  |  |  | CMI Project | CMI
273 | CMI | RLC | Nasional | #NAME? | 2025-08-06 | E3500373 | ID-JI-06538 | HOTEL CORE SBY | 15 | EMA | JAWA TIMUR | Kota Surabaya | JL MANYAR KERTOARJO 5 NO 62 SURABAYA | -7.27909 | 112.765 | 805.62 | 2 x 9 | IOH | Rooftop | Pole | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-01-13 | 2026-01-14 | 2026-08-10 |  | 2026-07-24 |  | 2026-07-24 |  |  |  |  | Inbound | HO ke Protelindo | 2026-01-30 | 2026-02-18 | 2026-02-10 |  | 2026-02-19 | 2026-02-19 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-01-14 | 2026-01-15 | JSA No.05/TSA/HSE/01/2026 | 2026-01-15 | 2026-01-21 |  | Approved | Approved |  |  | Dismantle Equipment | Include Dism Tower | 2026-02-25 | 6 |  |  | 0 |  |  |  | done dismantle perangkat | CMI Project | CMI
274 | CMI | RLC | Nasional | #NAME? | 2025-08-06 | E3500373 | ID-JI-06538 | HOTEL CORE SBY | 15 | EMA | JAWA TIMUR | Kota Surabaya | JL MANYAR KERTOARJO 5 NO 62 SURABAYA | -7.27909 | 112.765 | 805.62 | 2 x 9 | IOH | Rooftop | Pole | Relocation Equipment |  |  | Reloc | 2026-07-21 | 2026-08-03 | Expired |  | 2026-01-13 | 2026-01-14 | Drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2026-01-14 | 2026-01-15 | JSA No.05/TSA/HSE/01/2026 | 2026-01-15 | 2026-01-21 |  | Approved | Approved |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop |  |  |  | Dismantle Drop
275 | CMI | RLC | Nasional | #NAME? | 2026-04-22 | E3500307 | ID-JI-06472 | MOROKREMBANGAN | 15 | EMA | JAWA TIMUR | Kota Surabaya | KOMPLEKS KODIKLATAL JL BUMIMORO MOROKREMBANGAN SURABAYA | -7.21741 | 112.71696 | 5987.15 | 30 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-04-23 | 2026-05-08 | 2026-06-30 |  |  | 2026-06-25 |  |  |  |  | 2026-06-26 | BAST |  | 2026-05-09 | 2026-05-28 | 2026-05-11 |  | 2026-05-28 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-05-11 | 2026-05-15 | JSA No.19/TSA/HSE/05/2026 | 2026-05-11 | 2026-05-13 | SWP-HSE-119 | Approved | Approved | 2026-07-06 | 2026-07-22 | Dismantle Tower | EMAPO26-000792 | 2026-06-19 | 0 |  |  | 0 |  |  |  | Complete
276 | CMI | RLC | Nasional | #NAME? | 2026-01-19 | E3500307 | ID-JI-06472 | MOROKREMBANGAN | 15 | EMA | JAWA TIMUR | Kota Surabaya | KOMPLEKS KODIKLATAL JL BUMIMORO MOROKREMBANGAN SURABAYA | -7.21741 | 112.71696 | 5987.15 | 30 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-04-23 | 2026-05-08 | 2026-06-30 |  | 2026-06-21 |  | 2026-07-14 |  |  |  |  | Inbound | 23.06.26 inbound material IOH 14.07.26 inbound material XLS | 2026-05-09 | 2026-05-28 | 2026-05-11 |  | 2026-05-28 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | Include Dism Tower | 2026-06-19 | 0 |  |  | 0 |  |  |  | Complete
277 | CMI | RLC | Nasional | #NAME? | 2026-01-19 | E3500307 | ID-JI-06472 | MOROKREMBANGAN | 15 | EMA | JAWA TIMUR | Kota Surabaya | KOMPLEKS KODIKLATAL JL BUMIMORO MOROKREMBANGAN SURABAYA | -7.21741 | 112.71696 | 5987.15 | 30 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Relocation Equipment | [5 empty] | NY Submit |  | 2026-04-23 | 2026-05-08 | drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop
278 | CMI | RLC | Nasional | #NAME? | 2026-04-22 | R3270184 | ID-JB-09545 | SETRAINDAH BARAT | 10 | CMI | JAWA BARAT | Kota Bandung | JL. SUKAMULYA INDAH NO. 3, KP. KENDAL GEDE RT 06 RW 02, KEL. SUKAGALIH, KEC. SUKAJADI, KOTA BANDUNG [40163] | -6.88585 | 107.58686 | 1817.0805 | 18 | IOH, XL | Rooftop | Pole | Dismantle Tower | [5 empty] | NY Submit |  | 2026-05-20 | 2026-05-22 | 2026-08-19 | [8 empty] | Survey Report |  | 2026-07-24 |  | 2026-07-24 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit | 22.05.26 boq mentahan | 2026-06-26 | 2026-06-27 | JSA No.38/TSA/HSE/06/2026 | 2026-06-26 | 2026-07-02 | SWP-HSE-138 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
279 | CMI | RLC | Nasional | #NAME? | 2026-02-03 | R3270184 | ID-JB-09545 | SETRAINDAH BARAT | 10 | CMI | JAWA BARAT | Kota Bandung | JL. SUKAMULYA INDAH NO. 3, KP. KENDAL GEDE RT 06 RW 02, KEL. SUKAGALIH, KEC. SUKAJADI, KOTA BANDUNG [40163] | -6.88585 | 107.58686 | 1817.0805 | 18 | IOH, XL | Rooftop | Pole | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-05-20 | 2026-05-22 | 2026-08-19 | [8 empty] | Survey Report |  | 2026-07-24 |  | 2026-07-24 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
280 | CMI | RLC | Nasional | #NAME? | 2026-02-03 | R3270184 | ID-JB-09545 | SETRAINDAH BARAT | 10 | CMI | JAWA BARAT | Kota Bandung | JL. SUKAMULYA INDAH NO. 3, KP. KENDAL GEDE RT 06 RW 02, KEL. SUKAGALIH, KEC. SUKAJADI, KOTA BANDUNG [40163] | -6.88585 | 107.58686 | 1817.0805 | 18 | IOH, XL | Rooftop | Pole | Relocation Equipment | [5 empty] | NY Submit |  | 2026-05-20 | 2026-05-22 | 2026-08-19 | [8 empty] | Survey Report |  | 2026-07-24 |  | 2026-07-24 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0
281 | CMI | RLC | Nasional | #NAME? | 2006-04-29 | E3500158 | ID-JI-06326 | PLANDI | 15 | EMA | JAWA TIMUR | Kab. Jombang | DSN NGUDIREJO RT.05 RW 02. KEL.NGUDIREJO. KEC DIWEK. KAB. JOMBANG | -7.57142 | 112.254 | 16015.06 | 55 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-05-04 | 2026-05-10 | Expired |  | 2026-05-04 | 2026-05-13 | 2026-12-23 | [8 empty] | Survey Report |  | 2026-05-20 |  | 2026-05-21 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit |  | 2026-06-11 | 2026-06-12 | JSA No.35/TSA/HSE/06/2026 | 2026-06-11 | 2026-06-22 | SWP-HSE-135 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0 | [7 empty] | ID-JI-19152 | NGUDIREJO | -7.57167 | 112.257794
282 | CMI | RLC | Nasional | #NAME? | 2006-04-29 | E3500158 | ID-JI-06326 | PLANDI | 15 | EMA | JAWA TIMUR | Kab. Jombang | DSN NGUDIREJO RT.05 RW 02. KEL.NGUDIREJO. KEC DIWEK. KAB. JOMBANG | -7.57142 | 112.254 | 16015.06 | 55 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-05-04 | 2026-05-13 | 2026-12-23 | [8 empty] | Survey Report |  | 2026-05-20 |  | 2026-05-21 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0 | [7 empty] | ID-JI-19152 | NGUDIREJO | -7.57167 | 112.257794
283 | CMI | RLC | Nasional | #NAME? | 2006-04-29 | E3500158 | ID-JI-06326 | PLANDI | 15 | EMA | JAWA TIMUR | Kab. Jombang | DSN NGUDIREJO RT.05 RW 02. KEL.NGUDIREJO. KEC DIWEK. KAB. JOMBANG | -7.57142 | 112.254 | 16015.06 | 55 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Relocation Equipment | [5 empty] | NY Submit |  | 2026-05-04 | 2026-05-13 | 2026-12-23 | [8 empty] | Survey Report |  | 2026-05-20 |  | 2026-05-21 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0 | [7 empty] | ID-JI-19152 | NGUDIREJO | -7.57167 | 112.257794
284 | CMI | RLC | Nasional | #NAME? | 2026-02-09 | E3500496 | ID-JI-06660 | LAMONGAN | 15 | EMA | JAWA TIMUR | Kab. Lamongan | JL. ANDANSARI, KAB. LAMONGAN | -7.12236 | 112.413 | 26790.882 | 70 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-07-04 |  | 2026-12-31 | [8 empty] | Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | waiting survey report | [6 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0 |  |  |  | waiting survey report
285 | CMI | RLC | Nasional | #NAME? | 2026-02-09 | E3500496 | ID-JI-06660 | LAMONGAN | 15 | EMA | JAWA TIMUR | Kab. Lamongan | JL. ANDANSARI, KAB. LAMONGAN | -7.12236 | 112.413 | 26790.882 | 70 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-07-04 |  | 2026-12-31 | [8 empty] | Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
286 | CMI | RLC | Nasional | #NAME? | 2026-02-09 | E3500496 | ID-JI-06660 | LAMONGAN | 15 | EMA | JAWA TIMUR | Kab. Lamongan | JL. ANDANSARI, KAB. LAMONGAN | -7.12236 | 112.413 | 26790.882 | 70 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Relocation Equipment | [5 empty] | NY Submit |  | 2026-07-04 |  | drop | [8 empty] | Drop | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | Drop |  |  | Drop
287 | CMI | RLC | Nasional | #NAME? | 2025-08-27 | R3350451 | ID-JT-02715 | BANYUURIP | 11 | CMI | JAWA TENGAH | Kab. Purworejo | JL.BANYUURIP RT.01/01 KEC.BANYUURIP , PURWOREJO,JAWA TENGAH | -7.75616 | 109.972 | 6828.525 | 52 | IOH, XL | Greenfield | SST 3 Legs | Dismantle Tower | Joko Dedoyo | +62 878-6109-5209 | Survey | 2026-05-20 | 2026-05-26 | Expired |  | 2026-05-21 | 2026-06-26 | 2025-05-17 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | 03.06.26 boq mentahan | 2026-06-29 | 2026-06-30 | JSA No.39/TSA/HSE/06/2026 | 2026-06-29 | 2026-07-02 | SWP-HSE-139 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
288 | CMI | RLC | Nasional | #NAME? | 2025-08-27 | R3350451 | ID-JT-02715 | BANYUURIP | 11 | CMI | JAWA TENGAH | Kab. Purworejo | JL.BANYUURIP RT.01/01 KEC.BANYUURIP , PURWOREJO,JAWA TENGAH | -7.75616 | 109.972 | 6828.525 | 52 | IOH, XL | Greenfield | SST 3 Legs | Dismantle Equipment | Joko Dedoyo | +62 878-6109-5209 | Survey | 2026-05-20 | 2026-05-26 | Expired |  | 2026-05-21 | 2026-06-26 | 2025-05-17 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
289 | CMI | RLC | Nasional | #NAME? | 2025-08-27 | R3350451 | ID-JT-02715 | BANYUURIP | 11 | CMI | JAWA TENGAH | Kab. Purworejo | JL.BANYUURIP RT.01/01 KEC.BANYUURIP , PURWOREJO,JAWA TENGAH | -7.75616 | 109.972 | 6828.525 | 52 | IOH, XL | Greenfield | SST 3 Legs | Relocation Equipment | Joko Dedoyo | +62 878-6109-5209 | Survey | 2026-05-20 | 2026-05-26 | Expired |  | 2026-05-21 | 2026-06-26 | 2025-05-17 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0
290 | CMI | RLC | Nasional | #NAME? | 2026-02-10 | E3400030 | ID-YO-06112 | KRAPYAK_YGY | 11 | EMA | DI YOGYAKARTA | Kab. Bantul | JL. CUWIRI KEL. MANTRIJERON KEC. MANTRIJERON KODYA YOGYAKARTA (SMP ALI MAKSUM) | -7.82504 | 110.362 | 1643.7595 | 12 |  | Rooftop | Pole | Dismantle Tower | [5 empty] | NY Submit |  | 2026-04-18 | 2026-04-18 | 2026-11-30 | [8 empty] | Survey Report |  | 2026-05-12 | 2026-06-23 | 2026-05-13 |  | 2026-06-23 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-06-08 | 2026-06-10 | JSA No.32/TSA/HSE/06/2026 | 2026-06-08 | 2026-06-18 | SWP-HSE-132 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
291 | CMI | RLC | Nasional | #NAME? | 2026-02-10 | R5100125 | ID-BA-01273 | PELIATAN | 16 | CMI | BALI | Kab. Gianyar | JL. MADE LEBAH NO 2 BANJAR KALAH DESA PELIATAN KEC. UBUD KAB. GIANYAR PROV. BALI | -8.52365 | 115.268 | 1879.32 | 15 |  | Rooftop | Pole | Dismantle Tower | [5 empty] | NY Submit |  | 2026-02-20 | 2026-02-16 | 2028-02-14 | [8 empty] | Survey Report | Survey only | 2026-04-22 | 2026-04-23 |  |  | 2026-04-23 | 2026-04-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-04-13 | 2026-04-14 | JSA No.08/TSA/HSE/04/2026 | 2026-04-11 | 2026-04-14 | SWP-HSE-108 | Approved | Approved |  |  | Dismantle Tower | CMIPO26-001559 | 2026-05-07 | 10 |  |  | 0 |  |  |  | Complete
292 | CMI | RLC | Nasional | #NAME? | 2026-02-20 | E8100001 | ID-MA-07883 | AIRPORT_AMBON | 20 | EMA | MALUKU | Kota Ambon | BANDARA PATTIMURA AMBON - MALUKU | -3.70596 | 128.087 | 5549.895 | 30 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Dismantle | 2026-03-10 | 2026-03-16 | Expired |  | 2026-02-26 | 2026-02-26 |  |  |  | 2026-04-01 |  |  |  | 2026-04-14 | 2026-04-14 | BAST | 12.03.26 Start dismantle | 2026-03-02 | 2026-03-03 | 2026-03-04 |  | 2026-03-04 | 2026-03-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-03-02 | 2026-03-05 | JSA No.07/TSA/HSE/03/2026 | 2026-03-02 | 2026-03-03 | SWP-HSE-107 | Approved | Approved | 2026-04-14 | 2026-04-15 | Dismantle Tower | EMAPO26-000405 | 2026-03-16 | 11 |  |  | 0 |  |  |  | Complete
293 | CMI | RLC | Nasional | #NAME? | 2026-02-20 | E8100001 | ID-MA-07883 | AIRPORT_AMBON | 20 | EMA | MALUKU | Kota Ambon | BANDARA PATTIMURA AMBON - MALUKU | -3.70596 | 128.087 | 5549.895 | 30 |  | Greenfield | SST 4 Legs | Dismantle Equipment |  |  | Dismantle | 2026-03-10 | 2026-03-16 | Expired |  | 2026-02-26 | 2026-02-26 | drop | [8 empty] | Drop |  | 2026-03-02 | 2026-03-03 | 2026-03-04 |  | 2026-03-04 | 2026-03-05 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-03-02 |  |  | 2026-03-02 |  |  | Submit | Submit |  |  | Dismantle Equipment | Include Dism Tower | 2026-03-16 | Drop |  |  | Drop |  |  |  | Perangkat dismantle by MNO
294 | CMI | RLC | Nasional | #NAME? | 2026-03-06 | R3580603 | ID-JI-08021 | TLANAKAN_LARANGANSLAMPAR | 15 | CMI | JAWA TIMUR | Kab. Pamekasan | DSN. SEKAR PUTIH , RT. 002, RW. 001, DS. LARANGAN SLAMPAR , KEC. TLANAKAN KAB. PAMEKASAN PROV. JAWA TIMUR | -7.18638 | 113.42 | 14004.405 | 62 | XL | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit | No Need Permit | 2026-03-10 |  |  |  |  | 2026-03-14 | [5 empty] | Dismantle | 08.03.26 Start Cutting Tower | 2026-04-02 | 2026-04-06 | 2026-04-07 |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit |  | 2026-03-10 | 2026-03-10 | JSA No.09/TSA/HSE/03/2026 | 2026-03-10 | 2026-03-10 | SWP-HSE-109 | Approved | Approved |  |  | Dismantle Tower | CMIPO26-001482 | 2026-04-28 | 0 |  |  | 0 |  |  |  | Complete
295 | CMI | RLC | Nasional | #NAME? | 2026-03-09 | E3500584 | ID-JI-08313 | DESAGADING_BJO | 15 | EMA | JAWA TIMUR | Kab. Bojonegoro | DUSUN GADING RT 010 RW 002 DESA GADING KEC. TAMBAKREJO KAB. BOJONEGORO PROP. JAWA TIMUR | -7.24061 | 111.596 | 13632.5 | 62 |  | Greenfield | SST 4 Legs | Cutting Tower from 62 to 55 |  |  | survey | 2026-03-14 | 2026-03-17 | Expired |  | 2026-03-16 | 2026-03-17 | [9 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | 17.03.26 BOQ mentahan | [6 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
296 | CMI | RLC | Nasional | #NAME? | 2026-03-09 | E3500584 | ID-JI-08313 | DESAGADING_BJO | 15 | EMA | JAWA TIMUR | Kab. Bojonegoro | DUSUN GADING RT 010 RW 002 DESA GADING KEC. TAMBAKREJO KAB. BOJONEGORO PROP. JAWA TIMUR | -7.24061 | 111.596 | 13632.5 | 62 |  | Greenfield | SST 4 Legs | Reheight Antenna |  |  | survey | 2026-03-14 | 2026-03-17 | Expired |  | 2026-03-16 | 2026-03-17 | [9 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | 17.03.26 BOQ mentahan | [6 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0
297 | CMI | RLC | Nasional | #NAME? |  | R35780005 | ID-JI-00264 | WONOKESUMO | 15 | CMI | JAWA TIMUR | Kota Surabaya |  | -7.22355 | 112.7516 |  |  | IOH, Tsel | Greenfield | Combat | Dismantle Equipment in MBTS | [5 empty] | NY Submit |  | 2026-03-10 | 2026-03-10 |  |  | 2026-04-07 | [6 empty] | Dismantle Perangkat | 16.03.26 Start dismantle IOH 07.04.26 Start dismantle Tsel | 2026-03-10 | 2026-03-11 | NA | 2026-04-06 | 2026-03-11 | 2026-03-11 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | DRM 2nd BOQ 03.06.26 | [6 empty] | NY Submit | NY Submit | 2026-06-04 | 2026-06-04 | Dismantle Equipment | Include Reloc | 2026-04-02 | 22 |  |  | 0 | [7 empty] | R3580018 old site | PEGIRIKAN RELOCATION |  |  |  |  | CRQ000001104554
298 | CMI | RLC | Nasional | #NAME? |  | R35780005 | ID-JI-00264 | WONOKESUMO | 15 | CMI | JAWA TIMUR | Kota Surabaya |  | -7.22355 | 112.7516 |  |  | IOH, Tsel | Greenfield | Combat | Relocation Equipment to Permanent Site | [5 empty] | NY Submit |  | 2026-03-10 | 2026-03-10 | [5 empty] | 2026-04-09 | 2026-04-09 | 2026-04-14 | 2026-04-14 | ATP App MS | 18.03.26 IOH OA 09.04.26 Tsel OA | 2026-03-10 | 2026-03-11 | NA | 2026-04-06 | 2026-03-11 | 2026-03-11 | 1st BOQ App on ISAAC | 2026-06-03 |  |  | 2026-07-24 |  |  | BAN App | DRM 2nd BOQ 03.06.26 | [6 empty] | NY Submit | NY Submit | 2026-06-04 | 2026-06-04 | Relocation Equipment | CMIPO26-001229 | 2026-04-02 | 22 | NY release |  | 0 |  |  |  | PO Variation NY Release | CMI Project |  |  | R3580018 | [5 empty] | CRQ000001104554
299 | CMI | RLC | Nasional | #NAME? | 2026-03-06 | R3580603 | ID-JI-08021 | TLANAKAN_LARANGANSLAMPAR | 15 | CMI | JAWA TIMUR | Kab. Pamekasan | DSN. SEKAR PUTIH , RT. 002, RW. 001, DS. LARANGAN SLAMPAR , KEC. TLANAKAN KAB. PAMEKASAN PROV. JAWA TIMUR | -7.18638 | 113.42 | 14004.405 | 62 | XL | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-03-10 |  |  |  | 2026-03-08 | [6 empty] | Dismantle Perangkat | 07.03.26 Start Dism Perangkat | 2026-04-02 | 2026-04-06 | 2026-04-07 |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | Include Dism Tower | 2026-04-28 | 0 |  |  | 0 |  |  |  | Complete
300 | CMI | RLC | Nasional | #NAME? | 2026-03-06 | R3580603 | ID-JI-08021 | TLANAKAN_LARANGANSLAMPAR | 15 | CMI | JAWA TIMUR | Kab. Pamekasan | DSN. SEKAR PUTIH , RT. 002, RW. 001, DS. LARANGAN SLAMPAR , KEC. TLANAKAN KAB. PAMEKASAN PROV. JAWA TIMUR | -7.18638 | 113.42 | 14004.405 | 62 | XL | Greenfield | SST 4 Legs | Relocation Equipment | [5 empty] | NY Submit |  | 2026-03-10 | [6 empty] | 2026-04-10 |  |  |  | Install |  | 2026-04-02 | 2026-04-06 | 2026-04-07 |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | Include Dism Tower | 2026-04-28 | 0 | NY release |  | 0 |  |  |  | PO Variation (reheight antenna) NY release
301 | CMI | RLC | Nasional | #NAME? | 2026-04-09 | E6400127 |  | N_KALIORANG | 18 | EMA | KALIMANTAN TIMUR | Kab. Kutai Timur | Jl. Kenanga No 5 Rt 11/04 Ds.Bumi Sejatera Kel Kaliorang Kec Kaliorang Kab Kutim | 0.90123 | 117.9 |  |  | IOH | Greenfield | SST 4 Legs | Outdorization | [5 empty] | NY Submit |  | 2026-07-02 | 2026-07-02 | [5 empty] | 2026-04-20 |  |  |  | Install |  | 2026-04-09 | 2026-04-14 | NO Need | 2026-05-05 | 2026-07-07 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | 30.04.26 DRM | [6 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0 |  |  |  | BOQ NY App on ISAAC | CMI Project
302 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | R3350028 |  | AGUNG SELATAN | 11 | CMI | JAWA TENGAH | Kota Surakarta |  | -7.5556 | 110.8382 | 218.15 | 6 |  | Rooftop | Pole | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-04-15 |  | drop | [8 empty] | Drop |  | 2026-04-17 |  | 2026-04-21 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | Drop |  | Drop |  |  | Drop
303 | CMI | RLC | Nasional | #NAME? | 2026-01-12 | R3350028 |  | AGUNG SELATAN | 11 | CMI | JAWA TENGAH | Kota Surakarta |  | -7.5556 | 110.8382 | 218.15 | 6 |  | Rooftop | Pole | Relocation Equipment | [5 empty] | NY Submit |  | 2026-04-15 |  | drop | [8 empty] | Drop |  | 2026-04-17 |  | 2026-04-21 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | Drop |  | Drop |  |  | Drop
304 | CMI | RLC | Nasional | #NAME? | 2026-04-22 | E7300112 | ID-SN-07744 | BANTAENG | 19 | EMA | SULAWESI SELATAN | Kab. Bantaeng | JL. RAYA LANTO KEL. MALILINGI KEC. BANTAENG KAB. BANTAENG | -5.54805 | 119.9504 | 19172.256 | 72 |  |  |  | Dismantle Tower |  |  | Survey | 2026-05-02 | 2026-05-14 | Expired |  | 2026-05-02 | 2026-05-16 | 2026-07-19 | [8 empty] | Survey Report |  | 2026-06-24 | 2026-07-07 | 2026-07-03 |  | 2026-07-07 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit | 19.05.26 boq mentahan | 2026-05-18 | 2026-05-22 | JSA No.21/TSA/HSE/05/2026 | 2026-05-18 | 2026-05-18 | SWP-HSE-121 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
305 | CMI | RLC | Nasional | #NAME? | 2026-04-22 | E1200337 | ID-KR-04090 | BUKIT_BALADA | 2 | EMA | KEPULAUAN RIAU | Kota Batam | JL. KOLONEL SUGIONO TG. PINGGIR, SEKUPANG | 1.13133 | 103.92832 | 16460.318 | 55 | IOH & TSEL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-05-07 | 2026-05-13 | Expired |  | 2026-05-11 | 2026-05-20 | 2026-06-30 | [8 empty] | Survey Report |  | 2026-05-21 | 2026-06-14 | 2026-06-09 |  | 2026-06-15 | 2026-06-17 | 1st BOQ App on ISAAC |  |  |  | DRM |  |  | need DRM | SPH scrap onsite area batam need DRM | 2026-05-25 | 2026-05-25 | JSA No.26/TSA/HSE/05/2026 | 2026-05-25 | 2026-05-25 | SWP-HSE-126 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 49 |  |  | 0
306 | CMI | RLC | Nasional | #NAME? | 2026-04-22 | E1200119 | ID-SU-03874 | TELADAN | 1 | EMA | SUMATERA UTARA | Kota Medan | JL. SISINGAMANGARAJA NO. 176 MEDAN | 3.56185 | 98.69296 | 2819.853 | 20 |  |  |  | Dismantle Tower | [5 empty] | NY Submit |  | 2026-05-03 | 2026-05-03 | 2026-08-15 | [8 empty] | Survey Report |  | 2026-05-18 |  | 2026-05-20 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit | Need DRM | 2026-06-03 | 2026-06-04 | JSA No.28/TSA/HSE/06/2026 | 2026-06-03 | 2026-06-03 | SWP-HSE-128 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
307 | CMI | RLC | Nasional | #NAME? | 2026-04-22 | R1100013 | ID-AC-00498 | PASAR KUTA BLANG | 1 | CMI | NANGGROE ACEH DARUSSALAM | Kab. Bireun | JL. PDG, DSN TGK CHIK GAMPONG TINGKEM MANYANG, KEC. KUTA BLANG, KAB. BIREUN, PROV. ACEH | 5.21272 | 96.82892 | 6159 | 42 |  |  |  | Dismantle Tower | [5 empty] | NY Submit |  |  |  | 2027-01-01 | [8 empty] | NY Survey | on plan | [6 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
308 | CMI | RLC | Nasional | #NAME? | 2026-04-22 | E3400048 | ID-YO-06130 | BABARAN | 11 | EMA | DI YOGYAKARTA | Kota Yogyakarta | JL. GLAGAH SARI III UMBULHARJO, YOGYAKARTA | -7.8107 | 110.38758 | 9236.076 | 52 |  |  |  | Dismantle Tower | Joko Dedoyo | +62 878-6109-5209 | Survey | 2026-05-13 | 2026-05-19 | Expired |  | 2026-05-18 | 2026-06-12 | 2027-03-31 | [8 empty] | Survey Report |  | 2026-07-16 | 2026-07-22 | 2026-07-16 |  | 2026-07-22 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-07-22 | 2026-07-23 | JSA No.46/TSA/HSE/07/2026 | 2026-07-22 | 2026-07-23 | SWP-HSE-146 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
309 | CMI | RLC | Nasional | #NAME? | 2026-04-23 | E3200384 | ID-JB-05339 | KARABA INDAH | 10 | EMA | JAWA BARAT | Kab. Karawang | JL. WADAS PINTU AIR RT. 02 RW 04 KARABA INDAH KARAWANG | -6.32445 | 107.275 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-05-11 | 2026-05-17 | Expired |  | 2026-05-16 | 2026-07-10 | 2026-08-20 | [8 empty] | Survey Report | on plan | 2026-07-16 |  | 2026-07-16 |  |  |  | Engineering Structural Manager App |  |  |  | DRM |  |  | need DRM | Reinstall Genset & Pondasi di 2nd BOQ | 2026-07-10 | 2026-07-23 | JSA No.42/TSA/HSE/07/2026 | 2026-07-10 | 2026-07-17 | SWP-HSE-142 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
310 | CMI | RLC | Nasional | #NAME? | 2026-04-23 | E3200384 | ID-JB-05339 | KARABA INDAH | 10 | EMA | JAWA BARAT | Kab. Karawang | JL. WADAS PINTU AIR RT. 02 RW 04 KARABA INDAH KARAWANG | -6.32445 | 107.275 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-05-16 | 2026-07-10 | 2026-08-20 | [8 empty] | Survey Report |  | 2026-07-16 |  | 2026-07-16 |  |  |  | Engineering Structural Manager App |  |  |  | DRM |  |  | need DRM | Reinstall Genset & Pondasi di 2nd BOQ | 2026-07-10 | 2026-07-23 |  | 2026-07-10 | 2026-07-17 |  | Approved | Approved |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
311 | CMI | RLC | Nasional | #NAME? | 2026-04-23 | E3200384 | ID-JB-05339 | KARABA INDAH | 10 | EMA | JAWA BARAT | Kab. Karawang | JL. WADAS PINTU AIR RT. 02 RW 04 KARABA INDAH KARAWANG | -6.32445 | 107.275 | 18868.812 | 70 |  | Greenfield | SST 4 Legs | Relocation Equipment | [5 empty] | NY Submit |  | 2026-05-16 | 2026-07-10 | Drop | [8 empty] | Drop |  | 2026-07-16 |  | 2026-07-16 |  |  |  | Engineering Structural Manager App |  |  |  | DRM |  |  | need DRM | Reinstall Genset & Pondasi di 2nd BOQ | [6 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | Drop |  |  | Drop
312 | CMI | RLC | Nasional | #NAME? | 2026-04-30 | E1200424 | ID-KR-04174 | DAPUR_DUA_BELAS / DAPUR 12 | 2 | EMA | KEPULAUAN RIAU | Kota Batam | KAVLING BUKIT KAMBOJA RT 02/42 KEL. SAGULUNG KEC. SUNGAI BEDUK BATAM | 1.02341 | 103.959 | 13067.712 | 55 | IOH & TSEL | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-05-07 | 2026-05-13 | Expired |  | 2026-05-22 | 2026-05-23 | 2026-06-30 | 2026-06-22 | [7 empty] | RFD App |  | 2026-05-28 | 2026-06-15 | 2026-05-28 |  | 2026-06-15 | 2026-06-15 | 1st BOQ App on ISAAC |  |  |  | DRM |  |  | need DRM | Dismantle RRU blm masuk ke BOQ SPH scrap onsite area batam need DRM Add cost tiket pesawat need DRM (pengganti delay dismantle tower) | 2026-05-25 | 2026-05-25 | JSA No.25/TSA/HSE/05/2026 | 2026-05-25 | 2026-05-25 | SWP-HSE-125 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 51 |  |  | 0 |  |  |  | Waiting dism equip telkomsel W28 | CMI
313 | CMI | RLC | Nasional | #NAME? | 2026-04-30 | E1200363 | ID-KR-04115 | PINTU 4 MUKA KUNING | 2 | EMA | KEPULAUAN RIAU | Kota Batam | JL. TANJUNG RAYA , MUKA KUNING | 1.05913 | 104.039 | 8462.04 | 40 | IOH | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-05-07 | 2026-05-13 | Expired |  | 2026-05-19 | 2026-05-21 | 2026-06-30 | 2026-06-04 |  | 2026-07-21 |  |  |  |  | 2026-07-21 | BAST |  | 2026-05-21 | 2026-05-28 | 2026-05-28 |  | 2026-05-29 | 2026-05-29 | 1st BOQ App on ISAAC |  |  |  | DRM |  |  | need DRM | 14.07.26 DRM // 20.07.26 done revisi SPH SPH scrap onsite area batam Add cost tiket pesawat (pengganti delay dismantle tower) done DRM | 2026-05-25 | 2026-05-25 | JSA No.24/TSA/HSE/05/2026 | 2026-05-25 | 2026-05-25 | SWP-HSE-124 | Approved | Approved |  |  | Dismantle Tower | EMAPO26-000791 | 2026-06-19 | 21 |  |  | 0
314 | CMI | RLC | Nasional | #NAME? | 2026-05-07 | E3100353 | ID-JK-04756 | KAWIKAWI | 7 | EMA | DKI JAKARTA | Kota Administrasi Jakarta Pusat | KRAMAT SENTIONG L55 KAWI-KAWI BAWAH,JOHAR BARU. JAKARTA PUSAT | -6.18645 | 106.853 | 9126.83 | 70 |  | Greenfield | SST 4 Legs | Cutting Tower from 70 to 40 |  |  | Survey | 2026-05-08 | 2026-05-14 | Expired |  | 2026-05-26 | [10 empty] | Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | 04.06.26 boq mentahan | [6 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
315 | CMI | RLC | Nasional | #NAME? | 2025-12-22 | R3350421 | ID-JT-02685 | KARANGJUNTI | 11 | CMI | JAWA TENGAH | Kab. Brebes | KARANG JUNTI RT05/02 , KB BREBES - JAWA TENGAH | -6.91628 | 108.793 | 13212.913 | 71 |  | Greenfield | SST 3 Legs | Relocation Equipment |  |  | Survey | 2025-12-27 | 2025-12-30 | Expired |  | 2025-12-31 |  | 2026-02-10 |  |  |  |  | 2026-06-27 | 2026-06-27 |  |  | OA/RFS | 08.06.26 OA IOH 27.06.26 OA XLS | 2026-05-22 | 2026-05-29 |  |  | 2026-05-29 | 2026-05-31 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | CMIPO26-002311 | 2026-07-06 | 36 |  |  | 0 |  |  |  | 03.07.26 ATP IOH done upload ISAAC XLS NY take data ATP | TSA |  |  | ID-JT-17956 | LOSARI KARANGJUNTI | -6.9143 | 108.7942 | CR-20260529-00000297
316 | CMI | RLC | Nasional | #NAME? | 2026-05-25 | R3350408 | ID-JT-05929 | TINGKIR SALATIGA | 11 | CMI | JAWA TENGAH | Kota Salatiga | DSN NGEPOS RT01/08 KL TINGKIR , KC TINGKIR KODYA SALATIGA JATENG | -7.36271 | 110.515 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-07-03 | 2026-07-06 | 2026-11-17 | [8 empty] | Survey Report | on plan | 2026-07-16 | 2026-07-22 | 2026-07-16 |  | 2026-07-24 | 2026-07-27 | 1st BOQ App on ISAAC |  |  |  | DRM |  |  | need DRM | Reinstall Genset & Pondasi di 2nd BOQ | 2026-07-09 | 2026-07-23 | JSA No.40/TSA/HSE/07/2026 | 2026-07-09 | 2026-07-15 | SWP-HSE-140 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 9 |  |  | 0
317 | CMI | RLC | Nasional | #NAME? | 2026-05-25 | R3350408 | ID-JT-05929 | TINGKIR SALATIGA | 11 | CMI | JAWA TENGAH | Kota Salatiga | DSN NGEPOS RT01/08 KL TINGKIR , KC TINGKIR KODYA SALATIGA JATENG | -7.36271 | 110.515 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-07-03 | 2026-07-06 | [9 empty] | Survey Report |  | 2026-07-16 | 2026-07-22 | 2026-07-16 |  | 2026-07-24 | 2026-07-27 | 1st BOQ App on ISAAC |  |  |  | DRM |  |  | need DRM | Reinstall Genset & Pondasi di 2nd BOQ | 2026-07-09 | 2026-07-23 |  | 2026-07-09 | 2026-07-15 |  | Approved | Approved |  |  | Dismantle Equipment | NY release |  | 9 |  |  | 0
318 | CMI | RLC | Nasional | #NAME? | 2026-05-25 | R3350408 | ID-JT-05929 | TINGKIR SALATIGA | 11 | CMI | JAWA TENGAH | Kota Salatiga | DSN NGEPOS RT01/08 KL TINGKIR , KC TINGKIR KODYA SALATIGA JATENG | -7.36271 | 110.515 | 6828.525 | 51 |  | Greenfield | SST 3 Legs | Relocation Equipment | [5 empty] | NY Submit |  | 2026-07-03 | 2026-07-06 | [9 empty] | Survey Report |  | 2026-07-16 | 2026-07-22 | 2026-07-16 |  | 2026-07-24 | 2026-07-27 | 1st BOQ App on ISAAC |  |  |  | DRM |  |  | need DRM | Reinstall Genset & Pondasi di 2nd BOQ | [6 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 9 |  |  | 0
319 | CMI | RLC | Nasional | #NAME? | 2025-12-22 | R3350421 | ID-JT-02685 | KARANGJUNTI | 11 | CMI | JAWA TENGAH | Kab. Brebes | KARANG JUNTI RT05/02 , KB BREBES - JAWA TENGAH | -6.91628 | 108.793 | 13212.913 | 71 |  | Greenfield | SST 3 Legs | Rebuild_LOS Survey 14BRS0006 to 14BRS0004 / 14BRS0011 / 14BRS0013 | [5 empty] | NY Submit |  | 2026-05-25 | 2026-05-25 | [7 empty] | 2026-05-25 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | CMIPO26-002316 | 2026-07-07 | 0 |  |  | 0 |  |  |  | Complete | CMI Project
320 | CMI | RLC | Nasional | #NAME? | 2026-05-28 | R5100055 | ID-BA-00320 | T_COW TEUKU UMAR | 16 | CMI | BALI | Kota Denpasar | CELLULAR WORLD , JL. TEUKU UMAR NO. 60, KOTA DENPASAR - BALI | -8.67097 | 115.209 | 1039.5385 | 9 |  | Rooftop | Pole | Dismantle Tower | [5 empty] | NY Submit |  | 2026-06-10 | 2026-06-12 | 2026-07-15 | [8 empty] | Survey Report | 06.07.26 Start Dismantle | 2026-06-23 | 2026-07-01 | 2026-06-24 |  | 2026-07-01 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-06-12 | 2026-06-13 | JSA No.36/TSA/HSE/06/2026 | 2026-06-12 | 2026-06-18 | SWP-HSE-136 | Approved | Approved | 2026-07-24 |  | Dismantle Tower | NY release |  | 0 |  |  | 0 |  |  |  | PO NY release
321 | CMI | RLC | Nasional | #NAME? | 2026-05-28 | E3500354 | ID-JI-06519 | DCS_JAGALAN | 15 | EMA | JAWA TIMUR | Kota Surabaya | JL. JAGALAN 79/J-K RT/RW 001/012, KEL. PENELEH, KEC. GENTENG, SURABAYA, JAWA TIMUR | -7.24864 | 112.743 | 567.703 | 12 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-07-21 | 2026-07-27 | Expired |  | 2026-07-21 | 2026-07-21 | 2026-08-02 | [8 empty] | Survey Report | 09.07.26 team onsite survey no akses, LL tidak ada ditempat | 2026-07-23 | 2026-08-03 | 2026-07-23 |  | 2026-08-03 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-07-22 | 2026-07-23 | JSA No.45/TSA/HSE/07/2026 | 2026-07-22 | 2026-07-23 | SWP-HSE-145 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0 |  |  |  | Waiting RFD
322 | CMI | RLC | Nasional | #NAME? | 2026-05-28 | R3100430 | ID-JB-00992 | GP MALL (BEKASI TRADE CENTER II) | 10 | CMI | JAWA BARAT | Kab. Bekasi | JL. HAJI MULYADI JOYOMARTONO, MARGAHAYU, BEKASI TIMUR, JAWA BARAT | -6.25969 | 107.021 | 872.6 | 6 |  | Rooftop | Pole | Dismantle Tower | [5 empty] | NY Submit | [12 empty] | NY Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
323 | CMI | RLC | Nasional | #NAME? | 2026-05-29 | R7300149 | ID-SN-01892 | KDI AEROPPALA | 19 | CMI | SULAWESI SELATAN | Kota Makassar | JL. AROEPPALA, HERTASNING BARU, KEL. KASSI-KASSI, KEC. RAPPOCINI,MAKASSAR | -5.17642 | 119.457 | 2339.384 | 20 |  | Greenfield | Monopole | Dismantle Tower | [5 empty] | NY Submit |  | 2026-06-02 | 2026-06-02 | 2026-06-14 |  | 2026-06-04 | 2026-06-08 |  |  |  |  | 2026-06-11 | BAST | 05.06.26 Start dismantle tower need inbound Telkomsel | 2026-06-03 | 2026-06-03 | 2026-06-04 |  | 2026-06-04 | 2026-06-04 | 1st BOQ App on ISAAC | 2026-07-01 | [5 empty] | 2nd BOQ Submit | Need DRM | 2026-06-02 | 2026-06-04 | JSA No.29/TSA/HSE/06/2026 | 2026-06-02 | 2026-06-04 | SWP-HSE-129 | Approved | Approved |  |  | Dismantle Tower | CMIPO26-002158 | 2026-06-19 | 15 |  |  | 0 |  |  |  | Complete
324 | CMI | RLC | Nasional | #NAME? | 2006-04-29 | E3500158 | ID-JI-06326 | PLANDI | 15 | EMA | JAWA TIMUR | Kab. Jombang | DSN NGUDIREJO RT.05 RW 02. KEL.NGUDIREJO. KEC DIWEK. KAB. JOMBANG | -7.57142 | 112.254 | 16015.06 | 55 | TSEL, IOH, XL | Greenfield | SST 4 Legs | Rebuild_LOS Survey 16JMB0118 SUMBER_MULYO_MT to 16JMB0108 PLANDI_JMB1_EP | [5 empty] | NY Submit |  | 2026-06-02 | 2026-06-08 | [9 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO26-000862 | 2026-07-07 | 0 |  |  | 0 |  |  |  | Complete | CMI Project |  |  | 16JMB0118 | SUMBER_MULYO_MT | -7.56379 | 112.26398
325 | CMI | RLC | Nasional | #NAME? | 2026-06-09 | E9100006 | ID-PB-07922 | V_BABO | 20 | EMA | PAPUA BARAT | Kab. Teluk Bintuni | DEPAN SP. N I BABO, KAMPUNG IRARUTU III JL. ANGKASA RT. 08/RK.01 BABO, KAB. TELUK BINTUNI | -2.54047 | 133.443 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  |  |  | 2026-12-31 | [8 empty] | NY Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
326 | CMI | RLC | Nasional | #NAME? | 2026-06-09 | E7300019 | ID-SN-07651 | MAKASSAR_TRADE | 19 | EMA | SULAWESI SELATAN | Kota Makassar | JL HOS COKRO AMINOTO MAKASAR | -5.13247 | 119.413 | 1576.09 | 6 |  | Rooftop | Pole | Dismantle Tower | [5 empty] | NY Submit |  | 2002-07-31 |  | 2026-12-31 | [8 empty] | Survey | 14.06.26 onsite survey, butuh konfirmasi pole cmi 31.07.26 jovis & resurvey with CMI TM | [6 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
327 | CMI | RLC | Nasional | #NAME? | 2026-06-17 | E6400127 |  | N_KALIORANG | 18 | EMA | KALIMANTAN TIMUR | Kab. Kutai Timur | Jl. Kenanga No 5 Rt 11/04 Ds.Bumi Sejatera Kel Kaliorang Kec Kaliorang Kab Kutim | 0.90123 | 117.9 |  |  |  | Greenfield | SST 4 Legs | Dismantle Shelter | [5 empty] | NY Submit | [12 empty] | NY Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
328 | CMI | RLC | Nasional | #NAME? | 2025-12-11 | R1200302 | ID-SU-02192 | BANGUN PURBA | 1 | CMI | SUMATERA UTARA | Kab. Deli Serdang | DSN/LINK.III,KEL.BANGUN PURBA , KEC.BANGUN PURBA,KAB.DELI SERDANG | 3.37203 | 98.8141 | 13212.913 | 71 | XL | Greenfield | SST 3 Legs | Rebuild_LOS Survey SUM-SU-LBP-0054 BANGUN PURBA Relocation to SUM-SU-SRH-1245 Sei Buaya // SUM-SU-LBP-0412 Batu Lokong // SUM-SU-SRH-8224 SF_Pematang Raya 2_COLLECTOR | [5 empty] | NY Submit |  | 2026-05-10 | 2026-05-12 | [7 empty] | 2026-05-12 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Rebuild_LOS Survey | EMAPO26-000855 | 2026-07-03 | 0 |  |  | 0 |  |  |  | Complete | CMI Project
329 | CMI | RLC | Nasional | #NAME? | 2026-06-29 | E1600094 | ID-SS-04315 | TELKOM TL KELAPA / NASKAH | 4 | EMA | SUMATERA SELATAN | Kota Palembang | JL.KOL H BURLIAN RT.012/RW.04 KEL.KARYA BARU KEC.ALANG-ALANG BESAR | -2.93799 | 104.72 | 5874.02 | 25 |  | Rooftop | MT 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-06-30 | 2026-07-20 | [9 empty] | Survey Report |  | 2026-07-23 | 2026-07-24 | 2026-07-23 |  | 2026-07-24 | 2026-07-27 | 1st BOQ App on ISAAC | [6 empty] | NY Submit |  | 2026-07-24 | 2026-07-31 | JSA No.48/TSA/HSE/07/2026 | 2026-07-24 |  | SWP-HSE-148 | Approved | Submit |  |  | Dismantle Tower | NY release |  | 9 |  |  | 0
330 | CMI | RLC | Nasional | #NAME? | 2026-06-29 | E3500229 | ID-JI-06397 | DIENG_MALANG | 15 | EMA | JAWA TIMUR | Kota Malang | JL.SIMPANGRAYALANGSEPNO.20A,MALANG | -7.97733 | 112.612 | 11752.764 | 40 | IOH & XL | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  |  |  | 2026-10-11 | [8 empty] | NY Survey | Comcase | [6 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
331 | CMI | RLC | Nasional | #NAME? | 2026-06-29 | E3500229 | ID-JI-06397 | DIENG_MALANG | 15 | EMA | JAWA TIMUR | Kota Malang | JL.SIMPANGRAYALANGSEPNO.20A,MALANG | -7.97733 | 112.612 | 11752.764 | 40 | IOH & XL | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  |  |  | 2026-10-11 | [8 empty] | NY Survey | Comcase | [6 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
332 | CMI | RLC | Nasional | #NAME? | 2026-06-30 | E3300200 | ID-JT-05910 | UNISULA | 11 | EMA | JAWA TENGAH | Kota Semarang | JL. KALIGAWE RAYA NO.4 KODYA SEMARANG | -6.95592 | 110.457 | 7279.054 | 42 |  | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-07-03 | 2026-07-06 | [9 empty] | Survey Report |  | 2026-07-27 | 2026-08-03 | 2026-07-27 |  | 2026-08-03 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-07-24 | 2026-07-29 | JSA No.47/TSA/HSE/07/2026 | 2026-07-24 | 2026-07-27 | SWP-HSE-147 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
333 | CMI | RLC | Nasional | #NAME? | 2026-06-30 | R3270702 | ID-JB-02532 | PABUARAN (CIREBON) | 10 | CMI | JAWA BARAT | Kab. Cirebon | KH ZAENAL ARIFIN NO68 PABUARAN LOR , KC PABUARAN KB CIREBON - JAWA BARAT | -6.90332 | 108.718 | 6828.525 | 51 | XLS | Greenfield | SST 3 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-07-08 | 2026-07-15 | 2026-09-30 | [8 empty] | Survey Report |  | 2026-07-27 |  | 2026-07-28 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit |  | 2026-07-28 |  | JSA No.50/TSA/HSE/07/2026 | 2026-07-28 |  | SWP-HSE-150 | Submit | Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
334 | CMI | RLC | Nasional | #NAME? | 2026-04-30 | E1200424 | ID-KR-04174 | DAPUR_DUA_BELAS / DAPUR 12 | 2 | EMA | KEPULAUAN RIAU | Kota Batam | KAVLING BUKIT KAMBOJA RT 02/42 KEL. SAGULUNG KEC. SUNGAI BEDUK BATAM | 1.02341 | 103.959 | 13067.712 | 55 | IOH & TSEL | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-05-22 | 2026-05-23 | 2026-06-30 |  | 2026-06-29 |  | 2026-06-30 |  |  |  |  | Inbound | 29.06.26 dismantle equipment IOH 30.06.26 HO matrial ke MS IOH Plan dism tsel di W28 | 2026-05-28 | 2026-06-15 | 2026-05-28 |  | 2026-06-15 | 2026-06-15 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | Dismantle RRU blm masuk ke BOQ SPH scrap onsite area batam need DRM | 2026-05-25 | 2026-05-25 | JSA No.25/TSA/HSE/05/2026 | 2026-05-25 | 2026-05-25 |  | Approved | Approved |  |  | Dismantle Equipment | NY release |  | 51 |  |  | 0
335 | CMI | RLC | Nasional | #NAME? | 2026-04-30 | E1200363 | ID-KR-04115 | PINTU 4 MUKA KUNING | 2 | EMA | KEPULAUAN RIAU | Kota Batam | JL. TANJUNG RAYA , MUKA KUNING | 1.05913 | 104.039 | 8462.04 | 40 | IOH | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-05-19 | 2026-05-21 | 2026-06-30 |  | 2026-07-09 |  | 2026-07-12 |  |  |  |  | Inbound | 09.07.26 sebagian perangkat diambil MS di site 12.07.26 Inbound to HB MS | 2026-05-21 | 2026-05-28 | 2026-05-28 |  | 2026-05-29 | 2026-05-29 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | 14.07.26 DRM // 20.07.26 done revisi SPH SPH scrap onsite area batam Add cost tiket pesawat (pengganti delay dismantle tower) done DRM | 2026-05-25 | 2026-05-25 | JSA No.24/TSA/HSE/05/2026 | 2026-05-25 | 2026-05-25 |  | Approved | Approved |  |  | Dismantle Equipment | NY release |  | 68 |  |  | 0
336 | CMI | RLC | Nasional | #NAME? | 2026-04-22 | E1200337 | ID-KR-04090 | BUKIT_BALADA | 2 | EMA | KEPULAUAN RIAU | Kota Batam | JL. KOLONEL SUGIONO TG. PINGGIR, SEKUPANG | 1.13133 | 103.92832 | 16460.318 | 55 | IOH & TSEL | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-05-11 | 2026-05-20 | 2026-06-30 | [8 empty] | Survey Report |  | 2026-05-21 | 2026-06-14 | 2026-06-09 |  | 2026-06-15 | 2026-06-17 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | SPH scrap onsite area batam need DRM | 2026-05-25 | 2026-05-25 | JSA No.26/TSA/HSE/05/2026 | 2026-05-25 | 2026-05-25 |  | Approved | Approved |  |  | Dismantle Equipment | NY release |  | 49 |  |  | 0
337 | CMI | RLC | Nasional | #NAME? | 2026-07-07 | E3400063 | ID-YO-06145 | SINDUHARJO | 11 | EMA | DI YOGYAKARTA | Kab. Sleman | DSN.GADINGAN,DSA SINDUHARJO, KEC NGAGLIK | -7.71724 | 110.407 |  | 52 | IOH, Tsel, XL | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-07-01 | [10 empty] | Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
338 | CMI | RLC | Nasional | #NAME? | 2026-07-07 | E3400063 | ID-YO-06145 | SINDUHARJO | 11 | EMA | DI YOGYAKARTA | Kab. Sleman | DSN.GADINGAN,DSA SINDUHARJO, KEC NGAGLIK | -7.71724 | 110.407 |  | 52 | IOH, Tsel, XL | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-07-01 | [10 empty] | Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
339 | CMI | RLC | Nasional | #NAME? | 2026-07-07 | E3400063 | ID-YO-06145 | SINDUHARJO | 11 | EMA | DI YOGYAKARTA | Kab. Sleman | DSN.GADINGAN,DSA SINDUHARJO, KEC NGAGLIK | -7.71724 | 110.407 |  | 52 | IOH, Tsel, XL | Greenfield | SST 4 Legs | Relocation Equipment | [7 empty] | 2026-07-01 | [10 empty] | Survey | [26 empty] | Relocation Equipment
340 | CMI | RLC | Nasional | #NAME? | 2026-07-13 | R3270681 | ID-JB-02511 | JAPARA KUNINGAN | 10 | CMI | JAWA BARAT | Kab. Kuningan | Jl. Karang Muncang, Jepara, Kec. Japara, Kabupaten Kuningan | -6.89619 | 108.5167 | 6828.525 | 51 | XLS | Greenfield | SST 4 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-07-14 | 2026-07-14 | 2026-12-12 | [8 empty] | Survey Report |  | 2026-07-29 | 2026-07-31 | 2026-07-29 |  | 2026-07-31 | 2026-07-31 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 5 |  |  | 0
341 | CMI | RLC | Nasional | #NAME? | 2026-07-13 | R3270681 | ID-JB-02511 | JAPARA KUNINGAN | 10 | CMI | JAWA BARAT | Kab. Kuningan | Jl. Karang Muncang, Jepara, Kec. Japara, Kabupaten Kuningan | -6.89619 | 108.5167 | 6828.525 | 51 | XLS | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-07-14 | 2026-07-14 | 2026-12-12 | [8 empty] | Survey Report |  | 2026-07-29 | 2026-07-31 | 2026-07-29 |  | 2026-07-31 | 2026-07-31 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 5 |  |  | 0
342 | CMI | RLC | Nasional | #NAME? | 2026-07-13 | R3270681 | ID-JB-02511 | JAPARA KUNINGAN | 10 | CMI | JAWA BARAT | Kab. Kuningan | Jl. Karang Muncang, Jepara, Kec. Japara, Kabupaten Kuningan | -6.89619 | 108.5167 | 6828.525 | 51 | XLS | Greenfield | SST 4 Legs | Relocation Equipment | [5 empty] | NY Submit |  | 2026-07-14 | 2026-07-14 | 2026-12-12 | [8 empty] | Survey Report |  | 2026-07-29 | 2026-07-31 | 2026-07-29 |  | 2026-07-31 | 2026-07-31 | 1st BOQ App on ISAAC | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 5 |  |  | 0
343 | CMI | RLC | Nasional | #NAME? | 2026-07-13 | R6200094 | ID-KU-03075 | JUWATA PERMAI | 18 | CMI | KALIMANTAN UTARA | Kota Tarakan | Juata Permai, Kota Tarakan, Kalimantan Utara | 3.36448 | 117.55021 | 13212.913 | 71 |  | Greenfield | SST 3 Legs | Dismantle Tower | [5 empty] | NY Submit |  | 2026-07-25 | 2026-07-27 | [9 empty] | Survey Report |  | 2026-07-29 | 2026-07-31 | 2026-07-29 |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | waiting BOQ pass TI sign | [6 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
344 | CMI | RLC | Nasional | #NAME? | 2026-07-13 | R6200094 | ID-KU-03075 | JUWATA PERMAI | 18 | CMI | KALIMANTAN UTARA | Kota Tarakan | Juata Permai, Kota Tarakan, Kalimantan Utara | 3.36448 | 117.55021 | 13212.913 | 71 |  | Greenfield | SST 3 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-07-25 | 2026-07-27 | [9 empty] | Survey Report |  | 2026-07-29 | 2026-07-31 | 2026-07-29 |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | waiting BOQ pass TI sign | [6 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
345 | CMI | RLC | Nasional | #NAME? | 2026-07-13 | R6200094 | ID-KU-03075 | JUWATA PERMAI | 18 | CMI | KALIMANTAN UTARA | Kota Tarakan | Juata Permai, Kota Tarakan, Kalimantan Utara | 3.36448 | 117.55021 | 13212.913 | 71 |  | Greenfield | SST 3 Legs | Relocation Equipment |  |  | Survey | 2026-07-24 | 2026-07-30 | Expired |  | 2026-07-25 | 2026-07-27 | [9 empty] | Survey Report |  | 2026-07-29 | 2026-07-31 | 2026-07-29 |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | waiting BOQ pass TI sign | [6 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0
346 | CMI | RLC | Nasional | #NAME? | 2026-07-15 | R3350202 | ID-JT-01739 | RAYA TAHUNAN KALIPANG | 11 | CMI | JAWA TENGAH | Kab. Grobogan | DUSUN KALIPANG.RT.001/RW. 001, KEL. KALIPANG, KEC.GABUS, KAB. GROBOGAN | -7.14027 | 111.214 |  | 52 |  | Greenfield | SST 3 Legs | Dismantle Kamuflase | [5 empty] | NY Submit |  | 2026-07-18 | 2026-07-25 | [9 empty] | Survey Report |  | 2026-07-18 |  |  | 2026-07-22 | 2026-07-25 |  | Upload 1st BOQ & BAN Isaac | [6 empty] | NY Submit |  | 2026-07-25 | 2026-07-25 | JSA No.43/TSA/HSE/07/2026 | 2026-07-25 | 2026-07-25 | SWP-HSE-143 | Approved | Approved |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
347 | CMI | RLC | Nasional | #NAME? | 2026-07-16 | E1200036 | ID-SU-03792 | BANDARA BINAKA | 1 | EMA | SUMATERA UTARA | Kab. Nias | DESA HILIWETO GIDO KECAMATAN GIDO KABUPATEN NIAS | 1.11684 | 97.7269 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-07-20 | 2026-07-20 |  |  | 2026-07-23 | [6 empty] | Dismantle Perangkat |  | 2026-07-18 | 2026-07-18 | NA | 2026-07-24 |  |  | BAN App | [6 empty] | NY Submit | 20.07.26 Dism equip done DRM (waiting BAN Full Sign) | [6 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
348 | CMI | RLC | Nasional | #NAME? | 2026-07-16 | R3580776 | ID-JI-10048 | Jalan ahmad Yani 2 | 15 | CMI | JAWA TIMUR | Kota Surabaya | JL. Grand Ruko Ahmad Yani park No. 151P, Kel. Jemur Wonosari, Kec. Wonocolo, Kota Surabaya | -7.32839 | 112.732 |  | 17 + 7 |  | Rooftop | Pole | Dismantle Equipment |  |  | Survey | 2026-07-29 | 2026-08-04 | Expired |  | 2026-07-17 |  |  |  | 2026-07-22 | [6 empty] | Dismantle Perangkat | 20.07.26 Dismantle XLS 22.07.26 Dismantle IOH temporary reinstall S3 | 2026-07-18 | 2026-07-22 |  |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
349 | CMI | RLC | Nasional | #NAME? | 2026-07-16 | R3580776 | ID-JI-10048 | Jalan ahmad Yani 2 | 15 | CMI | JAWA TIMUR | Kota Surabaya | JL. Grand Ruko Ahmad Yani park No. 151P, Kel. Jemur Wonosari, Kec. Wonocolo, Kota Surabaya | -7.32839 | 112.732 |  | 17 + 7 |  | Rooftop | Pole | Relocation Equipment | [5 empty] | NY Submit |  | 2026-07-17 | [10 empty] | Survey |  | 2026-07-18 | 2026-07-22 |  |  |  |  | 1st BOQ Pass TI | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0
350 | CMI | RLC | Nasional | #NAME? | 2026-07-16 | R3580798 | ID-JI-10049 | Puri Indah Lestari | 15 | CMI | JAWA TIMUR | Kab. Sidoarjo | Bapak Sukemi, Perumahan Puri Indah Lestari Blok ED 01, Desa Sungon, Kec. Suko, Kab. Sidoarjo, Propinsi Jawa Timur | -7.45296 | 112.682 | 637.8405 | 13 + 12 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-07-23 | 2026-07-29 | Expired |  | 2026-07-27 | 2026-07-28 | 2026-08-19 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2026-07-29 |  | JSA No.53/TSA/HSE/07/2026 | 2026-07-29 |  | SWP-HSE-153 | Submit | Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
351 | CMI | RLC | Nasional | #NAME? | 2026-07-16 | E3500230 | ID-JI-06398 | MIC_GALUNGGUNG | 15 | EMA | JAWA TIMUR | Kota Malang | JL. JOMBANG III, KELURAHAN GADING KASRI, KECAMATAN KLOJEN, KOTAMADYA MALANG, JAWA TIMUR | -7.96716 | 112.614 | 496.77 | 6 + 6 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-07-23 | 2026-07-29 | Expired |  | 2026-07-27 | 2026-07-28 | 2026-08-01 | [8 empty] | Survey Report |  | 2026-07-28 |  | 2026-07-28 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit |  | 2026-08-04 |  | JSA No.51/TSA/HSE/07/2026 | 2026-08-04 |  | SWP-HSE-151 | Submit | Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
352 | CMI | RLC | Nasional | #NAME? | 2026-07-20 | R1800057 | ID-LA-09506 | GEDUNG BANDAR RAHAYU |  | CMI | LAMPUNG | Kab. Tulang Bawan | BRATASENA ADIWARNA KEC. DENTE TELADAS KAB. TUBA | -4.58919 | 105.819 | 7260.324 | 45 |  | Greenfield | SST 4 Legs | Dismantle Tower |  |  | Survey | 2026-07-23 | 2026-07-29 | Expired |  | 2026-07-30 |  | 2026-08-16 | [8 empty] | Survey | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
353 | CMI | RLC | Nasional | #NAME? | 2026-07-23 | E1600102 | ID-SS-04323 | IP_PLG | 4 | EMA | SUMATERA SELATAN | Kota Palembang | JL JEND SUDIRMAN NO 147 KEL 17 ILIR KEC ILIR TIMUR I KODYA PALEMBANG PROP SUMATERA SELATAN | -2.98418 | 104.757 | 393.5295 | 27 + 4 |  | Rooftop | Pole | Dismantle Tower |  |  | Survey | 2026-07-25 | 2026-07-30 | Expired |  | 2026-07-25 | 2026-07-25 | 2026-08-07 | [8 empty] | Survey Report | [7 empty] | NY Submit | [6 empty] | NY Submit |  | 2026-07-29 | 2026-07-31 | JSA No.52/TSA/HSE/07/2026 | 2026-07-29 |  | SWP-HSE-152 | Approved | Submit |  |  | Dismantle Tower | NY release |  | 0 |  |  | 0
354 | CMI | RLC | Nasional | #NAME? | 2026-06-30 | R3270702 | ID-JB-02532 | PABUARAN (CIREBON) | 10 | CMI | JAWA BARAT | Kab. Cirebon | KH ZAENAL ARIFIN NO68 PABUARAN LOR , KC PABUARAN KB CIREBON - JAWA BARAT | -6.90332 | 108.718 | 6828.525 | 51 | XLS | Greenfield | SST 3 Legs | Dismantle Equipment | [5 empty] | NY Submit |  | 2026-07-08 | 2026-07-15 | 2026-09-30 | [8 empty] | Survey Report |  | 2026-07-27 |  | 2026-07-28 |  |  |  | Engineering Structural Manager App | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  | Dismantle Equipment | NY release |  | 0 |  |  | 0
355 | CMI | RLC | Nasional | #NAME? | 2026-07-16 | E1200036 |  | BANDARA BINAKA | 1 | EMA | SUMATERA UTARA | Kab. Nias | DESA HILIWETO GIDO KECAMATAN GIDO KABUPATEN NIAS | 1.11684 | 97.7269 | 22120.78 | 70 |  | Greenfield | SST 4 Legs | Relocation Equipment | [5 empty] | NY Submit |  | 2026-07-20 | 2026-07-20 | [9 empty] | Survey Report |  | 2026-07-28 | 2026-07-29 | NA | DRM |  |  | need DRM | [6 empty] | NY Submit | waiting DRM Reinstall equipment | [6 empty] | NY Submit | NY Submit |  |  | Relocation Equipment | NY release |  | 0 |  |  | 0
356 | CMI | RLC | Nasional | #NAME? | 2026-07-28 | E3200182 | ID-JB-05137 | GEULIS_RESORT | 10 | EMA | JAWA BARAT | Kab. Bogor | Gn. Geulis, Kabupaten Bogor, Jawa Barat | -6.6269 | 106.86487 | 18868.812 | 70 | IOH & XLS | Greenfield | SST 4 Legs | Rebuild_LOS Survey JAW-JB-CBI-0515 to JAW-JB-BGR-0421 | [5 empty] | NY Submit |  | 2026-07-30 | 2026-07-31 | [7 empty] | 2026-07-31 |  | Survey LOS App | [7 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit | 2026-07-31 | 2026-07-31 | Rebuild_LOS Survey | NY release |  | 0 |  |  | 0 |  |  |  | po ny release
357 | CMI | RLC | Nasional | #NAME? | [22 empty] | NY Submit | [20 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  |  | NY release |  | 0 |  |  | 0
358 | CMI | RLC | Nasional | #NAME? | [22 empty] | NY Submit | [20 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  |  | NY release |  | 0 |  |  | 0
359 | CMI | RLC | Nasional | #NAME? | [22 empty] | NY Submit | [20 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  |  | NY release |  | 0 |  |  | 0
360 | CMI | RLC | Nasional | #NAME? | [22 empty] | NY Submit | [20 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  |  | NY release |  | 0 |  |  | 0
361 | CMI | RLC | Nasional | #NAME? | [22 empty] | NY Submit | [20 empty] | NY Submit | [6 empty] | NY Submit | [7 empty] | NY Submit | NY Submit |  |  |  | NY release |  | 0 |  |  | 0
Formulas:
Validitas Permit = IF([Expired]="ds","Submit",IF([Expired]="","NY Submit",IF([Expired]<TODAY(),"Expired",IFERROR(DATEDIF(TODAY(),[Expired],"d"),""))))
Aging PO = IF([Update Progress]="Drop", "Drop", IF(ISBLANK([App 1st BOQ & BAN Isaac]), 0, IF(ISBLANK([PO Release]), DATEDIF([App 1st BOQ & BAN Isaac],TODAY(),"d"), DATEDIF([App 1st BOQ & BAN Isaac],[PO Release],"d") ) ) )
Aging PO Variation 1 = IF([Update Progress]="Drop", "Drop", IF(ISBLANK([App 2nd BOQ & BAN Isaac]), 0, IF(ISBLANK([PO Variation 1 Release]), DATEDIF([App 2nd BOQ & BAN Isaac],TODAY(),"d"), DATEDIF([App 2nd BOQ & BAN Isaac],[PO Variation 1 Release],"d") ) ) )